PROGRAMME OF KEY TASKS FOR 3 STREAM WASTE COLLECTION SERVICE

| # DATE | DAY | ACTION |
| --- | --- | --- |
| 30 JUNE | MONDAY | - Start of collections on Phase II. |
| 20 JUNE | FRIDAY | - Last day for delivery of wheeled bins and information leaflets to properties on Phase II |
| 9 JUNE | MONDAY | - Finalise press release for CA&T on 19/26 May, Longridge News on 20/27 May, Lancashire Telegraph week commencing 26 May. |
| 27 MAY | TUESDAY | - Delivery of wheeled bins to properties on Phase II to start today (including leaflets) – allows 4 weeks delivery period. |
| 23 MAY | FRIDAY | - Last day by which letters to properties on Phase II are to be received by residents advising of new arrangements and delivery of bins. - Last day by which new information leaflets are to be supplied to RVBC from printers ready to be handed to Titan. |
| 6 MAY | TUESDAY | - Start distribution of letters to properties in Phase II advising of new arrangements and delivery of wheeled bins – allows 3 week delivery period. |
| 2 MAY | FRIDAY | - Last day by which Titan require full address list for Chipping and delivery of wheeled bins. |
| 1 MAY | THURSDAY | - Final amendments to leaflets and calendars and send to printer for production. |
| 30 APRIL | WEDNESDAY | - Return of second proofs from printer re leaflets and calendars. |
| 21 APRIL | MONDAY | - Last date for letter data to PMM. |
| 18 APRIL | FRIDAY | - Return of first proofs for leaflets and calendars from printers. |
| 15 APRIL | TUESDAY | - Start sorting data for plans for collection points. - Start production of delivery point plans and letters. - Last day for numbers of bins to Titan. |
| 14 APRIL | MONDAY | - Results from Entec. |
| 11 APRIL | FRIDAY | - Send details to printer re leaflets and calendars. |
| 7 APRIL | MONDAY | - Data to Entec for re-evaluation. - Start draft of letters (Consult with Councillors). |
| 4 APRIL | FRIDAY | - Final results of Councillor consultation to feed into database. |
| # DATE | DAY | ACTION |
| 28 MARCH | FRIDAY | - End of period of consultation with Councillors re Phase II. |
| 24 MARCH | MONDAY | - GMJ on leave all week. |
| 14 MARCH | FRIDAY | - Confirm delivery dates with Titan. |
| 11 MARCH | TUESDAY | - Meeting of Community Committee – progress report. |
| 10 MARCH | MONDAY | - PMcG on leave all week. |
| 5 MARCH | WEDNESDAY | - Meeting of Leader, Chairman of Community Committee, Chief Executive, Director of Community Services and Street Scene Manager to discuss problem sites that remain unresolved from Phase I. |
| 3 MARCH | MONDAY | - Start of Councillor consultation period regarding proposals for Phase II. - Completion of Phase I issues analysis ready for report to Community Committee. |
| 25 FEBRUARY | MONDAY | - BK starts 2 weeks leave. |
| 18 FEBRUARY | MONDAY | - Start of collection point re-evaluation process for Phase II including map analysis and site visits. - PMcG on leave all week. |
| 28 JANUARY | MONDAY | - Start review of Phase I issues and preparation of detailed list of locations where interim collection arrangements continue to be provided. |
| 15 JANUARY | TUESDAY | - Meeting of Community Committee – decisions taken regarding criteria for larger bins for residual waste and to continue to provide interim arrangements to some properties in rural areas of Phase I. |