LONGRIDGE SPORTS CENTRE – REPLACEMENT OF THE SYNTHETIC SPORTS PITCH

The project will generally consist of the taking up and removal of the existing sand filled synthetic pitch and shock pad and any resulting repairs/leveling of the macadam base. It is proposed to relay the pitch with a ‘sand dressed’ synthetic pitch over a suitable shock pad (insitu or precast).

General estimates have been provided by two contractors who specialize in carrying out this type of work.

It must be noted that any costing cannot be accurately made with regards to any repairs or leveling of the macadam base. An accurate price can only be established once the existing macadam base has been exposed and cleaned.

Below is a general list of the expected work that is required to be carried out:

- Site establishment

- Take up and remove from site the sand filled synthetic pitch

- Take up and remove from site the shock pad

- Sweep and clean macadam base

- Repair/level macadam base to within allowable tolerances

- Lay insitu or pre cast rubber shock pad

- Lay sand filled or sand dressed synthetic grass with in-laid hockey and football lines

- Make good site

It has been expressed that a ‘sand dressed’ synthetic surface is more preferable than the existing ‘sand filled’ surface as it is more durable and easier to maintain.

The ‘sand dressed’ option is generally £25,000 to £30,000 more than the ‘sand filled’ pitch.

The overall estimated costs that have been recently provided are as follows:

OPTION 1

‘Sand filled’ synthetic pitch (ranges from)	£120,000 to £130,000

+ estimated repair costs of macadam base	£5,000

+ 5% contingencies					£6520 to £6750

+ 8% design & supervision costs			£10,500 to £11,340

Estimated total cost 				£148,500 to £160,380

OPTION 2

‘Sand dressed’ synthetic pitch (ranges from)	£145,000 to £155,000

+ estimated repair costs of macadam base	£5,000

+ 5% contingencies					£7,500 to £8,000

+ 8% design & supervision costs			£12,560 to £13,440

Estimated total cost				£170,060 to £181,440

Repairs/leveling to the macadam base will most likely be required. The existing synthetic pitch surface has obvious undulations that may be a result of unevenness of the macadam base. If this is the case there are two preferred methods of correcting the levels to provide a playing surface within the permitted tolerances.

- To level isolated low patches with shock pad material if not more than 3-4mm. If however the low spot exceeds 4mm in depth then this option cannot be used.

- To level isolated low patches by excavating the macadam base and compacting the sub-base prior to inlaying with macadam to finish flush with surrounding surface.

- To level isolated low patches by building up the low spot with 6mm macadam and using additional insitu shock pad material to level off.

A rough estimate for the cost of ‘patching’ any isolated areas of the tarmac base ranges from £20/m2 to £25/m2 and with an estimated 200m2 that may, as a worst-case scenario, need patching. The additional costs therefore amount to between £4000 and  £5000 are have been included in the estimated total cost.