## Sheet1
ALL WEATHER PITCH - LONGRIDGE
2008 | MONTH | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | October
| Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Decisions/ Costing | bar: April 3 to April 4
Select List | bar: April 3 to April 4
Tender (production) | bar: April 3 to May 9
Report to Committee | bar: June 10
Tender Period (30/5 to 20/6) | bar: June 10 to June 12
Tender Evaluation / Award of Contract | bar: June 13 to July 16
Construction period (24/7 to 31/8)
Inspection and Handover | bar: August 22
Maintenance Period | bar: September 23 to October 31
Half Term
Summer break