RIBBLE VALLEY BOROUGH COUNCIL

REPORT TO POLICY AND FINANCE COMMITTEE

Agenda Item No

meeting date: 	23 SEPTEMBER 2008

title:	SERVICE PLAN UPDATE

submitted by: 	DIRECTOR OF RESOURCES

principal author: 	MARSHAL SCOTT

1	PURPOSE

  - To inform member of the progress made during 2008/09 with the action plans for the following Service Plans covered by this committee

- Revenues and Benefits

- Financial Services

- Computer Services

- Legal Services

  - Relevance to the Council’s ambitions and priorities - Each service plan sets out and demonstrates how that service links to the council’s ambitions and priorities.

2	BACKGROUND

  - These service plans were approved by this committee at its meeting on 29 January 2008.

  - Each service plan was prepared following an agreed template which included a detailed, comprehensive action plan setting out the objectives for the service over the coming period.  Expected outcomes and deadlines were also included in the action plans.

  - It was agreed that progress with the individual service action plans should be reported to committee half yearly.

3	ACTION PLANS

  - The individual action plans are attached as follows:

- Annex a)  Revenues and Benefits

- Annex b)  Financial Services

- Annex c)  Computer Services

- Annex d)  Legal Services

4	CONCLUSION

4.1	Members should consider the progress made with each service plan and make any comments felt necessary.

DIRECTOR OF RESOURCES

PF40-08/JP/AC

11 September 2008

Annex A

| Revenues and Benefits Action Plan Monitoring Report Report Author: Mark Edmondson Generated on: 10 September 2008 |  |
| --- | --- |

Efficient Administration & Collection of Council Tax

| Action | Description | Expected Outcome | Status | Progress | Due Date | Start Date | Completed Date | Assigned To | Latest progress update from assigned user |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Complete NFI SPD exercise | Complete NFI SPD exercise | Completion of exercise within current resources |  | 0 % | 31/03/2009 | 01/04/2008 |  | Mark Edmondson | 10/09/2008 Exercise not completed during 2008/9 due to data protection concerns. Will be completed during 2009/10 |
| Payment of refunds by BACS | Payment of refunds by BACS | To start paying all refunds by BACS |  | 50 % | 31/03/2009 | 01/04/2008 |  | Mark Edmondson | 09/09/2008 Work currently ongoing - on target form completion for 31 March 09 |
| Review written policies | Review all written policies | Completion of reviews of all written policies |  | 25 % | 31/03/2009 | 01/04/2008 |  | Mark Edmondson | 10/09/2008 Work ongoing |
| Produce joint leaflet with LCC | Produce joint leaflet with LCC | Completion of joint leaflet, produced in partnership with LCC |  | 100 % | 31/03/2009 | 01/04/2008 | 01/04/2008 | Mark Edmondson | 10/09/2008 Joint leaflet produced and issued with annual bills |

To Provide an Efficient Cashiering Service for the Whole Council

| Action | Description | Expected Outcome | Status | Progress | Due Date | Start Date | Completed Date | Assigned To | Latest progress update from assigned user |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Automate banking processes | Automate banking processes | All processes to be automated |  | 0 % | 31/03/2009 | 01/04/2008 |  | Mark Edmondson | 10/09/2008 Unable to commence due to greater priority for IT resources. |
| Review service | Review cashiers service | Review of cashiers service to be completed |  | 25 % | 31/03/2009 | 01/04/2008 |  | Mark Edmondson | 10/09/2008 Review ongoing. |

Efficient Administration & Collection of National Non-Domestic Rates

| Action | Description | Expected Outcome | Status | Progress | Due Date | Start Date | Completed Date | Assigned To | Latest progress update from assigned user |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Review written policies | Review all written policies | Completion of reviews of all written policies |  | 25 % | 31/03/2009 | 01/04/2008 |  | Mark Edmondson | 10/09/2008 Work ongoing. |
| Review relief’s | Review relief’s | Relief’s reviewed |  | 25 % | 31/03/2009 | 01/04/2008 |  | Mark Edmondson | 10/09/2008 Work ongoing. |
| Implement changes to Empty Property Rate Relief | Implement changes to Empty Property Rate Relief | Implementation of changes to Empty Property Rate Relief |  | 100 % | 31/03/2009 | 01/04/2008 | 01/04/2008 | Mark Edmondson | 10/09/2008 Changes successfully implemented. |

Effective Administration of Benefit Fraud

| Action | Description | Expected Outcome | Status | Progress | Due Date | Start Date | Completed Date | Assigned To | Latest progress update from assigned user |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Investigate cases identified from CT NFI SPD exercise | Investigate cases identified from CT NFI SPD exercise | Investigation of potential benefit fraud cases as identified through CT NFI SPD exercise |  | 0 % | 31/03/2009 | 01/04/2008 |  | Mark Edmondson | 10/09/2008 Did not take part in this exercise during 2008/9 due to data protection concerns. Will be undertaking exercise in 2009/10. |
| Proactively target fraud | Proactively target fraud | Reduction in number of benefit fraud cases |  | 50 % | 31/03/2009 | 01/04/2008 |  | Mark Edmondson | 10/09/2008 Work ongoing. |
| National Fraud Initiative | Fraud identified and reduced | Reduction in number of benefit fraud cases |  | 25 % | 31/03/2009 | 01/04/2008 |  | Mark Edmondson | 10/09/2008 Work ongoing. |

Efficient Administration of Council Tax Benefit

| Action | Description | Expected Outcome | Status | Progress | Due Date | Start Date | Completed Date | Assigned To | Latest progress update from assigned user |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Take Up campaign | Successful Take Up campaign | Increase in take-up of CTB and 2AR |  | 50 % | 31/03/2009 | 01/04/2008 |  | Mark Edmondson | 10/09/2008 Work ongoing. |
| Review targets, having regard to changes to PI's | Review targets, having regard to changes to PI's | Review of council tax benefit targets to be completed |  | 100 % | 31/03/2009 | 01/04/2008 | 16/06/2008 | Mark Edmondson | 10/09/2008 Targets reviewed and amended. |

Efficient Administration of Housing Benefit

| Action | Description | Expected Outcome | Status | Progress | Due Date | Start Date | Completed Date | Assigned To | Latest progress update from assigned user |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Review performance standards | Review performance standards | All performance standards reviewed |  | 25 % | 31/03/2009 | 01/04/2008 |  | Mark Edmondson | 10/09/2008 Work ongoing. |
| Take Up campaign | Successful Take Up campaign | Increased housing benefit take-up |  | 50 % | 31/03/2009 | 01/04/2008 |  | Mark Edmondson | 10/09/2008 Work ongoing. |
| Implement Local Housing Allowance | Introduction & implementation of Local Housing Allowance | Implementation of Local Housing Allowance |  | 100 % | 31/03/2009 | 01/04/2008 | 01/04/2008 | Mark Edmondson | 10/09/2008 LHA successfully implemented. |
| Convert Local Authority claims to Housing Association | Convert all Local Authority claims to Housing Association | Conversion of Local Authority claims to Housing Association |  | 100 % | 31/03/2009 | 01/04/2008 | 01/04/2008 | Mark Edmondson | 10/09/2008 All claims successfully converted. |

| Action Status |
| --- |
|  | Completed |  | Overdue |
|  | Assigned; In Progress |  | Cancelled |
|  | Unassigned; Check Progress; Not Started |  |  |

Annex B

| Financial Services Action Plan Monitoring Report Report Author: Michelle Haworth Generated on: 11 September 2008 |  |
| --- | --- |

To Plan & Monitor the Use of the Authority's Available Resources in an Orderly & Structured Manner in Order to Achieve the Authority's Stated Objectives

| Action | Description | Expected Outcome | Status | Progress | Due Date | Start Date | Completed Date | Assigned To | Latest progress update from assigned user |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| To prepare a sustainable budget within agreed timetable | To prepare a sustainable budget within agreed timetable |  |  | 2 % | 15/12/2008 | 01/04/2008 |  | Jane Pearson | 10/09/2008 Budget process commences with high level budget forecast for 2009/10 currently being prepared. To be reported to Sept P&F cttee. |
| To maximise returns from the safe investment of the Council's surplus funds | To maximise returns from the safe investment of the Council's surplus funds |  |  | 42 % | 31/03/2009 | 01/04/2008 |  | Jane Pearson | 09/09/2008 Full compliance with the council's Treasury Management Strategy up to end August. |
| To prepare budget monitoring reports for each service committee on a quarterly basis and submit an overall report to P&F committee | To submit quarterly budget monitoring reports by required date for relevant service committee | Quarterly budget monitoring reports submitted to relevant committees |  | 25 % | 31/03/2009 | 01/04/2008 |  | Jane Pearson | 09/09/2008 Quarterly budget monitoring reports have been reported to all service committees - latest reports in July cycle. |
| To continue to develop e-procurement purchasing methods | To implement changes to the way the Council procures goods and services via e-procurement and Civica Financials | Full use of Civica Financials |  | 100 % | 31/03/2009 | 01/04/2008 |  | Jane Pearson | 09/09/2008 All appropriate users have been trained in use of Procurement system. |

To close the 2007/8 accounts (including the closure of the HRA) in accordance with the Accounts & Audit regulations 2003

| Action | Description | Expected Outcome | Status | Progress | Due Date | Start Date | Completed Date | Assigned To | Latest progress update from assigned user |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| To publish the Statement of accounts by end of Sept 2008 | Publication of accounts on council’s website by end September 2008 | Publication of accounts on council’s website by end September 2008 |  | 95 % | 30/09/2008 | 01/07/2008 |  | Jane Pearson | 09/09/2008 Final Statement of Accounts submitted to Accounts & Audit Committee on 17/9/08. |
| To prepare and agree a closure of accounts timetable with all relevant parties including external auditors | Production of agreed timetable which aims to achieve the closure of our accounts by the statutory deadlines | Production of agreed timetable which aims to achieve the closure of our accounts by the statutory deadlines (end of March 2008) |  | 100 % | 02/04/2008 | 01/04/2008 | 01/04/2008 | Jane Pearson | 17/07/2008 Timetable reported to Policy and Finance Committee on 01/04/08 and approved. |
| To complete the Statement of Accounts and have them approved by members by end June 2008 | Approval by members by end of June 2008 | Approval by members by end of June 2008 |  | 100 % | 30/06/2008 | 01/04/2008 | 25/06/2008 | Jane Pearson | 17/07/2008 Statement of Accounts for 2007/08 submitted to A&A cttee on 25/6/08 and subsequently approved. Available on website. |
| To prepare and publish a summary statement of accounts | Publication of summary statement of accounts by end September 2008 | Publication of summary statement of accounts by end September 2008 |  | 100 % | 30/09/2008 | 01/07/2008 | 04/09/2008 | Jane Pearson | 09/09/2008 Summary statement of accounts for 2007/08 prepared following audit of main accounts and has been published on our website. |

To comply with all applicable statutory requirements and codes of practice, and to report accurately and on time

| Action | Description | Expected Outcome | Status | Progress | Due Date | Start Date | Completed Date | Assigned To | Latest progress update from assigned user |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| To close the 2007/8 accounts (including the closure of the HRA) in accordance with the Accounts & Audit regulations 2003 | To close the 2007/8 accounts (including the closure of the HRA) in accordance with the Accounts & Audit regulations 2003 |  |  | 98 % | 30/09/2008 | 01/04/2008 |  | Jane Pearson | 10/09/2008 Accounts successfully closed in accord with A&A regs. Audit complete. Accounts to be published by end of Sept 2008 incl Auditors report. |
| To prepare the Council’s Statement of Accounts in an efficient manner complying with the SORP | To ensure SORP changes are properly assessed and are complied with | Successful sign off of Accounts and minimum number of errors on ISA260 report |  | 100 % | 15/09/2008 | 01/07/2008 | 08/09/2008 | Jane Pearson | 10/09/2008 Positive, pleasing responses from external auditors during audit of the accounts. No material misstatements not adjusted for. No errors on ISA260 report. |
| To successfully comply with the submission of Whole of Government Accounts | To submit our Whole of Government Accounts Return following sign off by our Auditors | Successful sign off of return by our auditors and submission to central government by end September 2008 |  | 100 % | 30/09/2008 | 01/07/2008 | 29/08/2008 | Jane Pearson | 09/09/2008 Whole of Government Accounts prepared before deadline and successfully audited by PwC. They will forward to DCLG before 1 October 2008. |

To deliver the Annual Internal Audit Plan by 31 March 2009

| Action | Description | Expected Outcome | Status | Progress | Due Date | Start Date | Completed Date | Assigned To | Latest progress update from assigned user |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| To complete all audits within the agreed allocation of resources | Minimum 90% of audits to be completed by 31 March 2009 | Minimum 90% audits completed by end of March 2009 |  | 42 % | 31/03/2009 | 01/04/2008 |  | Jane Pearson | 10/09/2008 Internal Audit Staff actively carrying out audits as per IA Plan for 2008/09, on schedule to meet full plan by end March 2008. |
| To produce reports and recommendations as per audit plan | 100% of recommendations to be implemented by 31 March 2009 | 100% of recommendations to be implemented |  | 42 % | 31/03/2009 | 01/04/2008 |  | Jane Pearson | 10/09/2008 Internal Audit Staff actively checking implementation of recommendations are carried out. |

To make all payments properly due accurately, on time and in accordance with law, standing orders, financial regulations, CIPFA guidance, and to maintain accurate, up to date, auditable records

| Action | Description | Expected Outcome | Status | Progress | Due Date | Start Date | Completed Date | Assigned To | Latest progress update from assigned user |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| To pay all creditors accurately and promptly | To pay all creditors accurately and promptly |  |  | 42 % | 31/03/2009 | 01/04/2008 |  | Jane Pearson | 10/09/2008 First Quarter's performance = 96.8% of invoices paid promptly. Checks carried out on accuracy of payments have been successful. |
| To pay employees and member allowances accurately and promptly | To pay employees and members allowances on time and accurately | Maximum 2% payroll errors |  | 42 % | 31/03/2009 | 01/04/2008 |  | Jane Pearson | 09/09/2008 April, May, June, July & August salaries and members allowances all paid on time and accurately |

To manage and minimise the financial and other risks to which the authority would otherwise be exposed

| Action | Description | Expected Outcome | Status | Progress | Due Date | Start Date | Completed Date | Assigned To | Latest progress update from assigned user |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| To deliver the Annual Internal Audit Plan by 31 March 2009 | To deliver the Annual Internal Audit Plan by 31 March 2009 |  |  | 42 % | 31/03/2009 | 01/04/2008 |  | Jane Pearson | 10/09/2008 Internal Audit Staff actively carrying out audits as per IA Plan for 2008/09, on schedule to meet full plan by end March 2008. |
| To maintain the Council's risk register in an accurate and timely manner | To ensure that the Grace system is kept up to date and that quarterly reports are produced | Production of half yearly reports on the outcome of the review of the Grace system |  | 50 % | 31/03/2009 | 01/04/2008 |  | Jane Pearson | 10/09/2008 Risk Management Update report prepared up to end Sept 2008. Will be reported to Overview & Scrutiny Cttee end of Sept 2008. |
| To complete all main system reconciliation’s promptly | To review, record and monitor 100% of reconciliation’s each month | 100% completed authorised reconciliation’s |  | 42 % | 31/03/2009 | 01/04/2008 |  | Jane Pearson | 09/09/2008 Monthly reconciliation’s carried out and authorised up to end of August 2008. |
| To ensure the authority is adequately and efficiently insured | To review the authority's insurance arrangements on an annual basis | Completion of review of insurance arrangements |  | 100 % | 30/06/2008 | 01/06/2008 | 20/06/2008 | Jane Pearson | 17/07/2008 Currently within Long Term Agreement until June 2011 (with option to extend by further 2 years). However annual review carried out of level of cover on all our polices. Report submitted for information to Policy and Finance on 29/7/08. |

To maximise amounts recovered from sundry debtors

| Action | Description | Expected Outcome | Status | Progress | Due Date | Start Date | Completed Date | Assigned To | Latest progress update from assigned user |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| To raise sundry debtor invoices promptly | Issue of 100% of invoices promptly | Issue of 100% of invoices promptly |  | 42 % | 31/03/2009 | 01/04/2008 |  | Jane Pearson | 10/09/2008 All sundry debtor invoices have been promptly raised from control sheets up to end of August 2008. |
| To issue reminder letters promptly and take recovery action in accordance with the Council's schedule | 100% compliance with the agreed recovery schedule | 100% compliance with the agreed recovery schedule |  | 42 % | 31/03/2009 | 01/04/2008 |  | Jane Pearson | 09/09/2008 Automatic recovery schedule in operation generates reminder letters each day and changes recovery status. |

To maximise returns from the safe investment of the Council's surplus funds

| Action | Description | Expected Outcome | Status | Progress | Due Date | Start Date | Completed Date | Assigned To | Latest progress update from assigned user |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| To monitor cash flow and investments on a daily basis & take appropriate action | Monitoring of cash flow and investments on a daily basis, and comparison of investment returns with the three monthly LIBID rate. Target of 260. | Maximised returns from the safe investment of the Council's surplus funds. |  | 42 % | 31/03/2009 | 01/04/2008 |  | Jane Pearson | 09/09/2008 Daily monitoring of cash flow carried out by Senior Accountant, including comparison of rates. |
| To maintain the Council's list of approved institutions with regard to credit ratings | To maintain the Council's list of approved institutions with regard to credit ratings | 100% compliance with list of approved institutions |  | 42 % | 31/03/2009 | 01/04/2008 |  | Jane Pearson | 09/09/2008 Up to date list of approved institutions maintained and full compliance against this for lending to date has been achieved. |

To maximise the collection and recovery of sums due to the authority, and to maintain accurate, up to date and auditable records

| Action | Description | Expected Outcome | Status | Progress | Due Date | Start Date | Completed Date | Assigned To | Latest progress update from assigned user |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| To maximise amounts recovered from sundry debtors | To maximise amounts recovered from sundry debtors |  |  | 42 % | 31/03/2009 | 01/04/2008 |  | Jane Pearson | 10/09/2008 Each sundry debtor invoice is automatically routed through system recovery groups and stages. At each stage the appropriate recovery action is automatically taken, e.g. 1st Reminder Letter, 2nd Reminder Letter, Referral to Legal, Court Action Letter etc. Payments Staff manage the recovery streams and negotiate payment by installment where necessary. |
| To ensure all grants and subsidies due to the authority are claimed by the specified deadline | To maintain a register of the grants and subsidies due to the Council | Submission of 100% audited subsidy/grants claims by the relevant deadline |  | 42 % | 31/03/2009 | 01/04/2008 |  | Jane Pearson | 10/09/2008 Grants claimed where appropriate to end of August 2008 & necessary claims sent to Pwc for auditing. |

To pay all creditors accurately and promptly

| Action | Description | Expected Outcome | Status | Progress | Due Date | Start Date | Completed Date | Assigned To | Latest progress update from assigned user |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| To pay all undisputed creditor invoices within 30 days | To pay all undisputed creditor invoices within 30 days | Minimum 97% of undisputed creditor invoices paid within 30 days |  | 42 % | 31/03/2009 | 01/04/2008 |  | Jane Pearson | 09/09/2008 Prompt payment of creditor invoices achieved (96.8% for Q1). Creditor operators trained in importance of prompt entering of invoices. |
| To increase the number of payments made by BACS | To increase the number of payments made by BACS to at least 80% | Minimum 80% of all payments to be made using BACS |  | 42 % | 31/03/2009 | 01/04/2008 |  | Jane Pearson | 09/09/2008 All new creditors initially only offered payment by BACS. Only in rare circumstances is cheque payment offered. |

To prepare a sustainable budget within agreed timetable

| Action | Description | Expected Outcome | Status | Progress | Due Date | Start Date | Completed Date | Assigned To | Latest progress update from assigned user |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| To prepare an agreed budget timetable by end of October 2008 | To prepare an agreed budget timetable by end of October which is approved by P&F committee | Approval of budget timetable by P&F committee by end of October 2008. |  | 5 % | 31/10/2008 | 01/04/2008 |  | Jane Pearson | 09/09/2008 Budget Timetable will be prepared in October 2008 following approval of Budget strategy in September. |
| To identify options for growth/reduction in the service planning process | Inclusion of growth/reductions in committee budget reports for January cycle | Inclusion of growth/reductions in committee budget reports in January cycle |  | 0 % | 15/12/2008 | 01/04/2008 |  | Jane Pearson | 09/09/2008 Service plans for 2009/10 yet to be formulated. Will be prepared within the coming months & incorporate growth and reduction. |

Annex C

| IT Action Plan Monitoring Report Report Author: Michelle Haworth Generated on: 12 September 2008 |  |
| --- | --- |

ICT SP Action Plan

| Action | Description | Expected Outcome | Status | Progress | Due Date | Start Date | Completed Date | Assigned To | Latest progress update from assigned user |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Network Infrastructure | To maintain a network infrastructure that will accommodate the increasing IT requirements of all services. | Maintaining an adequate network infrastructure. |  | 50 % | 31/03/2009 | 01/04/2008 |  | Peter Hothersall | 11/09/2008 Budget cuts are making this increasingly difficult to achieve. |
| Server Replacement Program | Investigate and implement a server replacement program for all corporate systems. This will impact on other services. | Server replacement program complete by 2010. |  | 15 % | 31/03/2009 | 01/04/2008 |  | Peter Hothersall | 11/09/2008 A 3 year capital budget has been allocated. |
| Internet Connection Speed | Expansion of our internet connection speed as demands grow. | Maintaining an adequate connection speed. |  | 50 % | 31/03/2009 | 01/04/2008 |  | Peter Hothersall | 11/09/2008 Budget cuts are making this increasingly difficult to achieve. |
| Microsoft Active Directory Domain Migration | Migrate our current Microsoft Active Directory 2000 domain to a 2003 domain due to loss of Microsoft support for 2000 in 2009. | Migration complete. |  | 0 % | 31/03/2009 | 01/04/2008 |  | Peter Hothersall | 11/09/2008 Budget cuts are making this increasingly difficult to achieve. |
| NLPG Interface Implementation | Implement technical requirements of the NLPG interfaces to all gazetteer based computer systems. | All interfaces implemented. |  | 0 % | 31/03/2009 | 01/04/2008 |  | Peter Hothersall | 11/09/2008 Budget cuts are making this increasingly difficult to achieve. |
| Contact Centre Support | Further support of the Contact Centre development regarding the CRM system and back office integration. | Contact Centre CRM development and integration to back office systems achieved. |  | 25 % | 31/03/2009 | 01/04/2008 |  | Peter Hothersall | 11/09/2008 Further support is not currently available because of requirements of other systems and budget cuts are making back office integration increasingly difficult to achieve. |
| Auditors' Recommendations | Implementation of the external auditors' recommendations. | Implementation of the external auditors' recommendations. |  | 10 % | 31/03/2009 | 01/04/2008 |  | Peter Hothersall | 11/09/2008 Partially complete. |

Annex D

| Legal Services Action Plan Monitoring Report Report Author: Diane Rice Generated on: 10 September 2008 |  |
| --- | --- |

Parent Title: Legal Services SP Action Plan 08/09

| Action | Description | Expected Outcome | Status | Progress | Due Date | Start Date | Completed Date | Assigned To | Latest progress update from assigned user |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Embedding Licensing (Alcohol) | Performance indicators to be set and satisfied | Performance indicators to be set by end June 2008, and satisfied as necessary |  | 50 % | 31/03/2009 | 01/04/2008 |  | Diane Rice | 10/09/2008 Work ongoing, pending refinements to LALPAC system to record appropriate measures |
| Improving Involvement in Contracts / Agreements | All agreements received by legal | All agreements received by legal |  | 40 % | 31/03/2009 | 01/04/2008 |  | Diane Rice | 10/09/2008 Work ongoing, in process of improving instruction method etc |
| Developing Proper Asset Management Function | Corporate property function operational | Corporate property function operational |  | 35 % | 31/03/2009 | 01/04/2008 |  | Diane Rice | 10/09/2008 The records/deeds (40 boxes in total) to be handed over to RVH have now been catalogued and the remaining task of revising and improving out own records is ongoing. |
| Embedding Ethical Framework | Standards Committee review arrangements with outside bodies | Standards Committee review arrangements with outside bodies by end October 2008 |  | 65 % | 31/10/2008 | 01/04/2008 |  | Diane Rice | 10/09/2008 Interim report to May committee final report to October committee. |
| Gambling | New systems implemented, now need to be imbedded | New gambling systems embedded |  | 100 % | 30/06/2008 | 01/04/2008 | 31/07/2008 | Diane Rice | 10/09/2008 system embedded |
| Improving Enforcement to Licensing (Taxis & Private Hire) | Penalty points scheme operational, Enforcement increased | Penalty points scheme operational by end April 2008. Aim to increase enforcement. |  | 100 % | 30/04/2008 | 01/04/2008 | 14/08/2008 | Diane Rice | 10/09/2008 Scheme operational, regular referrals to Committee, changes to grant of licence requirements to support improved standards. |
| Housing Stock Transfer | Successful transfer of housing assets | Successful transfer of housing assets |  | 100 % | 30/04/2008 | 01/04/2008 |  | Diane Rice | 10/09/2008 Transfer completed 31st March 2008 |
| Improving Information Systems | Increased capacity to provide information, including under Freedom of Information Act. More record systems | Increased capacity to provide information, including under Freedom of Information Act. More record systems |  | 100 % | 30/04/2008 | 01/04/2008 | 01/07/2008 | Diane Rice | 10/09/2008 Freedom of information system fully operational, records improved |

| Action Status |
| --- |
|  | Completed |
|  | Assigned; In Progress |
|  | Unassigned; Check Progress; Not Started |
|  | Overdue |
|  | Cancelled |

# Text boxes

INFORMATION