RIBBLE VALLEY BOROUGH COUNCIL

INFORMATION

REPORT TO POLICY AND FINANCE COMMITTEE

Agenda Item No

meeting date: 	18 NOVEMBER 2008

title:	TIMETABLE FOR BUDGET SETTING

submitted by: 	FINANCIAL SERVICES MANAGER

principal author: 	JANE PEARSON

1	PURPOSE

1.1	To inform you of the timetable for setting the 2009/10 budget.

2	BACKGROUND

2.1	Part of our Corporate Governance arrangements is to set out clearly to both officers and members the Council’s budget timetable.

3	BUDGET TIMETABLE

3.1	Attached at Annex 1 is a comprehensive timetable covering the main elements of the Council’s budget setting progress together with key dates and responsibilities.

The timetable has been circulated to Service Managers and the Corporate Management Team.

4	RECOMMENDED THAT COMMITTEE

  - Approve the budget timetable.

FINANCIAL SERVICES MANAGER

PF55-08/JP/AC

|  | Budget Timetable 2009/10 | Who? | When? |
| --- | --- | --- | --- |
|  | Task |  |  |
| 1 | Consideration of Budget Forecast | Policy and Finance Committee/BWG | 23 Sept 2008 |
| 2 | Provision of Budget information for Service Plans | Accountants | Sept/Oct 2008 |
| 3 | CMT to meet to discuss Service Plans with Service Managers | CMT | October 2008 |
| 4 | Service Plans to be discussed with Members | Corporate Policy Officer | October 2008 |
| 5 | Send out % time allocation sheets to service managers for purpose of calculating departmental recharges | Accountants | 10 October 2008 |
| 6 | Completion of Recharge time allocation sheets | Service Managers/individual members of staff | 15 October 2008 |
| 7 | Calculation of Taxbase for council tax setting purposes for 2009/10 | FSM/ Revenues Manager | 31 October 2008 |
| 8 | Send out Precept Letters to Parish Councils | Accounting Technician | 14 November 2008 |
| 9 | Finalise Revised Capital Programme for 2008/09 | FSM/Capital Working Group | Mid November 2008 |
| 10 | Calculate Capital Charges | Accountant - TH | Mid November 2008 |
| 11 | Consideration of Draft Medium Term Financial Strategy | Budget Working Group | December 2008 |
| 12 | Announcement of Provisional Settlement information from DCLG | DCLG | Mid to late November 2008 |
| 13 | Send out new Capital Scheme Pro Formas for completion by Service Managers | Financial Services Manager | 30 November 2008 |
| 14 | Identification of Growth Items/Gershon Efficiency Savings | Service Managers | November 2008 |
| 15 | Review of Fees and Charges | Service Managers/Accountants | November 2008 |
| 16 | Agreement of Service Plans | Committees | January 2009 |
| 17 | Final Calculations of Recharges | Accountants | 30 November 2008 |
| 18 | Assess Implications of Settlement for RVBC | DOR/FSM | Early Dec 2008 |
| 19 | DOR to agree taxbase with Chairman & Shadow Chairman of Policy and Finance Committee | DOR | Early Dec 2008 |
| 20 | Notification of Supported Borrowing Allocation | DCLG | December 2008 |
| 21 | Inform Members of Implications for RVBC of Settlement | DOR/FSM | Early December 2008 |
| 22 | CMT to consider latest budgetary position | CMT | 17 December 2008 |
| 23 | BWG to meet to consider latest indications of 2009/10 budget | BWG | Mid December |
| 24 | Calculate Collection Fund Surplus/Deficit and apportion between Precepting Authorities | FSM | Mid December |
| 25 | Finalisation of Draft Budget Reports | Accountants | 19 December 2008 |
| 26 | Deadline for receipt of parish precept letters | Accounting Technician | 5 January 2009 |
| 27 | Notify Lancashire County Council, Police and Fire Authorities of Collection Fund Surplus/Deficit and Taxbase | FSM | Mid January 2009 |
| 28 | Consideration of Budget Reports by Committees | Service Committees | 13 January 2009 to 27 January 2009 |
| 29 | Meetings of Budget Working Group to consider budgetary recommendations to give Special Policy & Finance Cttee | BWG | Mid to late January 2009 |
| 30 | Settlement Debate in Parliament |  | Late January, early February 2009 |
| 31 | Meeting of Special Policy and Finance Committee to approve budget and recommend Council Tax to Full Council | DOR/FSM | 10 February 2009 |
| 32 | Provision of Financial Information for Council Tax Leaflet | FSM to Revenues Manager | Mid February 2009 |
| 33 | Set up meeting with Industrialists to consider budget | PA to Director of Resources | February 2009 |
| 34 | Receipt of Precept Letters from Major Precepting Authorities | FSM | 1 March 2009 |
| 35 | Full Council to agree Budget and set Council Tax | Members | 10 March 2009 |
| 36 | DOR, FSM, CMT to inform Service Mangers of agreed Budget |  | 13 March 2009 |
| 37 | Entering of Approved Budget onto Financials system | Accountants | Feb/March 2008 |
| 38 | Production of Budget Book | FSM | Mid March 2009 |