RIBBLE VALLEY BOROUGH COUNCIL

REPORT TO HOUSING COMMITTEE

Agenda Item No.

meeting date:	16 November 2006

title: 	General Report

submitted by:  	Director of Community Services

principal author:  	Rod Pearce

1	PURPOSE

1.1	To inform committee of the progress with the various schemes currently being undertaken.

2	Relevance to Council Ambitions and Priorities

- Council’s Ambitions - To make people’s lives safer and healthier and to protect and enhance the existing environmental quality of our area.

- Community Objectives - Encouraging energy efficiency measures across all sectors. Reducing the number of dwellings requiring improvements. Working with other agencies to reduce crime and fear of crime. Improving the participation of tenants and other partner agencies.

- Corporate Priorities - Objectives 1, 2 and 3.

- Other Considerations - The report supports the Council’s commitment to the Government’s Decent Homes Standard Initiative and the Home Energy Conservation Act.

3	SCHEMES

3.1	Repair & Improvements 2006/2007

Contractor			Craig Hambling Ltd

Contract Value	£214,628.16

Commencement date		23 October 2006

Completion date		23 March 2007

Progress

The contract will consist of the replacement of 32 Nr kitchens, window replacements to 12 properties and the replacement of 44 Nr doors. Work to replace windows and doors commenced on site on 06 November 2006.

3.2	Kitchen Replacements 2006/2007

Contractor 		David Johnston Builders Ltd.

Contract Value		£177,638.50

Commencement date		30 October 2006

Completion date 	27 April 2007

Progress

The contract will consist of the replacement of 45 Nr kitchens. The site set up is now complete and work on site will commence week commencing13 November 2006.

  - Electrical Repairs & Testing 2006/2007

Contractor 		Jack Cunliffe (Blackpool) Ltd

Contract Value					£29,010.00

Commencement date 	20 November 2006

Completion date 	16 March 2007

Progress

Negotiations for the work are now complete. The works will consist of the electrical test and associated repairs of properties to remote villages.

  - Boiler Replacements 2006/2007

Progress housing has been commissioned to carry out boiler replacements within the gas servicing contract, primarily to replace non-serviceable and inefficient back boilers. At present 92 Nr boilers from a total of 126 Nr have been replaced.

4	Risk Assessment

4.1	The Approval of this report may have the following implications

4.2	Resources - The schemes can be funded from approved budgets.

4.3	Technical, Environmental and Legal - Clauses within all contracts require timbers to be sourced from sustainable managed forests, water fittings comply with water bye laws, the construction phase health and safety plan deals with identification, handling and disposal of asbestos products.

In accordance with commitments towards the Home energy conservation act, the council has promoted several energy efficiency schemes. These include a continuation of grant-funded schemes similar to those previously promoted. These provide energy efficiency measures such as cavity wall insulation, loft insulation, draught proofing and solar energy.

4.4	Replacement boilers are condensing boilers of high efficiency that will reduce the amount of energy used and the amount of CO2 emitted to the atmosphere.

4.5	Political - None

4.6	Reputation - could enhance the view some customers have of the Council.

5	RECOMMENDED THAT COMMITTEE

5.1	Note the contents of this report.

Director of Community Services

Background papers: Working Files

For further information, please contact Rod Pearce direct dial 01200 414525

28 July 2026