RIBBLE VALLEY BOROUGH COUNCIL

DECISION

REPORT TO COMMUNITY COMMITTEE

Agenda Item No

meeting date: 	16 JANUARY 2007

title:	REVISED CAPITAL PROGRAMME 2006/07 AND PROPOSED

PROGRAMME 2007/12

submitted by: 	DIRECTOR OF RESOURCES

principal author: 	JANE PEARSON

1	PURPOSE

1.1	To approve the revised programme for the current year and also the future five-year capital programme for this committee.

2	BACKGROUND

2.1	This report will review the following:

i)	The current year's programme.

ii)	Draft programme of schemes to be carried out in the following five years (2007/08 to 2011/12).

3	ORIGINAL PROGRAMME 2006/07 – CURRENT FINANCIAL YEAR

3.1	The original capital programme for the current year included schemes at a total estimated cost of £1,049,510.

3.2	Unfinished schemes from 2005/06, totalling £153,200, have been added to the original programme.  This is shown in Annex 1 and known as slippage.

4	REVISING THE CURRENT YEAR'S PROGRAMME

4.1	We have now discussed in some detail each scheme in the programme with budget holders and revised the programme to reflect likely expenditure this year.  This is shown in Annex 1, alongside the original estimate.

4.2	Updated capital evaluation forms completed by the responsible officers, for all these schemes are attached at Annex 2 (YELLOW).

4.3	In summary, the revised programme is:

| Total Approved Budget £ | Revised Estimate for Current Year £ | Expenditure to Date £ |
| --- | --- | --- |
| 1,212,710 | 1,077,870 | 711,810 |

5	DRAFT PROGRAMME 2007/08 TO 2011/12

5.1	New schemes have been put forward by officers to form part of our five-year capital programme.  Annex 3 shows the draft programme for this committee.

5.2	However, this is really only the first attempt to ascertain future schemes.  Therefore, Annex 3 is a possible programme that will require further consideration by the Budget Working Group and by Policy and Finance Committee who will want to make sure that it is affordable, both in capital and revenue terms.

5.3	A new capital scheme pro forma has been completed for any new schemes added to the five year programme by the relevant officer.  These are attached at Annex 4 (BLUE).

5.4	Members should therefore consider the schemes in Annex 3 and any amendments you may wish to make at this stage.

5.5	Capital evaluation forms for all new schemes approved for next year (2007/08) will be completed and reported to committees in the next cycle.

5.6	A summary of the five-year programme for Community Committee is shown below:

| 2007/08 £ | 2008/09 £ | 2009/10 £ | 2010/11 £ | 2011/12 £ |  | Total £ |
| --- | --- | --- | --- | --- | --- | --- |
| 1,776,800 | 852,100 | 340,300 | 353,700 | 35,300 |  | 3,358,200 |

6	RECOMMENDED THAT COMMITTEE

6.1	Approve the revised capital programme for 2006/07 as set out in Annex 1.

6.2	Consider the future five-year programme for 2007/8 to 2011/12 as set out in Annex 3 and agree any amendments you wish to make.

FINANCIAL SERVICES MANAGER

CM1-07/JP/AC

5 JANUARY 2007

| # COMMUNITY COMMITTEE ANNEX 1 REVISED CAPITAL PROGRAMME 2006/07 |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Budget Analysis |  |  |  |  |  | Expenditure Analysis |
| Cost | Schemes | Original | Slippage | Additional | Total | Revised | Budget | Total |
| Centre |  | Estimate |  | Approvals | Approved | Estimate | moved to | Expenditure |
|  |  | 2006/07 |  |  | Budget |  | 2007/08 | To Date |
|  |  | £ | £ | £ | £ | £ | £ | £ |
|  | Community Committee |  |  |  |  |  |  |  |
| BPIMP | Brungerley Park Improvement scheme |  | 1,900 | 10,000 | 11,900 | 11,900 |  | 4,475 |
| BPSCT | Replacement of Brungerley sculpture trail | 5,400 | 15,300 |  | 20,700 | 20,700 |  | 7,586 |
| CASED | Castle/Museum/Heritage Improvement Scheme |  | 20,800 | -13,250 | 7,550 | 20,800 |  | 22,746 |
| CLPAT | Cemetery - Resurface paths and roadways |  | 1,600 |  | 1,600 | 1,600 |  | 0 |
| CLWAL | Cemetery - Rebuild wall |  | 11,600 |  | 11,600 | 20,000 |  | 19,435 |
| CSLOT | Castle Lottery Scheme |  |  |  |  | 213,000 |  | 168,539 |
| CYCIN | Cycling Initiatives | 5,500 |  |  | 5,500 | 5,500 |  | 13,137 |
| EDICR | Edisford Consultantancy Costs |  |  |  |  | 9,200 |  | 9,200 |
| FENCW | Fencing Improvements at Edisford All Weather Pitch | 15,000 |  |  | 15,000 | 15,000 |  | 13,548 |
| FOODR | Football pitches drainage | 16,900 |  |  | 16,900 | 15,100 |  | 15,030 |
| KEEPR | Castle Keep Repairs - Phase 1 |  |  | 13,250 | 13,250 | 79,400 |  | 0 |
| LFIRD | Provision of Fire Escape at Longridge Depot | 6,300 |  |  | 6,300 |  | 6,300 | 0 |
| LSREC | Longridge Sports Centre Reception (moved from 05/06) | 54,410 |  |  | 54,410 |  | 54,410 | 0 |
| LOADS | Loading Shovel Waste Transfer Station |  | 60,000 |  | 60,000 | 60,200 |  | 60,184 |
| LOCHG | Grant Aid to Longridge Action Group re Civic Hall |  | 10,000 |  | 10,000 | 10,000 |  | 0 |
| PBOIL | Pool - Replace boiler and calorifier | 96,300 |  |  | 96,300 |  | 96,300 | 0 |
| PCRPE | Replace Slaidburn Toilets (moved from 05/06) | 113,040 | -4,300 |  | 108,740 | 108,740 |  | 107,232 |
| PESTS | Replace Pest Control Suzuki Van - Y378 XHG | 10,000 |  |  | 10,000 | 9,100 |  | 9,065 |
| PLAYF | Improvements to children's play areas |  | 29,600 |  | 29,600 | 34,200 |  | 34,195 |
| PLAYG | Improvements to children's play areas | 35,300 |  |  | 35,300 | 35,300 |  | 33,159 |
| POSEC | Pool - Security & Fire alarm | 13,200 |  |  | 13,200 | 13,200 |  | 6,040 |
| RALSH | Replace Grounds Maintenance Allet Shaver with Dennis cylinder mower | 2,245 |  |  | 2,245 | 2,250 | 0 | 2,245 |
| RCOLT | Replace N313 SWK Dennis Refuse Collection Vehicle | 180,000 |  |  | 180,000 | 180,000 |  | 0 |
| REBIN | Recycling and Residual Waste Containers | 172,500 |  |  | 172,500 |  | 172,500 | 0 |
| RGBUF | Replace Grounds Maintenance 4 Allett Buffalo mowers with 1 Dennis | 6,985 |  |  | 6,985 | 6,980 |  | 6,985 |
| RGDCW | Replace Grounds Maintenance Hayter ride-on N383 DCW | 20,800 |  |  | 20,800 | 20,700 |  | 20,700 |
| RGMOW | Purchase of 4 mowing machines & Trailer | 7,700 |  |  | 7,700 | 5,200 |  | 5,159 |
| RGOFR | Replace Grounds Maintenance G190 OFR mini tractor | 9,000 |  |  | 9,000 | 9,000 |  | 9,000 |
| RIBCA | Refurbishment of Ribchester Public Conveniences | 37,200 |  |  | 37,200 | 37,200 |  | 17,887 |
| RLIFT | Bin Lifts (x2) for existing Refuse Vehicles | 30,900 |  |  | 30,900 |  | 30,900 | 0 |
| ROSEG | Rose Garden Castle Grounds |  |  |  |  | 56,000 |  | 48,802 |
| RPCHA | Ribblesdale Pool - Refurbish Staff changing rooms & external store |  | 6,700 |  | 6,700 | 7,100 |  | 7,104 |
| RVERG | Replace Grounds Maintenance 3 Blade Verge Cutter Haytor Condor | 4,500 |  |  | 4,500 | 4,500 |  | 4,497 |
| RWFBU | Replace Grounds Maintenance Vehicle R485 FBU Iveco 7.5tonne | 37,000 |  |  | 37,000 | 35,100 |  | 35,090 |
| RWKEG | Replace P715 KEG Ford General Works Vehicle | 15,400 |  |  | 15,400 | 12,100 |  | 12,040 |
| RWXCK | Replace Grounds Maintenance Vehicle P996 XCK with Transit van | 13,500 |  |  | 13,500 | 11,800 |  | 11,726 |
| SDIMP | Improvements to Salthill Depot budget moved from 05/06 | 6,530 |  |  | 6,530 | 7,000 |  | 7,004 |
| SYNCA | Longridge Sports Centre Replace carpet on synthetic pitch | 133,900 |  |  | 133,900 |  | 133,900 | 0 |
|  | Total Community Committee | 1,049,510 | 153,200 | 10,000 | 1,212,710 | 1,077,870 | 494,310 | 711,810 |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  | ANNEX 2 |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | BPIMP |
| Name of Scheme | BRUNGERLEY PARK IMPROVEMENT SCHEME |  |  |  |
| Officer Responsible | GRAHAM JAGGER |  |  |  |
| Description of Scheme | Various improvements to Brungerley Park |  |  |  |
| Benefits of Scheme | Appearance of park will be enhanced |  |  |  |
| Project Timetable | Start Date | October 2003 |  |  |
|  | Completion Date | October 2006 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Response to any consultation exercise that may be undertaken |  |  |  |

|  |  |  |  |  | Cost Centre | BPIMP |
| --- | --- | --- | --- | --- | --- | --- |
| Financial Summary | Slippage from 2005/06: |  |  |  | £1,900 |  |
|  | Additional Approvals: |  |  |  | £10,000 |  |
|  | Approved Budget for Scheme: |  |  |  | £11,900 |  |
|  | Expected Total Cost of Scheme: |  |  |  | £11,900 |  |
|  | Approved by Committee: |  |  |  | Council |  |
|  | Date: |  |  |  | 4 March 2003 |  |
|  | Minute Ref: |  |  |  |  |  |
| Expenditure Analysis |  | Actual Expenditure 2003/04 £ | Actual Expenditure 2004/05 £ | Actual Expenditure 2005/06 £ | Expected Expenditure 2006/07 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |
|  | Cost of Work | 26,657 | 124 | 763 | 11,900 | 39,444 |
|  | Retention (Show separately) |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |
|  | Internal Salaries | 5,017 | 367 | 1,252 | 0 | 6,636 |
|  | TOTAL | 31,674 | 491 | 2,015 | 11,900 | 46,080 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |
| End August 2003 | Work to start November and complete by March. An extra £10,000 has been secured by external funding. |  |  |  |  |  |
| End Dec 2003 | Work is in progress and to proposed timetable. Will be complete by end of March. |  |  |  |  |  |
| End June 2004 | Work is almost complete. Paths about to be resurfaced. Dependent on weather. |  |  |  |  |  |
| End Nov 2004 | As above, some works outstanding. |  |  |  |  |  |
| End June 2005 | £10,000 grant to be received from Lancashire County Council to resurface paths. Work to be carried out soon. |  |  |  |  |  |
| End Sept 2005 | Work to be carried out by Council’s General Works section and is scheduled to start soon. |  |  |  |  |  |
| End Dec 2005 | Work delayed due to other priorities but will be complete end of February 2006. |  |  |  |  |  |
| End Sept 2006 | Work still underway with final footpath surfacing to be completed by end of October 2006 |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | BPSCT |
| Name of Scheme | REPLACEMENT OF BRUNGERLEY SCULPTURE TRAIL |  |  |  |
| Officer Responsible | CHRIS HUGHES |  |  |  |
| Description of Scheme | Replace public art pieces in Brungerley Park |  |  |  |
| Benefits of Scheme | Improve environment of park |  |  |  |
| Project Timetable | Start Date | April 2003 |  |  |
|  | Completion Date |  |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
|  |  | Develop annual projects to replace one sculpture each year for the duration of the project |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None, although each piece will rely on a partnership between community groups and artists |  |  |  |

|  |  |  |  |  |  | Cost Centre | BPSCT |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Original Budget for Current Year: |  |  |  |  | £5,400 |  |
| Summary | Slippage from 2005/06 |  |  |  |  | £15,300 |  |
|  | Total budget for current year: |  |  |  |  | £20,700 |  |
|  | Expected Total Cost of Scheme: |  |  |  |  | £20,810 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 4 March 2003 |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  | Actual Expenditure 2003/04 £ | Actual Expenditure 2005/06 £ | Expected Expenditure 2006/07 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  | 110 | 0 | 20,700 | 20,810 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  | 110 | 0 | 20,700 | 20,810 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End August 2003 |  | Potential to expand trail. External funding is being explored before project is started. Still able to implement original timetable. |  |  |  |  |  |
| End Dec 2003 |  | Work still being carried out on project details. |  |  |  |  |  |
| End June 2004 |  | Waiting to see if our investment can be matched through money within the Market Towns Initiative to provide an enhanced scheme. |  |  |  |  |  |
| End Nov 2004 |  | As above, however need to set a deadline with Clitheroe the Future to determine whether an enhanced scheme is possible otherwise Ribble Valley to run its own scheme early next year. Due to this suggest money moved to 2005/06. |  |  |  |  |  |
| End June 2005 |  | In final stages of securing match funding. Will shortly be commencing scheme. Artist to start work. |  |  |  |  |  |
| End Sept 2005 |  | Awaiting to confirm funding via Clitheroe the Future. Sent out initial expressions of interest for commissions for local artist to start the work. |  |  |  |  |  |
| End Dec 2005 |  | Work to start January 2006. |  |  |  |  |  |
| End March 2006 |  | Problems in delay in securing matched funding via Clitheroe The Future. Just heard that we have £12,000 and so are able to start someone. Artists have been commissioned but this will mean that the bulk of the expenditure will be in 2006/07. |  |  |  |  |  |
| End Sept 2006 |  | Sculptures being made for 2006-07 expenditure for installation from Dec – March. |  |  |  |  |  |
| End Dec 2006 |  | Plan to install sculptures for end March |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | CASED |
| Name of Scheme | CASTLE IMPROVEMENT SCHEME - GROUNDS |  |  |  |
| Officer Responsible | CHRIS HUGHES/GRAHAM JAGGER |  |  |  |
| Description of Scheme | Improvements to paths, lighting etc |  |  |  |
| Benefits of Scheme | Appearance and safety |  |  |  |
| Project Timetable | Start Date | Autumn 2004 |  |  |
|  | Completion Date | Summer 2005 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Any consultation process that may be required Sourcing of suitable materials Impact on park users |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | None |  |  |  |

|  |  |  |  |  |  | Cost Centre | CASED |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Slippage from 2005/06: |  |  |  |  | £20,800 |  |
| Summary | Transferred to Castle Keep Scheme: |  |  |  |  | -£13,250 |  |
|  | Approved Budget for Current Year: |  |  |  |  | £7,550 |  |
|  | Revised Estimate: |  |  |  |  | £20,800 |  |
|  | Expected Total Cost of Scheme: |  |  |  |  | £96,259 |  |
|  | Approved by Committee: |  |  |  |  | Special Policy & Finance |  |
|  | Date: |  |  |  |  | 6 February 2001 |  |
|  | Minute Ref: |  |  |  |  | 667 |  |
| Expenditure Analysis |  |  |  | Actual Expenditure 2004/05 £ | Actual Expenditure 2005/06 £ | Expected Expenditure 2006/07 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  | 31,625 | 29,886 | 17,300 | 78,811 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  | 2,048 | 11,900 | 3,500 | 17,448 |
|  | TOTAL |  |  | 33,673 | 41,786 | 20,800 | 96,259 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End June 2004 |  | A report detailing full proposal is elsewhere on the agenda. Work will start autumn 2004. |  |  |  |  |  |
| End Nov 2004 |  | Work has now started, landscaping, tree work, paths and drives, as reported to committee July 2004. Funding to be received from English Heritage in respect of works carried out by L & R Consultants for the provision of the lottery application for the castle. |  |  |  |  |  |
| End June 2005 |  | Work around the old bottom bowling green has been carried out. New seats etc purchased and to be installed soon. Some work done in the former rose garden as part of joint project with Ribblesdale School and Lancashire County Council. |  |  |  |  |  |
| End Sept 2005 |  | Works to rose garden to recommence during first week in November. Preparation work to be done by our General Works section. Contractor has been appointed for specialist surfacing work. |  |  |  |  |  |
| End Dec 2005 |  | Works underway and should be substantially complete early in the new year. |  |  |  |  |  |
| End Sept 2006 |  | Work substantially complete |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | CLPAT |
| Name of Scheme | CEMETERY – RESURFACE PATHS AND ROADWAYS |  |  |  |
| Officer Responsible | ROD PEARCE |  |  |  |
| Description of Scheme | Resurface worn surfaces on all paths and roadways |  |  |  |
| Benefits of Scheme | Improved health and safety |  |  |  |
| Project Timetable | Start Date | August 2005 |  |  |
|  | Completion Date | September 2005 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Inclement weather. Burials that may be booked to take place during works. Workload of the general works section. |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | None |  |  |  |

|  |  |  |  |  |  | Cost Centre | CLPAT |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Slippage from 2005/06: |  |  |  |  | £1,600 |  |
| Summary | Approved Budget for Current Year: |  |  |  |  | £1,600 |  |
|  | Expected Total Cost of Scheme: |  |  |  |  | £19,970 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 1 March 2005 |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  |  | Actual Expenditure 2005/06 £ | Expected Expenditure 2006/07 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  | 16,751 | 1,600 | 18,351 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  | 1,619 |  | 1,619 |
|  | TOTAL |  |  |  | 18,370 | 1,600 | 19,970 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| June 2005 |  | Condition of roads and paths to be assessed shortly so as to decide on which parts of the site the money will be best spent on. |  |  |  |  |  |
| End Sept 2005 |  | Tenders received for resurfacing work on 30 September 2005. Work expected to start on site in early November. |  |  |  |  |  |
| End Dec 2005 |  | Works complete. |  |  |  |  |  |
| End Sept 2006 |  | Works complete slippage to be utilised to provide seating area |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | CLWAL |
| Name of Scheme | CEMETERY - REBUILD WALL |  |  |  |
| Officer Responsible | ROD PEARCE |  |  |  |
| Description of Scheme | Rebuild collapsed boundary wall |  |  |  |
| Benefits of Scheme | Improved health and safety |  |  |  |
| Project Timetable | Start Date | July 2006 |  |  |
|  | Completion Date | January 2006 (anticipated) |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Inclement weather Access issues within cemetery |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | None |  |  |  |

|  |  |  |  |  |  | Cost Centre | CLWAL |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Slippage from 2005/06: |  |  |  |  | £11,600 |  |
| Summary | Approved Budget for Current Year: |  |  |  |  | £11,600 |  |
|  | Revised Estimate: |  |  |  |  | £20,000 |  |
|  | Expected Total Cost of Scheme: |  |  |  |  | £20,431 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 1 March 2005 |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  |  | Actual Expenditure 2005/06 £ | Expected Expenditure 2006/07 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  | 431 | 20,000 | 20,431 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  | 431 | 20,000 | 20,431 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| June 2005 |  | Design to be agreed. Initial costing to be provided by DSO for work. |  |  |  |  |  |
| End Sept 2005 |  | Works let and commenced on site in September. Savings anticipated. |  |  |  |  |  |
| End Dec 2005 |  | Works let and commenced on site in September. Savings anticipated. Anticipated completion end February 2006. |  |  |  |  |  |
| End Sept 2006 |  | Scheme complete July 06 overspend on scheme £7,834.76 several issues with original contractor failing to proceed diligently with the work therefore contract terminated. Replacement contractor prices exceeded budgets available. |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  |  |  | Cost Centre | CSLOT |
| Name of Scheme |  | CASTLE LOTTERY BID |  |  |  |  |
| Officer Responsible |  | CHRIS HUGHES |  |  |  |  |
| Description of Scheme |  | Preparation and submission stage 2 Lottery Bid for Castle Scheme |  |  |  |  |
| Benefits of Scheme |  | Benefits of Castle Lottery Project |  |  |  |  |
| Project Timetable |  | Start Date |  | Spring 2006 |  |  |
|  |  | Completion Date |  | December 2006 |  |  |
|  |  | Any Other Key Dates |  | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs |  | Securing all external funding |  |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose |  | No – cost of consultants built into scheme |  |  |  |  |
| What are the revenue implications of the scheme? |  | Refer to Community Committee |  |  |  |  |
| Costing Total Development costs Less HLF Grant RVBC Contribution | £212,987 £159,748 £53,247 |  | Say £213,000 Say £160,000 Say £53,000 |  |  |  |
| (To be met from Castle Lottery Scheme match funding in 5 year Capital Programme) |  |  |  |  |  |  |

|  |  |  |  |  |  | Cost Centre | CSLOT |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | RVBC contribution of |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £53,000 to be met |  |
|  | Approved by Committee: |  |  |  |  | from Lottery match |  |
|  | Date: |  |  |  |  | funding |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  |  |  |  | Expected Expenditure 2006/07 £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  | 213,000 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  |  | 213,000 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End Sept 06 |  | Final application submitted to HLF on 10th November |  |  |  |  |  |
| End Dec 06 |  | All works carried out by consultancy, bid submitted. £168k spent to date. Now need to make grant application to HLF. Remaining invoices to be paid soon. |  |  |  |  |  |

| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | CYCIN |
| Name of Scheme | CYCLING INITIATIVES |  |  |  |
| Officer Responsible | GRAHAM JAGGER |  |  |  |
| Description of Scheme | To facilitate two events and launch the cycling strategy |  |  |  |
| Benefits of Scheme | Promote cycling and its benefits and organise two major sporting events |  |  |  |
| Project Timetable | Start Date | April 2005 |  |  |
|  | Completion Date | August 2005 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
|  | 27 July 2005 3 August 2005 | Pendle/Ribble Valley road race Clitheroe town centre race |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Agreement to road closures. Opposition from town centre residents and businesses. Lack of additional sponsorship. Lack of community support. |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Part of the event planning will be to bring in additional organisational support, the cost of which is included in the budget. |  |  |  |
| What are the revenue implications of the scheme? | None |  |  |  |

|  |  |  |  |  |  |  |  |  | Cost Centre |  | CYCIN |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Revised Estimate: |  |  |  |  |  |  |  | £5,500 |  |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  |  |  |  | £15,000 |  |  |
|  | Approved by Committee: |  |  |  |  |  |  |  | Council |  |  |
|  | Date: |  |  |  |  |  |  |  | 2 March 2005 |  |  |
|  | Minute Ref: |  |  |  |  |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  |  |  |  | Actual Expenditure 2005/06 £ |  | Expected Expenditure 2006/07 £ |  | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  | 9,564 |  | 5,500 |  | 15,000 |
|  | Retention (show separately) |  |  |  |  |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  |  | 9,564 |  | 5,500 |  | 15,000 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |  |  |  |  |
| March 2005 |  | Planning for the two events (Pendle/Ribble Valley road race on Sunday, 27 July and the Clitheroe town centre race on Wednesday, 3 August) is well underway. The event on 3 August will also include activities during the day in the castle grounds and the official launch on that day of the Council’s cycling strategy. Publicity will start soon so as to maximise public awareness and spectator numbers. |  |  |  |  |  |  |  |  |  |
| June 2005 |  | The cycling strategy received approval of this committee on 17 May 2005. Arrangements for the Pendle/Ribble Valley road race on 27 July and the Clitheroe town centre race on 3 August are now in place. |  |  |  |  |  |  |  |  |  |
| End Sept 2005 |  | Extremely successful event held on 3 August in Clitheroe Town Centre. Balance of scheme funding will be used in 2006/07 to fund same event for next year. |  |  |  |  |  |  |  |  |  |
| End Dec 2005 |  | See above. Carry forward underspend to next financial year. |  |  |  |  |  |  |  |  |  |
| End March 2006 |  | Arrangements for the 2006/07 event are in hand and this money will be used to support it taking place. |  |  |  |  |  |  |  |  |  |
| End Sept 2006 |  | The Clitheroe Town Centre Cycle Race took place on Wednesday 2 August. Financial support from the business community did not meet with original expectations as reported to Committee on 12 September 2006. The balance of the budget in the sum of £2,500 will be used to support the work being done on the cycle facilities in Gisburn Forest and on activity at the Bowland Festival. |  |  |  |  |  |  |  |  |  |
| End Dec 2006 |  | With regards to the balance of funds left on CYCIN – approx £2,400 it was intended that this money was to be a match funding contribution towards a Grant Bid to fund the creation of new Mountain Bike Trails in Gisburn Forest. However, the Steering Group for this project has been unable to progress to the point of submitting a bid at this date and it is unlikely that even if a grant bid was to be submitted this year that we would receive approval before 31/3/07. The group expects to be in a position to bid for money by the summer. |  |  |  |  |  |  |  |  |  |
| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |  |  |  |  |  |  |  |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |  |  |  |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  |  |  |  |  |  | Cost Centre |  | EDICR |  |
| Name of Scheme |  |  | EDISFORD OPIONS APPRAISAL CONSULTANCY COSTS. |  |  |  |  |  |  |  |  |
| Officer Responsible |  |  | CHRIS HUGHES |  |  |  |  |  |  |  |  |
| Description of Scheme |  |  | Consultancy costs for Edisford Options Appraisal – production of report to outline management options for the Edisford site. |  |  |  |  |  |  |  |  |
| Benefits of Scheme |  |  |  |  |  |  |  |  |  |  |  |
| Project Timetable |  |  | Start Date |  |  | July 06 |  |  |  |  |  |
|  |  |  | Completion Date |  |  | October 06 |  |  |  |  |  |
|  |  |  | Any Other Key Dates |  |  | Description of Work |  |  |  |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs |  |  |  |  |  |  |  |  |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose |  |  | Cost of scheme - £9,200 to be met from Edisford Changing Rooms allocation in 5 year capital programme – 2007/08 |  |  |  |  |  |  |  |  |
| What are the revenue implications of the scheme? |  |  |  |  |  |  |  |  |  |  |  |

|  |  |  |  |  |  | Cost Centre | EDICR |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Revised Estimate for Current Year |  |  |  |  | 9,200 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | 9,200 |  |
|  | Approved by Committee: |  |  |  |  |  |  |
|  | Date: |  |  |  |  |  |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  |  |  |  | Expected Expenditure 2006/07 £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  |  |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  | 9,200 |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  |  | 9,200 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End Dec 06 |  | Final report produced by KPP Consultants and submitted to November Committee Meeting. |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | FENCW |
| Name of Scheme | FENCING IMPROVEMENTS AT EDISFORD ALL WEATHER PITCH |  |  |  |
| Officer Responsible | CHRIS HUGHES |  |  |  |
| Description of Scheme | Provision of backboards and higher fencing |  |  |  |
| Benefits of Scheme | Making people’s lives safer and healthier |  |  |  |
| Project Timetable | Start Date | October 2006 |  |  |
|  | Completion Date | One month from commencement |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
|  |  | As above |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Contractor delays, but would be minimal effect |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | No adverse implications. Possible increase due to greater flexibility |  |  |  |

|  |  |  |  |  |  | Cost Centre | FENCW |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £15,000 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £15,000 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 28 February 2006 |  |
|  | Minute Ref: |  |  |  |  | 755 |  |
| Expenditure Analysis |  |  |  |  |  |  | Expected Expenditure 2006/07 £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  | 15,000 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  |  | 15,000 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End March 2006 |  | The scheme is straightforward and only needs the procurement of a contractor to carry out the work. Work will start when there is least disruption to customers. |  |  |  |  |  |
| End Sept 2006 |  | Work complete |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | FOODR |
| Name of Scheme | FOOTBALL PITCHES DRAINAGE |  |  |  |
| Officer Responsible | GRAHAM JAGGER |  |  |  |
| Description of Scheme | Work to improve quality and durability of football pitches |  |  |  |
| Benefits of Scheme | Less games need to be cancelled and reduction in maintenance required |  |  |  |
| Project Timetable | Start Date | April 2006 |  |  |
|  | Completion Date | September 2006 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Weather conditions during summer |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | None |  |  |  |

|  |  |  |  |  |  | Cost Centre | FOODR |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £16,900 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £15,100 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 28 February 2006 |  |
|  | Minute Ref: |  |  |  |  | 755 |  |
| Expenditure Analysis |  |  |  |  |  |  | Expected Expenditure 2006/07 £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  | 14,880 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  | 620 |
|  | TOTAL |  |  |  |  |  | 15,100 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End March 2006 |  | Work needed on various pitches has been established. Contract document for works is being prepared and will be put out to tender shortly. Work should begin towards end of May 2006. |  |  |  |  |  |
| End Sept 2006 |  | Work carried out during May and June. Has shown improvement in quality of playing surfaces on pitches covered by scheme. |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | KEEPR |
| Name of Scheme | CASTLE KEEP IMPROVEMENTS – PHASE 1 |  |  |  |
| Officer Responsible | CHRIS HUGHES |  |  |  |
| Description of Scheme | Health and Safety improvements, permanent flood lighting and refurbishment of garden areas and signage |  |  |  |
| Benefits of Scheme | Improvements to keep |  |  |  |
| Project Timetable | Start Date | January 07 |  |  |
|  | Completion Date | March 07 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Securing all external funding |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose |  |  |  |  |
| What are the revenue implications of the scheme? | None |  |  |  |
| Funding | Phase 2 brought into 5 year Capital Programme - £110,000 in 2008/09 as a new bid |  |  |  |
|  | £ Total cost of Phase 1 = 79,400 To be funded from: Lancashire Environmental Fund -25,000 Clitheroe Rotary Club -1,800 Regional Park Grant -39,400 From RVBC 13,200 |  |  |  |
|  | (To be met from Castle Lottery scheme monies in 5 year capital prog) i.e. 2007/08 allocation reduced by £13,200 |  |  |  |

|  |  |  |  |  |  | Cost Centre | KEEPR |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | To be met from Castle |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | Lottery Scheme |  |
|  | Approved by Committee: |  |  |  |  |  |  |
|  | Date: |  |  |  |  |  |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2006/07 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 79,400 | 79,400 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 79,400 | 79,400 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End Dec 2006 |  | Started on site early Jan 07 with Phase 1 Scheme Grant application made to Regional Park (Approved) and also made to LEF. |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | LFIRD |
| Name of Scheme | PROVISION OF FIRE ESCAPE LONGRIDGE DEPOT |  |  |  |
| Officer Responsible | ROD PEARCE |  |  |  |
| Description of Scheme | The need for the provision of a first floor fire escape has been identified as a priority within the fire risk assessment. This will provide alternative means of escape from first floor work and storage areas. Within the scheme would also be the demolition of s single storey asbestos and brick store. |  |  |  |
| Benefits of Scheme | Health and safety and comply with fire precautions workplace regulation |  |  |  |
| Project Timetable | Start Date | June 2006 |  |  |
|  | Completion Date | June 2006 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Asbestos removal may overspend budget. |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | Minor addition to electricity bills for extra lighting to stairs |  |  |  |

|  |  |  |  |  |  | Cost Centre | LFIRD |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £6,300 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £6,300 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 28 February 2006 |  |
|  | Minute Ref: |  |  |  |  | 755 |  |
| Expenditure Analysis |  |  |  |  |  |  | Expected Expenditure 2006/07 £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  | 5,900 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  | 400 |
|  | TOTAL |  |  |  |  |  | 6,300 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End March 2006 |  | Scheme design to commence April 2006. Demolition of existing store March 2006. |  |  |  |  |  |
| End Sept 2006 |  | Scheme delayed due to need for asbestos removal. Estimates for fire escape requested. Anticipated commencement Feb 07. |  |  |  |  |  |
| End Dec 2006 |  | Quotes currently being sought for asbestos removal and demolition. Work anticipated to commence February 2007 |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | LOADS |
| Name of Scheme | LOADING SHOVEL WASTE TRANSFER STATION |  |  |  |
| Officer Responsible | GRAHAM JAGGER |  |  |  |
| Description of Scheme | Purchase of a loading shovel for bulk loading of waste |  |  |  |
| Benefits of Scheme | To facilitate the effective operation of the new waste transfer station |  |  |  |
| Project Timetable | Start Date | April 2005 |  |  |
|  | Completion Date | July 2005 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
|  | June 2005 | Purchase of item of plant |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Availability of suitable item of plant. Delivery period. Tendering process. Progress on construction of waste transfer station. Appointment of a suitable haulage contractor. Closure of Henthorn landfill site. |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | Associated costs of employing a driver are included in 2005/06 revenue budget. |  |  |  |

|  |  |  |  |  |  | Cost Centre | LOADS |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Revised Estimate: |  |  |  |  | £60,200 |  |
| Summary | Slippage from 2005/06: |  |  |  |  | £60,000 |  |
|  | Expected Total Cost of Scheme: |  |  |  |  | £60,184 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 2 March 2005 |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2006/07 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 60,184 | 60,184 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 60,184 | 60,184 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| March 2005 |  | Work is underway to establish the most suitable vehicle currently available on the market and budget costs. |  |  |  |  |  |
| June 2005 |  | Preliminary enquiries have been made for the purchase of a loading shovel for use in the new waste transfer station but as the project start has been delayed no firm prices have yet been sought. |  |  |  |  |  |
| End Sept 2005 |  | Purchase has been deferred due to delay in construction of Waste Transfer Station. Equipment will be ordered in this financial year but not put into use until June 2006. |  |  |  |  |  |
| End Dec 2005 |  | Suitable vehicle presently being secured. Delivery will be arranged for May 2006. |  |  |  |  |  |
| End Dec 2006 |  | Vehicle purchased and in use from beginning of August |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | LOCHG |
| Name of Scheme | GRANT AID TO LONGRIDGE ACTION GROUP FOR CIVIC HALL |  |  |  |
| Officer Responsible | CHRIS HUGHES |  |  |  |
| Description of Scheme | Improvements to reception/entrance |  |  |  |
| Benefits of Scheme | Improving access and better use of space |  |  |  |
| Project Timetable | Start Date | May 2005 |  |  |
|  | Completion Date |  |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Final costs will not change but timetable is reliant on Longridge Action Group signing their lease |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | None |  |  |  |

|  |  |  |  |  |  | Cost Centre | LOCHG |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Slippage from 2005/06: |  |  |  |  | £10,000 |  |
| Summary | Approved Budget for Current Year: |  |  |  |  | £10,000 |  |
|  | Expected Total Cost of Scheme: |  |  |  |  | £10,000 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 2 March 2005 |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2006/07 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 10,000 | 10,000 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 10,000 | 10,000 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| June 2005 |  | Awaiting receipt of proposal from Longridge Action Group. |  |  |  |  |  |
| End Sept 2005 |  | Still awaiting receipt of proposal from Longridge Action Group. |  |  |  |  |  |
| End Dec 2005 |  | Still awaiting receipt of proposal from Longridge Action Group. |  |  |  |  |  |
| End Sept 2006 |  | Designs for new reception being produced |  |  |  |  |  |
| End Dec 2006 |  | Designs still underway for new reception. |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | LSREC |
| Name of Scheme | LONGRIDGE SPORTS CENTRE RECEPTION |  |  |  |
| Officer Responsible | ROD PEARCE |  |  |  |
| Description of Scheme | Relocation of fitness suite from first floor to ground floor incorporating bar area |  |  |  |
| Benefits of Scheme | To comply with DDA Act and also enhance existing facilities |  |  |  |
| Project Timetable | Start Date | March 2006 relocation of fitness suite |  |  |
|  | Completion Date |  |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
|  |  | Fitness suite relocated and extended to ground floor to comply with DDA |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | See notes over |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | Ongoing maintenance |  |  |  |

|  |  |  |  |  |  | Cost Centre | LSREC |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Revised Estimate: |  |  |  |  | £0 |  |
| Summary | Budget for Current Year: |  |  |  |  | £54,410 |  |
|  | Expected Total Cost of Scheme: |  |  |  |  | £185,361 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 2 March 2004 |  |
|  | Minute Ref: |  |  |  |  | 762 |  |
| Expenditure Analysis |  |  |  | Actual Expenditure 2004/05 £ | Actual Expenditure 2005/06 £ | Expected Expenditure 2006/07 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  | 128,495 | 2,456 | 54,410 | 185,361 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  | 128,495 | 2,456 | 54,410 | 185,361 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End June 2004 |  | Scheme is 75% complete. Toilet and changing room work to commence in August. New fitness suite to be opened shortly. |  |  |  |  |  |
| End Aug 2004 |  | Scheme to fitness suite complete. Work to toilet and changing rooms to commence October. Awaiting completion of public conveniences prior to commencement of this scheme. |  |  |  |  |  |
| End Nov 2004 |  | Works complete to function room. Public conveniences work to commence in January 2005. |  |  |  |  |  |
| End June 2005 |  | Scheme is on hold at the moment. Awaiting outcome of decision on the future arrangements at the sports centre. |  |  |  |  |  |
| End Sept 2005 |  | No further progress made since the end of June. |  |  |  |  |  |
| End Dec 2005 |  | No further progress made since the end of June. |  |  |  |  |  |
| End March 2006 |  | Scheme on hold due to negotiation with Lancashire County Council. Some expenditure due March 2006 in relocation of fitness suite to Longridge Civic Hall, anticipated cost £12,500 |  |  |  |  |  |
| End Sept 2006 |  | Scheme on hold due to negotiations with LCC. Some expenditure anticipated due to relocation of fitness suite to Longridge Civic Hall anticipated cost £18,500. Decision due from Committee Nov 06 if scheme is to proceed. |  |  |  |  |  |
| End Dec 2006 |  | Scheme as above on hold, no decision received from Committee, to date. |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | PBOIL |
| Name of Scheme | POOL – REPLACE BOILER AND CALORIFIER |  |  |  |
| Officer Responsible | ROD PEARCE |  |  |  |
| Description of Scheme | Replacement of oil boiler for gas boiler |  |  |  |
| Benefits of Scheme | Energy efficiency, reduced fuel usage |  |  |  |
| Project Timetable | Start Date | Design stage to commence March 2006 Installation of boilers July 2006 |  |  |
|  | Completion Date | End August 2006 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | See notes overleaf |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | Decrease in fuel usage and therefore cost |  |  |  |

|  |  |  |  |  |  | Cost Centre | PBOIL |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Revised Estimate: |  |  |  |  | £0 |  |
| Summary | Approved Budget for Current Year: |  |  |  |  | £96,300 |  |
|  | Expected Total Cost of Scheme: |  |  |  |  | £96,300 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 28 February 2006 |  |
|  | Minute Ref: |  |  |  |  | 755 |  |
| Expenditure Analysis |  |  |  |  |  |  | Expected Expenditure 2006/07 £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  | 106,000 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  | 9,000 |
|  | Internal Salaries |  |  |  |  |  | 1,500 |
|  | TOTAL |  |  |  |  |  | 116,500 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End March 2006 |  | The scheme has previously been held back awaiting finalisation of Edisford changing room scheme and of associated consequences. However, the decision has now been taken to enter a joint scheme for the changing rooms with Roefield and therefore the boiler will be stand alone supplying the pool only. Consultants will be employed early in the financial year to carry out design of scheme and provide an accurate estimate of costs. |  |  |  |  |  |
| End Sept 2006 |  | Scheme back on hold following consultants appraisal of whole site management arrangements. Report to committee November 2006 re: trust recommendations to include boiler situation. |  |  |  |  |  |
| End Dec 2006 |  | Scheme on hold no decision received from Committee |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | PCRPE |
| Name of Scheme | PUBLIC CONVENIENCES – SLAIDBURN |  |  |  |
| Officer Responsible | ROD PEARCE |  |  |  |
| Description of Scheme | Demolition of existing public conveniences and rebuild new due to ongoing problem with user capacity |  |  |  |
| Benefits of Scheme | Larger facility to cater for large demand |  |  |  |
| Project Timetable | Start Date | October 2005 |  |  |
|  | Completion Date | August 2006 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
|  | Spring 2006 | Building control application |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Originally this scheme was for Dunsop Bridge but due to problems obtaining permission from the Duchy of Lancaster the scheme was “swapped” with Slaidburn public conveniences due in 2007/08. Scheme altered to reconstruct Slaidburn conveniences. |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | Increased cleaning cost and materials and potential higher rateable value. However, this will be a new facility and therefore should be cheaper to maintain. |  |  |  |

|  |  |  |  |  |  | Cost Centre | PCRPE |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Budget for Current Year: |  |  |  |  | £108,740 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £125,046 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 1 March 2005 |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  |  | Actual Expenditure 2005/06 £ | Expected Expenditure 2006/07 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  | 13,703 | 95,665 | 109,368 |
|  | Retention (show separately) |  |  |  |  | 3,000 | 3,000 |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  | 3,075 | 3,075 |
|  | Internal Salaries |  |  |  | 2,603 | 7,000 | 9,603 |
|  | TOTAL |  |  |  | 16,306 | 108,740 | 125,046 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| June 2005 |  | Specification in production. Potential delay on start date due to outstanding permission from landowner. |  |  |  |  |  |
| End Sept 2005 |  | Specification in production. No approval to date from landowner. Separate report will be submitted to committee requesting commencement with Slaidburn scheme. |  |  |  |  |  |
| End Dec 2005 |  | Specification in progress for Slaidburn conveniences. Realistically no expenditure on construction work will take place in 2005/06. |  |  |  |  |  |
| End March 2006 |  | Contracts have now been tendered for. Tenders have been returned. Contract in process of being let. Work should commence on site by end of March. |  |  |  |  |  |
| End Sept 2006 |  | Work complete July 06 possible anticipated expenditure possible underspend by approx £500 |  |  |  |  |  |
| End Dec 2006 |  | Scheme complete. Retention outstanding £2,533.85 |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | PESTS |
| Name of Scheme | ROUTINE RENEWAL OF PEST CONTROL/DOG WARDEN VEHICLE |  |  |  |
| Officer Responsible | JAMES RUSSELL |  |  |  |
| Description of Scheme | Replace Suzuki 1.3 supercarry (Y378 XHG) with Fiat Diablo 1.3D white panel van |  |  |  |
| Benefits of Scheme | Assist in making people’s lives safer and healthier. Improved vehicle safety for operative. |  |  |  |
| Project Timetable | Start Date |  |  |  |
|  | Completion Date |  |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
|  | Purchase vehicle | October 2006 |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | Reduced fuel usage and maintenance frequency |  |  |  |

|  |  |  |  |  |  | Cost Centre | PESTS |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £10,000 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £9,065 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 28 February 2006 |  |
|  | Minute Ref: |  |  |  |  | 755 |  |
| Expenditure Analysis |  |  |  |  |  |  | Expected Expenditure 2006/07 £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  |  |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  | 9,065 |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  |  | 9,065 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End March 2006 |  | Van will be purchased to coincide with the return of the current vehicle to the leasing company in October 2006. |  |  |  |  |  |
| End Dec 2006 |  | Van purchased. Fitted accordingly. Now in use. Previous vehicle returned to lease company some additional costs incurred re return inspection and repairs. Scheme complete. |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | PLAYF |
| Name of Scheme | IMPROVEMENTS TO CHILDREN’S PLAY AREAS |  |  |  |
| Officer Responsible | GRAHAM JAGGER |  |  |  |
| Description of Scheme | Part of rolling programme of improvements previously approved by committee |  |  |  |
| Benefits of Scheme | Better play facilities for young children |  |  |  |
| Project Timetable | Start Date | August 2005 |  |  |
|  | Completion Date | March 2008 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Existing staffing problems in engineering section will delay the scheme. Complete removal of play equipment maintenance budget will mean a review of rolling programme is necessary. |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes. Subject to filling the two vacancies in the engineering section as soon as possible. |  |  |  |
| What are the revenue implications of the scheme? | There will be more equipment to maintain but no maintenance budget |  |  |  |

|  |  |  |  |  |  | Cost Centre | PLAYF |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Slippage from 2005/06: |  |  |  |  | £29,600 |  |
| Summary | Revised Estimate: |  |  |  |  | £34,200 |  |
|  | Approved Budget for Current Year: |  |  |  |  | £29,600 |  |
|  | Expected Total Cost of Scheme: |  |  |  |  | £34,272 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 1 March 2005 |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  |  | Actual Expenditure 2005/06 £ | Expected Expenditure 2005/06 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 27,300 | 27,300 |
|  | Retention (show separately) |  |  |  |  | 0 |  |
|  | Other Costs |  |  |  |  | 0 |  |
|  | External Fees |  |  |  |  | 0 |  |
|  | Internal Salaries |  |  |  | 4,672 | 2,300 | 6,972 |
|  | TOTAL |  |  |  | 4,672 | 29,600 | 34,272 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| April 2005 |  | In the light of the removal of the whole of the play equipment maintenance budget it would be prudent to review how and on what this money is to be spent before ordering any new equipment for installation. |  |  |  |  |  |
| June 2005 |  | A review of the equipment on the play areas is about to start so a decision can be made as to how and where the funding would be best spent. |  |  |  |  |  |
| End Sept 2005 |  | Proposals are to spend allocation on improving access to equipment for children with disabilities and to replace some equipment, which is beyond repair. |  |  |  |  |  |
| End Dec 2005 |  | New equipment to be installed in Clitheroe centre play area and vandalised space not to be repaired and re-fixed. |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | PLAYG |
| Name of Scheme | IMPROVEMENTS TO CHILDREN’S PLAY AREAS |  |  |  |
| Officer Responsible | GRAHAM JAGGER |  |  |  |
| Description of Scheme | Provision of new equipment to replace items that are beyond their useful life |  |  |  |
| Benefits of Scheme | To maintain a reasonable standard of equipment on the play areas |  |  |  |
| Project Timetable | Start Date | April 2006 |  |  |
|  | Completion Date | January 2007 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | There is no budget for maintaining children’s play equipment |  |  |  |

|  |  |  |  |  |  | Cost Centre | PLAYG |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £35,300 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £35,300 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 28 February 2006 |  |
|  | Minute Ref: |  |  |  |  | 755 |  |
| Expenditure Analysis |  |  |  |  |  |  | Expected Expenditure 2006/07 £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  | 33,000 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  | 2,300 |
|  | TOTAL |  |  |  |  |  | 35,300 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End March 2006 |  | A review of the condition of each of the play areas will be undertaken in the summer to establish the priority item for replacement and any additional items considered necessary. |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre |  | POSEC |
| Name of Scheme | POOL – SECURITY AND FIRE ALARM |  |  |  |  |
| Officer Responsible | ROD PEARCE |  |  |  |  |
| Description of Scheme | Upgrade of current system |  |  |  |  |
| Benefits of Scheme | Comply with current fire regulations. Security benefits. |  |  |  |  |
| Project Timetable | Start Date | December 2006 |  | To coincide with seasonal pool closure |  |
|  | Completion Date | January 2006 |  |  |  |
|  | Any Other Key Dates | Description of Work |  |  |  |
|  | Oct/Nov 2006 | Design of system |  |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |  |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |  |
| What are the revenue implications of the scheme? | Slight increase in annual maintenance costs |  |  |  |  |

|  |  |  |  |  |  | Cost Centre | POSEC |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £13,200 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £13,200 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 28 February 2006 |  |
|  | Minute Ref: |  |  |  |  | 755 |  |
| Expenditure Analysis |  |  |  |  |  |  | Expected Expenditure 2006/07 £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  | 12,900 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  | 300 |
|  | TOTAL |  |  |  |  |  | 13,200 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End Sept 2006 |  | Works planned during seasonal closure December 2006 |  |  |  |  |  |
| End Dec 2006 |  | Work Due in January 2007 to complete the screen |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | RALSH |
| Name of Scheme | REPLACE ALLET SHAVER WITH DENNIS CYLINDER MOWER |  |  |  |
| Officer Responsible | GRAHAM JAGGER |  |  |  |
| Description of Scheme | Replace 6 year old mower with one more suited to the job |  |  |  |
| Benefits of Scheme | Improved quality of work and less breakdowns |  |  |  |
| Project Timetable | Start Date | April 2006 |  |  |
|  | Completion Date | April 2006 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | None |  |  |  |

|  |  |  |  |  |  | Cost Centre | RALSH |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £2,245 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £2,245 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 28 February 2006 |  |
|  | Minute Ref: |  |  |  |  | 755 |  |
| Expenditure Analysis |  |  |  |  |  |  | Expected Expenditure 2006/07 £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  | 2,245 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  |  | 2,245 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End March 2006 |  | Process is underway to get replacement machine ready for use next spring |  |  |  |  |  |
| End Sept 2006 |  | Item purchased and in use from start of financial year (complete) |  |  |  |  |  |
| End Dec 2006 |  | Scheme Complete |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | RCOLT |
| Name of Scheme | REPLACE N313 SWK REFUSE COLLECTION VEHICLE |  |  |  |
| Officer Responsible | GRAHAM JAGGER |  |  |  |
| Description of Scheme | To replace a vehicle on expiry of its lease |  |  |  |
| Benefits of Scheme | To have a vehicle fleet fit for purpose |  |  |  |
| Project Timetable | Start Date | 1 April 2006 |  |  |
|  | Completion Date | 29 October 2006 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
|  |  | Lease ends 29 October 2006 |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Manufacture and delivery period depending on type and style of vehicle chosen |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | Costs included our existing budgets |  |  |  |

|  |  |  |  |  |  | Cost Centre | RCOLT |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £180,000 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £180,000 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 28 February 2006 |  |
|  | Minute Ref: |  |  |  |  | 755 |  |
| Expenditure Analysis |  |  |  |  |  |  | Expected Expenditure 2006/07 £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Vehicle |  |  |  |  |  | 180,000 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  |  | 180,000 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End March 2006 |  | A decision has yet to be taken on the type and style of vehicle(s) to be purchased. The work being undertaken in respect of re-designing the collection service will influence the decision on the vehicle(s) bought. |  |  |  |  |  |
| End Sept 2006 |  | The delay in purchasing a new refuse collection vehicle is because decisions have yet to be made about how and when to extend the three-stream refuse collection and recycling service. The type of vehicle will depend on the style of service finally adopted following the evaluation of the trial operation. N313 SWK is to be purchased from lease company to be used as a spare vehicle. |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | REBIN |
| Name of Scheme | RESIDUAL WASTE BINS – THREE STREAM WASTE COLLECTION |  |  |  |
| Officer Responsible | PETER McGEORGE |  |  |  |
| Description of Scheme | The provision of 140 litre wheeled bins to target round for recovery of residual household waste |  |  |  |
| Benefits of Scheme | The provision of residual waste bins will complete investment in first targeted collection round for three stream collection and improve recycling performance |  |  |  |
| Project Timetable | Start Date | Delivery of bins commencing 27 February 2006. Completion in two weeks. Completion of service March 2006. |  |  |
|  | Completion Date | New service delivery |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
|  |  | Provision of three stream refuse collection service |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Public participation. Change to cost sharing arrangement. Downturn in market value/price. |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | Estimated income from recycling credits at £41.26 per tonne (£18,567 per annum). Estimated income from sale of recyclate at £7 per tonne (£3,150) |  |  |  |

|  |  |  |  |  |  | Cost Centre | REBIN |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Revised Estimate for Current Year: |  |  |  |  | £0 |  |
| Summary | Approved Budget for Current Year: |  |  |  |  | £172,500 |  |
|  | Expected Total Cost of Scheme: |  |  |  |  | £725,000 |  |
|  | Approved by Committee: |  |  |  |  | Policy & Finance |  |
|  | Date: |  |  |  |  | 24 January 2006 |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  | Expected Expenditure 2005/06 £ | Expected Expenditure 2006/07 £ | Expected Expenditure 2007/08 £ | Expected Expenditure 2008/09 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  |  |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  | 80,500 | 0 | 408,500 | 236,000 | 725,000 |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  | 80,500 | 0 | 408,500 | 236,000 | 725,000 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End March 2006 |  | Bins due to be delivered to households this week. |  |  |  |  |  |
| End Sept 2006 |  | Expenditure completed in 2005/06 with purchase of wheeled bins and introduction of new three-stream collection system to target round. Target round still being evaluated. Delay in development of Waste Transfer facility has affected programme for expansion of wheeled bin delivery. It is now proposed to commence expansion Mid 2007 therefore 2006/07 Budget needs to be included in 2007/08 expenditure. |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | RGBUF |
| Name of Scheme | REPLACE FOUR ALLETT BUFFALO MOWERS WITH ONE DENNIS |  |  |  |
| Officer Responsible | GRAHAM JAGGER |  |  |  |
| Description of Scheme | Replacement with multi-functional machine |  |  |  |
| Benefits of Scheme | Improved efficiency and quality of service |  |  |  |
| Project Timetable | Start Date | April 2006 |  |  |
|  | Completion Date | May 2006 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | None |  |  |  |

|  |  |  |  |  |  | Cost Centre | RGBUF |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £6,985 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £6,985 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 28 February 2006 |  |
|  | Minute Ref: |  |  |  |  | 755 |  |
| Expenditure Analysis |  |  |  |  |  |  | Expected Expenditure 2006/07 £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  | 6,985 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  |  | 6,985 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End March 2006 |  | Tenders have been invited for the purchase of this new machine and so should be in use in spring. |  |  |  |  |  |
| End Sept 2006 |  | Item purchased and in use from start of financial year (complete) |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | RGDCW |
| Name of Scheme | REPLACE HAYTER RIDE-ON N383 DCW |  |  |  |
| Officer Responsible | GRAHAM JAGGER |  |  |  |
| Description of Scheme | Replace 10 year old mowing machine |  |  |  |
| Benefits of Scheme | Improved quality and efficiency and less mechanical breakdowns |  |  |  |
| Project Timetable | Start Date | April 2006 |  |  |
|  | Completion Date | April 2006 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | None |  |  |  |

|  |  |  |  |  |  | Cost Centre | RGDCW |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £20,800 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £20,700 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 28 February 2006 |  |
|  | Minute Ref: |  |  |  |  | 755 |  |
| Expenditure Analysis |  |  |  |  |  |  | Expected Expenditure 2006/07 £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  | 20,700 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  |  | 20,700 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End March 2006 |  | Process in underway to get a replacement machine ready for use in spring. |  |  |  |  |  |
| End Sept 2006 |  | Item purchased and in use from start of financial year |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | RGMOW |
| Name of Scheme | PURCHASE OF FOUR MOWING MACHINES AND TRAILER |  |  |  |
| Officer Responsible | GRAHAM JAGGER |  |  |  |
| Description of Scheme | New mowing machines to meet the needs of the service |  |  |  |
| Benefits of Scheme | Improved efficiency and quality of service |  |  |  |
| Project Timetable | Start Date | April 2006 |  |  |
|  | Completion Date | May 2006 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | None |  |  |  |

|  |  |  |  |  |  | Cost Centre | RGMOW |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £7,700 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £5,159 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 28 February 2006 |  |
|  | Minute Ref: |  |  |  |  | 755 |  |
| Expenditure Analysis |  |  |  |  |  |  | Expected Expenditure 2006/07 £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  | 5,159 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  |  | 5,159 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End March 2006 |  | Tenders have been invited for the purchase of this equipment and so should be in use in spring. |  |  |  |  |  |
| End Sept 2006 |  | Item purchased and in use from start of financial year |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | RGOFR |
| Name of Scheme | REPLACE G190 OFR MINI TRACTOR |  |  |  |
| Officer Responsible | GRAHAM JAGGER |  |  |  |
| Description of Scheme | Replace 16 year old tractor with more suitable machine |  |  |  |
| Benefits of Scheme | Improve efficiency of service and less breakdowns |  |  |  |
| Project Timetable | Start Date | April 2006 |  |  |
|  | Completion Date | May 2006 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | None |  |  |  |

|  |  |  |  |  |  | Cost Centre | RGOFR |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £9,000 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £9,000 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 28 February 2006 |  |
|  | Minute Ref: |  |  |  |  | 755 |  |
| Expenditure Analysis |  |  |  |  |  |  | Expected Expenditure 2006/07 £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  | 9,000 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  |  | 9,000 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End March 2006 |  | Tenders have been invited for replacement of this vehicle with a view to purchase in May 2006. |  |  |  |  |  |
| End Sept 2006 |  | Item purchased and in use from start of financial year |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | RIBCA |
| Name of Scheme | REFURBISHMENT OF RIBCHESTER PUBLIC CONVENIENCES |  |  |  |
| Officer Responsible | ROD PEARCE |  |  |  |
| Description of Scheme | Full refurbishment to include re-roofing of existing public conveniences at Ribchester |  |  |  |
| Benefits of Scheme | Provision of anti-vandal fittings |  |  |  |
| Project Timetable | Start Date | October 2006 |  |  |
|  | Completion Date | January 2006 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | As existing |  |  |  |

|  |  |  |  |  |  | Cost Centre | RIBCA |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £37,200 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £37,200 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 28 February 2006 |  |
|  | Minute Ref: |  |  |  |  | 755 |  |
| Expenditure Analysis |  |  |  |  |  |  | Expected Expenditure 2006/07 £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  | 33,150 |
|  | Retention (show separately) |  |  |  |  |  | 850 |
|  | Other Costs |  |  |  |  |  | 0 |
|  | External Fees |  |  |  |  |  | 0 |
|  | Internal Salaries |  |  |  |  |  | 3,700 |
|  | TOTAL |  |  |  |  |  | 37,200 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End March 2006 |  | Design stage to commence May 2006. |  |  |  |  |  |
| End Sept 2006 |  | Scheme tenders received September 2006 work to commence Mid October/early November – completion January 2007 |  |  |  |  |  |
| End Dec 2006 |  | Work on site completion due 19 January 2007, scheme appears to be on budget at present time no savings anticipated. |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | RLIFT |
| Name of Scheme | BIN LIFTS FOR TWO EXISTING VEHICLES |  |  |  |
| Officer Responsible | GRAHAM JAGGER |  |  |  |
| Description of Scheme | To purchase fit bin lifts for wheelie bin collection |  |  |  |
| Benefits of Scheme | To support the introduction of three stream refuse collection |  |  |  |
| Project Timetable | Start Date | April 2006 |  |  |
|  | Completion Date | October 2006 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | The decision on when to extend the introduction of wheelie bins to other parts of the borough will influence when the bin lifts are purchased |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | The addition of bin lifts to refuse collection vehicles increases fuel consumption and reduces the carrying capacity of the vehicle, which has an effect on running costs |  |  |  |

|  |  |  |  |  |  | Cost Centre | RLIFT |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Revised Estimate: |  |  |  |  | £0 |  |
| Summary | Approved Budget for Current Year: |  |  |  |  | £30,900 |  |
|  | Expected Total Cost of Scheme: |  |  |  |  | £30,900 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 28 February 2006 |  |
|  | Minute Ref: |  |  |  |  | 755 |  |
| Expenditure Analysis |  |  |  |  |  | Expected Expenditure 2006/07 £ | Expected Expenditure 2006/07 £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  | 0 | 30,900 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  | 0 | 30,900 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End March 2006 |  | Consideration regarding the type of lift to be purchased will be included as part of the process of extending the three stream collection service. |  |  |  |  |  |
| End Sept 2006 |  | Bin lifts cannot be purchased until the decision has been taken on the extension of the three stream refuse collection/recycling service. |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | ROSEG |
| Name of Scheme | ROSE GARDEN CASTLE GROUNDS |  |  |  |
| Officer Responsible | CHRIS HUGHES |  |  |  |
| Description of Scheme | To refurbish the old rose garden in the Castle Grounds. |  |  |  |
| Benefits of Scheme | Aesthetics and environmental improvements in Castle area. |  |  |  |
| Project Timetable | Start Date | Autumn 05 |  |  |
|  | Completion Date | March 07 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? |  |  |  |  |
| Funding | Total cost of scheme (over 2 years) 92,000 To be funded: LCC Grant -31,000 Market Towns Initiative Grant -28,000 Art Development Revenue Budget -5,000 Balance to be identified 28,000 |  |  |  |

|  |  |  |  |  |  | Cost Centre | ROSEG |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £0 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £91,880 |  |
|  | Approved by Committee: |  |  |  |  |  |  |
|  | Date: |  |  |  |  |  |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  |  | Actual Expenditure 2005/06 £ | Expected Expenditure 2006/07 £ | Total Cost £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  | 32,692 | 56,000 | 88,692 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  | 3,188 |  | 3,188 |
|  | TOTAL |  |  |  | 35,880 | 56,000 | 91,880 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End Sept 06 |  | Scheme complete apart from installation of Public Art pieces |  |  |  |  |  |
| End Dec 06 |  | Scheme complete except awaiting installation of one public art piece. Final payments be made before end of financial year. |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | RPCHA |
| Name of Scheme | RIBBLESDALE POOL – REFURBISH STAFF CHANING ROOMS AND EXTERNAL STORE |  |  |  |
| Officer Responsible | ROD PEARCE |  |  |  |
| Description of Scheme | Replace existing kitchen units in staff area and rebuild external store |  |  |  |
| Benefits of Scheme | Improve health and safety and fire protection and staff welfare |  |  |  |
| Project Timetable | Start Date | September 2005 |  |  |
|  | Completion Date | January 2006 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | None |  |  |  |

|  |  |  |  |  |  | Cost Centre | RPCHA |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Slippage from05/06: |  |  |  |  | £6,700 |  |
| Summary | Approved Budget for Current Year: |  |  |  |  | £6,700 |  |
|  | Expected Total Cost of Scheme: |  |  |  |  | £15,000 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 1 March 2005 |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  |  | Actual Expenditure 2005/06 | Expected Expenditure 2006/07 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  | 8,299 | 6,700 | 14.999 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  | 8,299 | 6,700 | 14,900 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| June 2005 |  | Scheme is now at the design stage. |  |  |  |  |  |
| End Sept 2005 |  | Work complete to external store. Yet to be invoiced. Work to commence November 2005 on staff room. |  |  |  |  |  |
| End Dec 2005 |  | Work to commence on staff room January 2006. |  |  |  |  |  |
| End Sept 2006 |  | Scheme complete July 06 overspend on scheme £403.60 due to need for wheeled bin |  |  |  |  |  |
| End Dec 2006 |  | Scheme complete no further expenditure on this scheme |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | RVERG |
| Name of Scheme | REPLACE 3 BLADE CUTTER HAYTOR CONDOR |  |  |  |
| Officer Responsible | GRAHAM JAGGER |  |  |  |
| Description of Scheme | Replace 6 year old machine with one more suited to job |  |  |  |
| Benefits of Scheme | Improved quality of work and less breakdowns |  |  |  |
| Project Timetable | Start Date | April 2006 |  |  |
|  | Completion Date | April 2006 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | No |  |  |  |
| What are the revenue implications of the scheme? | None |  |  |  |

|  |  |  |  |  |  | Cost Centre | RVERG |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £4,500 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £4,497 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 28 February 2006 |  |
|  | Minute Ref: |  |  |  |  | 755 |  |
| Expenditure Analysis |  |  |  |  |  |  | Expected Expenditure 2006/07 £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  | 4,497 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  |  | 4,497 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End March 2006 |  | Process is underway to get a replacement machine ready for use in spring. |  |  |  |  |  |
| End Sept 2006 |  | Item purchased in use at start of financial year (complete) |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | RWFBU |
| Name of Scheme | REPLACE R485 FBU IVECO 7.5 TONNE |  |  |  |
| Officer Responsible | GRAHAM JAGGER |  |  |  |
| Description of Scheme | Replace 8 year old vehicle |  |  |  |
| Benefits of Scheme | Having a truck more suited to today’s operational needs |  |  |  |
| Project Timetable | Start Date | April 2006 |  |  |
|  | Completion Date | November 2006 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | None |  |  |  |

|  |  |  |  |  |  | Cost Centre | RWFBU |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £37,000 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £35,100 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 28 February 2006 |  |
|  | Minute Ref: |  |  |  |  | 755 |  |
| Expenditure Analysis |  |  |  |  |  |  | Expected Expenditure 2006/07 £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  | 35,100 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  |  | 35,100 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End March 2006 |  | Consideration will be given shortly to the type of vehicle felt to be the most suitable replacement. |  |  |  |  |  |
| End Sept 2006 |  | Item purchased in use at start of financial year (complete) |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | RWKEG |
| Name of Scheme | REPLACE WORKS VEHICLE P715 KEG |  |  |  |
| Officer Responsible | GRAHAM JAGGER |  |  |  |
| Description of Scheme | Replace 8 year old van |  |  |  |
| Benefits of Scheme | To have a more suitable vehicle and reduced maintenance |  |  |  |
| Project Timetable | Start Date | April 2006 |  |  |
|  | Completion Date | November 2006 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | None |  |  |  |

|  |  |  |  |  |  | Cost Centre | RWKEG |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £15,400 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £12,040 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 28 February 2006 |  |
|  | Minute Ref: |  |  |  |  | 755 |  |
| Expenditure Analysis |  |  |  |  |  |  | Expected Expenditure 2006/07 £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  | 12,040 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  |  | 12,040 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End March 2006 |  | Consideration will be given shortly to the type of vehicle felt to be most appropriate to replace the Ford Courier 1.8D van. |  |  |  |  |  |
| End Sept 2006 |  | Item purchased in use at start of financial year (complete) |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | RWXCK |
| Name of Scheme | REPLACE P996 XCK WITH TRANSIT VAN |  |  |  |
| Officer Responsible | GRAHAM JAGGER |  |  |  |
| Description of Scheme | Replace 9 year old van with more appropriate vehicle |  |  |  |
| Benefits of Scheme | Having a vehicle more suited to operational needs |  |  |  |
| Project Timetable | Start Date | April 2006 |  |  |
|  | Completion Date | November 2006 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | None |  |  |  |

|  |  |  |  |  |  | Cost Centre | RWXCK |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £13,500 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £11,726 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 28 February 2006 |  |
|  | Minute Ref: |  |  |  |  | 755 |  |
| Expenditure Analysis |  |  |  |  |  |  | Expected Expenditure 2006/07 £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  | 11,726 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  |  | 11,726 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End March 2006 |  | The vehicle is owned by the Council and may be best replaced in the second half of the year. |  |  |  |  |  |
| End Sept 2006 |  | Item purchased in use at start of financial year (PK06 VWY) |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2005/06 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | SDIMP |
| Name of Scheme | IMPROVEMENTS TO NEW DEPOT |  |  |  |
| Officer Responsible | GRAHAM JAGGER |  |  |  |
| Description of Scheme | Alterations to comply with health and safety requirements |  |  |  |
| Benefits of Scheme | Health and safety compliance and better welfare facilities for employees |  |  |  |
| Project Timetable | Start Date | May 2004 |  |  |
|  | Completion Date | March 2005 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | It appears highly likely that a Waste Transfer Station will be built in Salthill Depot by May 2005 with the consequential alteration of some of the existing facilities on site. The need to carry out some of the proposed work will depend on the work necessary to facilitate the Transfer Station. |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose? | Yes |  |  |  |
| What are the revenue implications of the scheme? | None as far as the proposed health and safety improvements are concerned. |  |  |  |

|  |  |  |  |  |  | Cost Centre | SDIMP |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Revised Estimate |  |  |  |  | £7,000 |  |
| Summary | Original Budget for Current Year: |  |  |  |  | £6,530 |  |
|  | Expected Total Cost of Scheme: |  |  |  |  | £31,395 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 2 March 2004 |  |
|  | Minute Ref: |  |  |  |  | 762 |  |
| Expenditure Analysis |  |  | Actual Expenditure 2003/04 £ | Actual Expenditure 2004/05 £ | Expected Expenditure 2005/06 £ | Expected Expenditure 2006/07 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  | 18,084 | 2,538 | 0 | 7,004 | 27,626 |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  | 1,939 | 1,830 |  |  | 1,939 |
|  | TOTAL |  | 20,023 | 4,368 | 0 | 7,004 | 31,395 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End June 2004 |  | Discussions are at an advanced stage regarding the Waste Transfer Station at Salthill Depot and a decision on what additional improvement works are to be done will only be taken when the full extent of the proposed scheme is known. |  |  |  |  |  |
| End Aug 2004 |  | No change to above. |  |  |  |  |  |
| End Nov 2004 |  | Waste transfer station unlikely to be up and running by July 2005. This budget will be spent on necessary equipment/facilities at the depot, probably during next financial year. Therefore £7,000 moved to 2005/06. |  |  |  |  |  |
| End June 2005 |  | A decision on how this money is to be spent will be made when the work relating to the construction of the new waste transfer station is nearing completion later this financial year. |  |  |  |  |  |
| End Sept 2005 |  | Completion of Waste Transfer Station in Depot has now started but will not be complete until May 2006. Budget unlikely to be committed until very end of financial year. |  |  |  |  |  |
| End Dec 2005 |  | See above. To be carried over into 2006/07. |  |  |  |  |  |
| End March 2006 |  | As the new facilities are nearing completion we will shortly be able to determine the most appropriate way to make best use of the money available. |  |  |  |  |  |
| End Sept 2006 |  | New Waste Transfer Station and Depot alteration were completed in August 2006 |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2006/07 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | SYNCA |
| Name of Scheme | LONGRIDGE SPORTS CENTRE – REPLACE CARPET ON SYNTHETIC PITCH |  |  |  |
| Officer Responsible | ROD PEARCE |  |  |  |
| Description of Scheme | Contribution to Lancashire County Council (joint use) to replacement of defective playing surface |  |  |  |
| Benefits of Scheme | Health and safety |  |  |  |
| Project Timetable | Start Date | Summer 2006 (grant dependable LCC) Summer 2007 if no grant |  |  |
|  | Completion Date |  |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Scheme is joint use and 50% : 50% funded between school and RVBC. May be delayed until summer 2007 if grant from LCC not available to school. |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes. LCC will manage scheme. |  |  |  |
| What are the revenue implications of the scheme? | Future maintenance as pitch wears as existing. |  |  |  |

|  |  |  |  |  |  | Cost Centre | SYNCA |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Revised Estimate: |  |  |  |  | £0 |  |
| Summary | Approved Budget for Current Year: |  |  |  |  | £133,900 |  |
|  | Expected Total Cost of Scheme: |  |  |  |  | £133,900 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 28 February 2006 |  |
|  | Minute Ref: |  |  |  |  | 755 |  |
| Expenditure Analysis |  |  |  |  |  |  | Expected Expenditure 2006/07 £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  | 133,900 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  |  | 133,900 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End March 2006 |  | See problems. |  |  |  |  |  |
| End Sept 2006 |  | As previous awaiting LCC commitment to scheme – expenditure unlikely 07 |  |  |  |  |  |
| End Dec 2006 |  | As end September 2006 |  |  |  |  |  |

|  | Scheme DRAFT 5 yr Capital Programme 2007/12 ANNEX 3 | 2007/08 | 2008/09 | 2009/10 | 2010/11 | 2011/12 | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | £ | £ | £ | £ | £ | £ |
|  | Community Committee |  |  |  |  |  |  |
|  | Public Conveniences: |  |  |  |  |  |  |
|  | Replace & increase size of Dunsop Bridge Toilets |  |  |  | 121,500 |  | 121,500 |
| ## NEW | Funding towards reconstruction of Whalley toilets | 50,000 |  |  |  |  | 50,000 |
| ## NEW | Refurbishment of Chipping toilets | 75,000 |  |  |  |  | 75,000 |
|  | Improvements to children's play areas | 35,300 | 35,300 | 35,300 | 35,300 | 35,300 | 176,500 |
|  | Castle Café - refurbish toilets |  | 10,600 |  |  |  | 10,600 |
|  | Football pitches drainage |  | 16,900 |  | 16,900 |  | 33,800 |
|  | Grant Aid to Longridge Action Group re Civic Hall | 90,000 |  |  |  |  | 90,000 |
| NEW | Gisburn Forest Park Cycling Trails and Cycling Strategy Initiatives | 25,000 |  |  |  |  | 25,000 |
| ** | Castle Lottery scheme | 33,800 | 132,500 |  |  |  | 166,300 |
| NEW | Improvements to Clitheroe Castle Keep |  | 110,000 |  |  |  | 110,000 |
|  | Edisford Changing Rooms | 214,700 |  |  |  |  | 214,700 |
| NEW | Replace Wc's and Showers at Roefield Changing Rooms | 24,000 |  |  |  |  | 24,000 |
|  | Platform Gallery: |  |  |  |  |  |  |
| NEW | CCTV scheme for Platform Gallery | 5,000 |  |  |  |  | 5,000 |
| NEW | Replace Boiler at Platform Gallery | 11,000 |  |  |  |  | 11,000 |
|  | Longridge Sports Centre: |  |  |  |  |  |  |
|  | Security system |  | 10,900 |  |  |  | 10,900 |
|  | Sports hall roof |  | 61,800 |  |  |  | 61,800 |
|  | Replace light fittings synthetic pitch |  | 10,600 |  |  |  | 10,600 |
|  | Replace fire alarm |  | 6,400 |  |  |  | 6,400 |
| NEW | Provision of online software & remote card readers | 14,000 |  |  |  |  | 14,000 |
| NEW | Relocate fitness room to Longridge Civic Hall | 18,600 |  |  |  |  | 18,600 |
|  | Ribblesdale Pool: |  |  |  |  |  |  |
| NEW | Energy Efficiency measures to Ribblesdale Pool | 104,500 |  |  |  |  | 104,500 |
| NEW | Replace Steel Windows to building at Ribblesdale Pool | 36,400 |  |  |  |  | 36,400 |
|  | Calderstones - new pitches & changing rooms | 255,000 |  |  |  |  | 255,000 |
|  | Replacement of Brungerley sculpture trail | 5,400 |  |  |  |  | 5,400 |
|  | Vehicles & Plant: |  |  |  |  |  |  |
|  | Refuse Collection |  |  |  |  |  |  |
|  | Replace W697 WHP Dennis | 180,000 |  |  |  |  | 180,000 |
|  | Replace V052 FRL Dennis |  | 180,000 |  |  |  | 180,000 |
|  | Replace V052 FRJ Dennis |  |  | 180,000 |  |  | 180,000 |
|  | Replace V052 FRK Dennis |  |  |  | 180,000 |  | 180,000 |
|  | Recycling and Residual Waste Containers | 236,000 | 236,000 |  |  |  | 472,000 |
| NEW | New Vehicle to meet requirements of extension of Three Stream Waste Coll | 190,000 |  |  |  |  | 190,000 |
|  | General Works |  |  |  |  |  |  |
|  | Replace G191 OFR Tractor | 15,400 |  |  |  |  | 15,400 |
|  | Replace V955 EVM JCB |  | 25,700 |  |  |  | 25,700 |
|  | Replace PF03 HFA Ford Transit |  |  | 15,400 |  |  | 15,400 |
|  | Replace PF03 HEU Ford Transit |  |  | 15,400 |  |  | 15,400 |
|  | Replace PF03 HFE Ford Transit |  |  | 15,400 |  |  | 15,400 |
|  | Replace PF03 HFC Ford Transit |  | 15,400 |  |  |  | 15,400 |
|  | Replace PE54 YXF |  |  | 15,400 |  |  | 15,400 |
|  | Replace Replacement for R675 HCW (PO54 COA) |  |  | 30,900 |  |  | 30,900 |
|  | Replace Replacement for P291 RCW (P054 COH) |  |  | 30,900 |  |  | 30,900 |
|  | Small Compressor Ingersoll Rand | 5,100 |  |  |  |  | 5,100 |
|  | Small Jetting Machine | 20,600 |  |  |  |  | 20,600 |
|  | Outdoor Recreation Vehicles and Plant: |  |  |  |  |  |  |
|  | Replace P051 DHM Iveco Daily | 27,300 |  |  |  |  | 27,300 |
|  | Replace Hayter Triple Mower LT322 2WD | 25,700 |  |  |  |  | 25,700 |
|  | Replace P053 WYW |  |  | 1,600 |  |  | 1,600 |
|  | Replace Landrover J438 JFV | 26,300 |  |  |  |  | 26,300 |
|  | Replace G516 OCK | 27,800 |  |  |  |  | 27,800 |
|  | Replace R563 SFR John Deere Ride On Mower | 14,900 |  |  |  |  | 14,900 |
|  | Replace Suzuki Van - PJ02 NNA | 10,000 |  |  |  |  | 10,000 |
|  | Total Community Committee | 1,776,800 | 852,100 | 340,300 | 353,700 | 35,300 | 3,358,200 |

** The extent of match funding required from RVBC is significantly more than identified here in the 5 year Capital Programme (£166,250).  This is because current capital schemes at the Castle e.g. CASED, KEEPR, CSLOT have been funded from this original allocation of £270,000 toward the lottery scheme.

The Actual Capital Commitment of the Council cannot be determined until confirmation has been received from HLF and RVBC have secured other grant sources.  Obviously further reports will be brought to Committee

| # NEW CAPITAL SCHEME PROFORMA ANNEX 4 |  |  |  |
| --- | --- | --- | --- |
| Name of Officer Responsible |  | C Hughes |  |
| Committee |  | Community |  |
| Brief Description of Scheme |  | CCTV Scheme for Platform Gallery |  |
| Full Details of Scheme |  | Provide additional security through the installation of a CCTV system at the Gallery |  |
| Links to Corporate Objectives |  | Making peoples lives safer and healthier |  |
| Cost of Scheme: |  | £ | Notes |
|  | Cost of Land |  |  |
|  | Contractor |  |  |
|  | Fees | 5,000 | Cost of equipment and installation |
|  | Internal Staff Salaries |  |  |
|  | Planning/Build Regs Fees |  |  |
|  | Other costs |  |  |
|  |  | 5,000 |  |

| Revenue Implications of the Scheme per year |  | £ | Details |
| --- | --- | --- | --- |
|  |  |  | None |
| Timescale (incl any key dates) |  |  |  |
|  | eg start on site | April 2007 |  |
|  | scheme completion | June 2007 |  |
|  | other dates… |  |  |
| Financial Year/(s) the scheme will take place |  |  |  |
| if the scheme will cover more than one year please breakdown the cost for each year |  |  |  |
|  | Year eg | £ |  |
|  | 2007/08 | 5,000 |  |
| Capital Funding & Sources |  |  |  |
|  | eg Special Grants |  |  |
|  | Contributions from voluntary bodies |  |  |

| # NEW CAPITAL SCHEME PROFORMA |  |  |  |
| --- | --- | --- | --- |
| Name of Officer Responsible |  | R Pearce |  |
| Committee |  | Community |  |
| Brief Description of Scheme |  | Replace boiler to Platform Gallery |  |
| Full Details of Scheme |  | Existing boiler has become inefficient and unreliable, existing heating also requires attention as none is present within the staff/counter area. The replacement of the boiler will increase efficiency, reduce C02 emissions and maintenance costs and free up much needed storage space. |  |
| Links to Corporate Objectives |  | To make peoples lives safer and healthier. To protect and enhance the existing environmental quality of our area. |  |
| Cost of Scheme: |  | £ | Notes |
|  | Cost of Land |  |  |
|  | Contractor | 8,000 |  |
|  | Fees | 1,000 |  |
|  | Internal Staff Salaries | 1,000 |  |
|  | Planning/Build Regs Fees |  |  |
|  | Other costs | 1,000 | Contingency |
|  |  | 11,000 |  |

| Revenue Implications of the Scheme per year |  | £ | Details |
| --- | --- | --- | --- |
|  |  | 500 | Annual maintenance |
| Timescale (incl any key dates) |  |  |  |
|  | eg start on site | August 2007 |  |
|  | scheme completion | August 2007 |  |
|  | other dates… |  |  |
| Financial Year/(s) the scheme will take place |  |  |  |
| if the scheme will cover more than one year please breakdown the cost for each year |  |  |  |
|  | Year eg | £ |  |
|  | 2007/08 | 11,000 |  |
| Capital Funding & Sources |  |  |  |
|  | eg Special Grants |  |  |
|  | Contributions from voluntary bodies |  |  |

| # NEW CAPITAL SCHEME PROFORMA |  |  |  |
| --- | --- | --- | --- |
| Name of Officer Responsible |  | C Hughes |  |
| Committee |  | Community |  |
| Brief Description of Scheme |  | Provision of online software and remote card readers |  |
| Full Details of Scheme |  | The provision of online bookings software and remote card readers to enable bookings at Longridge Sports Centre to be carried out remotely. |  |
| Links to Corporate Objectives |  | Making peoples lives safer and healthier |  |
| Cost of Scheme: |  | £ | Notes |
|  | Cost of Land | 14,000 | Cost of equipment and installation |
|  | Contractor |  |  |
|  | Fees |  |  |
|  | Internal Staff Salaries |  |  |
|  | Planning/Build Regs Fees |  |  |
|  | Other costs |  |  |
|  |  | 14,000 |  |

| Revenue Implications of the Scheme per year |  | £ | Details |
| --- | --- | --- | --- |
|  |  |  | None |
| Timescale (incl any key dates) |  |  |  |
|  | eg start on site | April 2007 | To be confirmed as part of negotiations with High School |
|  | scheme completion |  |  |
|  | other dates… |  |  |
| Financial Year/(s) the scheme will take place |  |  |  |
| if the scheme will cover more than one year please breakdown the cost for each year |  |  |  |
|  | Year eg | £ |  |
|  | 2007/08 | 14,000 |  |
| Capital Funding & Sources |  |  |  |
|  | eg Special Grants |  |  |
|  | Contributions from voluntary bodies |  |  |

| # NEW CAPITAL SCHEME PROFORMA |  |  |  |
| --- | --- | --- | --- |
| Name of Officer Responsible |  | C Hughes |  |
| Committee |  | Community |  |
| Brief Description of Scheme |  | Relocation of Fitness Room to Longridge Civic Hall |  |
| Full Details of Scheme |  | Relocate Fitness Room from Sports Centre to Civic Hall through the provision of a temporary building. |  |
| Links to Corporate Objectives |  | Making peoples lives safer and healthier |  |
| Cost of Scheme: |  | £ | Notes |
|  | Cost of Land |  |  |
|  | Contractor | 18,600 |  |
|  | Fees |  |  |
|  | Internal Staff Salaries |  |  |
|  | Planning/Build Regs Fees |  |  |
|  | Other costs |  |  |
|  |  | 18,600 |  |

| Revenue Implications of the Scheme per year |  | £ | Details |
| --- | --- | --- | --- |
| Timescale (incl any key dates) |  |  |  |
|  | eg start on site |  | TBA as part of ongoing negotiations with the school |
|  | scheme completion |  |  |
|  | other dates… |  |  |
| Financial Year/(s) the scheme will take place |  |  |  |
| if the scheme will cover more than one year please breakdown the cost for each year |  |  |  |
|  | Year eg | £ |  |
|  | 2007/08 | 18,600 |  |
| Capital Funding & Sources |  |  |  |
|  | eg Special Grants |  |  |
|  | Contributions from voluntary bodies |  |  |

| # NEW CAPITAL SCHEME PROFORMA |  |  |  |
| --- | --- | --- | --- |
| Name of Officer Responsible |  | Rod Pearce |  |
| Committee |  | Community |  |
| Brief Description of Scheme |  | Energy efficiency measures to Ribblesdale Pool |  |
| Full Details of Scheme |  | Provide new energy efficiency measures and upgrade existing as recommended by Carbon Trust energy survey of Pool. Measures will include erection of a 15m wine turbine, replace heat exchangers, variable speed fans, chp (combined heat and power) unit and other minor items to increase energy efficiency /Green label of pool. |  |
| Links to Corporate Objectives |  | Make peoples lives safer and healthier. Protect and enhance the existing environmental quality of our area. |  |
| Cost of Scheme: |  | £ | Notes |
|  | Cost of Land |  |  |
|  | Contractor | 85,000 |  |
|  | Fees | 8,500 |  |
|  | Internal Staff Salaries | 8,500 |  |
|  | Planning/Build Regs Fees | 2,500 |  |
|  | Other costs |  |  |
|  |  | 104,500 |  |

| Revenue Implications of the Scheme per year |  | £ | Details |
| --- | --- | --- | --- |
|  |  |  | Wind turbine maintenance at 5 years |
| Timescale (incl any key dates) |  |  |  |
|  | eg start on site | April 2007 |  |
|  | scheme completion | March 2008 |  |
|  | other dates… |  |  |
| Financial Year/(s) the scheme will take place |  |  |  |
| if the scheme will cover more than one year please breakdown the cost for each year |  |  |  |
|  | Year eg | £ |  |
|  | 2007/08 | 104,500 |  |
| Capital Funding & Sources |  |  |  |
|  | eg Special Grants |  |  |
|  | Contributions from voluntary bodies |  |  |
|  | £5,000 grant towards wind turbine from low carbon buildings programme. |  |  |

| # NEW CAPITAL SCHEME PROFORMA |  |  |  |
| --- | --- | --- | --- |
| Name of Officer Responsible |  | R Pearce |  |
| Committee |  | Community |  |
| Brief Description of Scheme |  | Replace steel windows to building Ribblesdale Pool |  |
| Full Details of Scheme |  | Replacement of existing steel/timber composite windows in UPVC. Existing windows poor from an energy efficiency position and timber sections are beginning to decay. PVC will reduce fuel usage and CO2 emissions and reduce planned maintenance due to no requirement to redecorate. |  |
| Links to Corporate Objectives |  | To make peoples lives safer and healthier. To protect and enhance the existing environmental quality of our area. |  |
| Cost of Scheme: |  | £ | Notes |
|  | Cost of Land |  |  |
|  | Contractor | 30,000 |  |
|  | Fees | 0 |  |
|  | Internal Staff Salaries | 3,000 |  |
|  | Planning/Build Regs Fees | 400, |  |
|  | Other costs | 3,000 | Contingency |
|  |  | 36,400 |  |

| Revenue Implications of the Scheme per year |  | £ | Details |
| --- | --- | --- | --- |
| Timescale (incl any key dates) |  |  |  |
|  | eg start on site | December 2007 |  |
|  | scheme completion | December 2007 |  |
|  | other dates… |  |  |
| Financial Year/(s) the scheme will take place |  |  |  |
| if the scheme will cover more than one year please breakdown the cost for each year |  |  |  |
|  | Year eg | £ |  |
|  | 2007/08 | 36,400 |  |
| Capital Funding & Sources |  |  |  |
|  | eg Special Grants |  |  |
|  | Contributions from voluntary bodies |  |  |

| # NEW CAPITAL SCHEME PROFORMA |  |  |  |
| --- | --- | --- | --- |
| Name of Officer Responsible |  | C Hughes/Rod Pearce |  |
| Committee |  | Community |  |
| Brief Description of Scheme |  | Improvement to Castle Keep |  |
| Full Details of Scheme |  | See enclosed for Phase 1 Phase 2 = Repairs and internal and external keep walls, repairs to curtain wall, repairs to war memorial wall. |  |
| Links to Corporate Objectives |  | To protect and enhance the existing environmental quality of our area |  |
| Cost of Scheme: |  | £ | Notes |
|  | Cost of Land |  |  |
|  | Contractor | 179,400 |  |
|  | Fees | 10,000 |  |
|  | Internal Staff Salaries | 0 |  |
|  | Planning/Build Regs Fees | 0 |  |
|  | Other costs | 0 |  |
|  |  | 189,400 |  |

| Revenue Implications of the Scheme per year |  | £ | Details |
| --- | --- | --- | --- |
|  |  |  | None |
| Timescale (incl any key dates) |  | Phase 1 | Phase 2 |
|  | eg start on site | November 2006 | 2008/09 |
|  | scheme completion | March 2007 |  |
|  | other dates… |  |  |
| Financial Year/(s) the scheme will take place |  |  |  |
| if the scheme will cover more than one year please breakdown the cost for each year |  |  |  |
|  | Year eg | £ |  |
|  | 2006/7 | 79,400 |  |
|  | 2008/09 | 110,000 |  |
| Capital Funding & Sources |  |  |  |
|  | eg Special Grants |  |  |
|  | Contributions from voluntary bodies |  |  |
|  | Regional Park Grant Contribution from Ribblesdale Rotary Club |  |  |

| # NEW CAPITAL SCHEME PROFORMA |  |  |  |
| --- | --- | --- | --- |
| Name of Officer Responsible |  | Rod Pearce |  |
| Committee |  | Community |  |
| Brief Description of Scheme |  | Refurbish wc’s and showers to Roefield Changing Rooms |  |
| Full Details of Scheme |  | Refurbishment of showers and wc’s to existing changing rooms. This is deemed necessary initially due to high legionella risk from the stored hot water system. The upgrade will replace all stored water supplied fittings with instantaneous showers and water heaters. The existing floor coverings cubicles, wall tiles and sanitary fittings will also be replaced. |  |
| Links to Corporate Objectives |  | Make peoples lives safer and healthier |  |
| Cost of Scheme: |  | £ | Notes |
|  | Cost of Land |  |  |
|  | Contractor | 20,000 |  |
|  | Fees |  |  |
|  | Internal Staff Salaries | 2,000 |  |
|  | Planning/Build Regs Fees |  |  |
|  | Other costs | 2,000 | Contingency |
|  |  | 24,000 |  |

| Revenue Implications of the Scheme per year |  | £ | Details |
| --- | --- | --- | --- |
| Timescale (incl any key dates) |  |  |  |
|  | eg start on site | May 2007 |  |
|  | scheme completion | August 2007 |  |
|  | other dates… |  |  |
| Financial Year/(s) the scheme will take place |  |  |  |
| if the scheme will cover more than one year please breakdown the cost for each year |  |  |  |
|  | Year eg | £ |  |
|  | 2007/08 | 24,000 |  |
| Capital Funding & Sources |  |  |  |
|  | eg Special Grants |  |  |
|  | Contributions from voluntary bodies |  |  |

| # NEW CAPITAL SCHEME PROFORMA |  |  |  |
| --- | --- | --- | --- |
| Name of Officer Responsible |  | Graham Jagger |  |
| Committee |  | Community |  |
| Brief Description of Scheme |  | Gisburn Forest Park Cycling Trails and Ribble Valley Cycling Strategy Initiatives |  |
| Full Details of Scheme |  | The Existing trails at Gisburn Forest Park are outdated in their design and redevelopment of the network will provide a resource capable of attracting increased numbers and appeal to a wider audience. This will also raise the Ribble Valley’s profile as a cycling tourism destination and generate income for the area. Approximately 16km of trail would be either created or resurfaced to create a range of trails suitable for family groups and experienced cyclists alike. Forest Enterprise, United Utilities and Lancashire County Council have all stated that they will contribute towards the scheme with match funding monies and staff time. To carry out work to continue to deliver the Cycling Strategy. |  |
| Links to Corporate Objectives |  | To help make people’s lives safer and healthier. To protect and enhance the existing environmental quality of our area. |  |
| Cost of Scheme: |  | £ | Notes |
|  | Cost of Land |  |  |
|  | Contractor |  |  |
|  | Fees |  |  |
|  | Internal Staff Salaries | 1,000 |  |
|  | Planning/Build Regs Fees |  |  |
|  | Other costs | 24,000 | Grant match funding and purchases |
|  |  | 25,000 |  |

| Revenue Implications of the Scheme per year |  | £ | Details |
| --- | --- | --- | --- |
|  |  | 0.00 | Maintenance of the new trails will be carried out by Forest Enterprise as part of their site management |
| Timescale (incl any key dates) |  |  |  |
|  | eg start on site | Feb 2007 (est) | Formulisation of the Gisburn Forest Steering Group |
|  | scheme completion |  |  |
|  | other dates… | Mar 2007 (est) | Submission of grant bid |
|  |  | Mar 2008 (est) | Completion of new trails |
| Financial Year/(s) the scheme will take place |  |  |  |
| if the scheme will cover more than one year please breakdown the cost for each year |  |  |  |
|  | Year eg | £ |  |
|  | 2007/08 | 20,000 | Match funding towards grant bid |
|  | 2007/08 | 5,000 | Cycling Strategy work |
| Capital Funding & Sources |  |  |  |
|  | eg Special Grants |  |  |
|  | Contributions from voluntary bodies |  |  |
|  | Forest Enterprise, United Utilities and Lancashire County Council have all stated that they will contribute towards the scheme with additional match funding monies and staff time. The remaining money will be made up of Grant Funding from Sport England. |  |  |

| # NEW CAPITAL SCHEME PROFORMA |  |  |  |
| --- | --- | --- | --- |
| Name of Officer Responsible |  | Graham Jagger |  |
| Committee |  | Community |  |
| Brief Description of Scheme |  | New Vehicle to meet requirements of extension of Three Stream Waste Collection |  |
| Full Details of Scheme |  | New Vehicle to meet requirements of extension of Three Stream Waste Collection |  |
| Links to Corporate Objectives |  |  |  |
| Cost of Scheme: |  | £ | Notes |
|  | Cost of Land |  |  |
|  | Contractor |  |  |
|  | Fees |  |  |
|  | Internal Staff Salaries |  |  |
|  | Planning/Build Regs Fees |  |  |
|  | Other costs | 190,000 | Purchase of Vehicle |
|  |  | 190,000 |  |

| Revenue Implications of the Scheme per year |  | £ | Details |
| --- | --- | --- | --- |
| Timescale (incl any key dates) |  |  |  |
|  | eg start on site |  |  |
|  | scheme completion | 190,000 | 2007/08 |
|  | other dates… |  |  |
| Financial Year/(s) the scheme will take place |  |  |  |
| if the scheme will cover more than one year please breakdown the cost for each year |  |  |  |
|  | Year eg | £ |  |
|  | 2007/08 | 190,000 |  |
| Capital Funding & Sources |  |  |  |
|  | eg Special Grants |  |  |
|  | Contributions from voluntary bodies |  |  |

| # NEW CAPITAL SCHEME PROFORMA |  |  |  |
| --- | --- | --- | --- |
| Name of Officer Responsible |  | Rod Pearce |  |
| Committee |  | Community |  |
| Brief Description of Scheme |  | Reconstruction and relocation of Whalley wc’s |  |
| Full Details of Scheme |  | To provide funding towards the reconstruction of Whalley Public Conveniences with a relocation to Whalley Bus Station. The Scheme is in conjunction with Whalley Parish Council who will provide the remainder of the funding to complete the scheme. RVBC will then undertake the maintenance of the toilets. |  |
| Links to Corporate Objectives |  | Make people’s lives safer and healthier. To protect and enhance the existing environmental quality of our area. |  |
| Cost of Scheme: |  | £ | Notes |
|  | Cost of Land |  |  |
|  | Contractor |  |  |
|  | Fees |  |  |
|  | Internal Staff Salaries |  |  |
|  | Planning/Build Regs Fees |  |  |
|  | Other costs | 50,000 | Funding to Whalley PC |
|  |  | 50,000 |  |

| Revenue Implications of the Scheme per year |  | £ | Details |
| --- | --- | --- | --- |
|  |  |  | Cleaning and general upkeep |
| Timescale (incl any key dates) |  |  | To be determined by Whalley PC |
|  | eg start on site |  |  |
|  | scheme completion |  |  |
|  | other dates… |  |  |
| Financial Year/(s) the scheme will take place |  |  |  |
| if the scheme will cover more than one year please breakdown the cost for each year |  |  |  |
|  | Year eg | £ |  |
|  | 2007/08 | 50,000 |  |
| Capital Funding & Sources |  |  |  |
|  | eg Special Grants |  |  |
|  | Contributions from voluntary bodies |  |  |

| # NEW CAPITAL SCHEME PROFORMA |  |  |  |
| --- | --- | --- | --- |
| Name of Officer Responsible |  | Rod Pearce |  |
| Committee |  | Community |  |
| Brief Description of Scheme |  | Chipping WC’s Refurbishment and extension of existing conveniences providing increased facilities with baby change room. |  |
| Full Details of Scheme |  | The existing conveniences located on Chipping car park are in need of refurbishment and are currently undersized for the number of visitors to Chipping. The refurbishment will provide a larger facility with the incorporation of a baby change facility. This scheme was planned for 2001 but was shelved due to lease issues. |  |
| Links to Corporate Objectives |  | To make people’s lives safer and healthier. To protect and enhance the existing environmental quality of our area. |  |
| Cost of Scheme: |  | £ | Notes |
|  | Cost of Land |  |  |
|  | Contractor | 63,000 |  |
|  | Fees | 1,400 | 10% |
|  | Internal Staff Salaries | 1,400 | 10% |
|  | Planning/Build Regs Fees |  | Fees previously paid in 2001 |
|  | Other costs | 9,200 | Prelims |
|  |  | 75,000 |  |

| Revenue Implications of the Scheme per year |  | £ | Details |
| --- | --- | --- | --- |
|  |  | 1,000 | Increased annual maintenance from existing facility. |
| Timescale (incl any key dates) |  |  |  |
|  | eg start on site | Sept 2007 |  |
|  | scheme completion | Nov 2007 |  |
|  | other dates… |  |  |
| Financial Year/(s) the scheme will take place |  |  |  |
| if the scheme will cover more than one year please breakdown the cost for each year |  |  |  |
|  | Year eg | £ |  |
|  | 2007/08 | 75,000 |  |
| Capital Funding & Sources |  |  |  |
|  | eg Special Grants |  |  |
|  | Contributions from voluntary bodies |  |  |