INFORMATION

RIBBLE VALLEY BOROUGH COUNCIL

##### REPORT TO

##### OVERVIEW & SCRUTINY (RESOURCES) COMMITTEE

Agenda Item No.

| meeting date: | 22 February 2007 |
| --- | --- |
| title: | Procurement Strategy Action Plan and Joint Procurement Activities - Progress Report |
| submitted by: | Director of Resources |
| principal author: | Lawson Oddie – Senior Accountant |

- PURPOSE

  - To update Members on the Procurement Strategy action plan and to provide an overview of current procurement activities.

- BACKGROUND

  - The council’s Procurement Strategy was approved by the Overview and Scrutiny (Resources) Committee in June 2006. Part 3 of the Procurement Strategy contains the Procurement Strategy Action Plan and it was agreed that this be monitored on a six monthly basis and this Committee monitor progress.

  - The Procurement and Contract Management Steering Group met in November 2006 and the revised Action Plan is attached at Appendix A.

- ACTION PLAN REVIEW

  - Since the last meeting of the Procurement and Contract Management Steering Group a number of items on the attached Action Plan have been completed or are currently underway.

  - A procurement user guide is now available to staff on the council’s intranet located together with the Procurement Strategy, Financial Regulations and the Contract Procedure Rules.

  - Contract Award and Management training has been provided through the East Lancashire ePartnership (ELeP) and it is planned to extend the provision of this training from ELeP to departmental staff responsible for contract award and management.

  - Work is currently underway to develop a set of performance indicators and measures for procurement, which can then be reported to members in the same manner as other local performance indicators.

  - All ELeP partners are now working to produce standardised tender letting and evaluation documentation and this is also being reviewed at a wider regional level with ELeP representing its partners at the North West Centre of Excellence Standards Group.

- STATUS AND PERFORMANCE OF JOINT PROCUREMENTs

  - Janitorial Supplies (Options Hygiene Ltd) Potential Annual Savings £4,230: This contract has recently been extended until the end of October 2007 at which point the options of re-tendering or joining an existing framework agreement will be assessed.

  - Protective Clothing (Porter Bros & Gardner Ltd) Potential Annual Savings £5,210: This contract continues to run without any issues and is due for renewal in June 2007.

  - Office Consumables (Office Depot UK Ltd) Potential Annual Savings £8,610: This contract was awarded in January this year and replaces three separate contracted suppliers that existed for Office Stationery, IT Consumables and Paper. As part of the environmental considerations on this contract this council now uses recycled white paper and is looking to rationalise the number of deliveries to the offices for non-urgent products.

  - IT Hardware (Hewlett Packard Ltd) Potential Annual Savings £5,000: This contract was awarded in November 2006 following a joint tender exercise undertaken with the ELeP partners in conjunction with the North West Centre of Excellence (NWCE) and the Office of Government Commerce (OGC). This Framework Agreement includes the purchase of Laptop and Desktop packages.

  - Vehicle Fuel (Carlton Fuels Ltd) Potential Annual Savings £500: This contract is for fuel stored at the depot for use in our vehicles. In considering the environmental impact of our operations the option of using Bio Fuels was examined and we are now operating our fleet on a 5% Bio Fuel.

  - Telecommunications (Thus Plc) – Potential Annual Savings £7,260: This contract is for the provision of telecommunications (line rental and voice calls) and is due for renewal in December 2007.

  - Furniture (H Jenkinson & Co Ltd) Potential Annual Savings £1,000: This contract is through the LAPP Framework Agreement and runs through to November 2007 with options to extend for a further two years.

  - Postal Services (UK Mail) Potential Annual Savings £2,500: No contract has been awarded for this service, however the ELeP partners entered a three month trial (which ends February 2007) with UK Mail for all the council’s second class mail. UK Mail collect and sort the post then deliver it to local Royal Mail distribution offices who are responsible for the 'final mile' of delivery. A number of problems have been encountered during the trial, notably late delivery of post and incorrect invoicing.

  - A number of ongoing and planned joint procurement exercises are shown below and will be reported on in more details as and when they are awarded.

- Recruitment and Advertising Services

- Heating Oil

- Vehicle Purchase and Lease

- Mobile Phones

- Plastic Sacks

- Agency Staff

- RISK ASSESSMENT

  - This contents of this report may have the following implications

- Resources – delivery of the above projects can be achieved with the existing procurement resources within the Financial Services section

- Technical, Environmental and Legal – the Legal Service section have been fully involved in the development of standardised tender letting and evaluation documentation.

  - Political: none.

  - Reputation: The delivery of contracted services to an agreed standard is part of the contract monitoring process and regular meetings are held with the contracted and trial period suppliers. Problems have been experienced with the postal service trial with UK Mail and by the nature of the service this has impacted on both internal and external customers.

- RECOMMENDed that committee

  - Note the contents of this report.

SENIOR ACCOUNTANT

12 FEBRUARY 2007

### PROCUREMENT STRATEGY – ACTION PLAN

Note :N = Action point compatible with the Government’s National Procurement Strategy

| #### ACTION POINT | RESOURCE REQUIREMENT |  |  | OFFICER/S RESPONSIBLE | HOW MONITORED AND MEASURED |  |  |  | TARGET DATE |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| # OWNERSHIP, MONITORING AND REVIEW |  |  |  |  |  |  |  |  |  |  |  |
| # (N) Ribble Valley Borough Council has developed this Strategy and the responsibility for its implementation, monitoring and review lies with all members and officers of the Council. | Corporate Services Manager |  |  | Corporate Services Manager | Reports to Overview and Scrutiny (Res)Committee |  |  |  | Ongoing |  |  |
| # (N) The Action Plan will be monitored on a six monthly basis by the Overview and Scrutiny (Resources) Committee | Corporate Services Manager |  |  | Corporate Services Manager | Reports to Overview and Scrutiny (Res)Committee |  |  |  | Every 6 months |  |  |
| # DEVELOP ROLE AND FUNCTIONS OF A PROCUREMENT OFFICER |  |  |  |  |  |  |  |  |  |  |  |
| # Establish a job description, role and responsibilities for and of a new post of Procurement Officer | Financial Management Team time |  |  | Financial Services Manager Senior Accountant | Report to Personnel Committee |  |  |  | Achieved July 06 |  |  |
| # Appoint to new post of Procurement Officer | Salary + costs |  |  | FSM/ Snr Acct | Post filled |  |  |  | Achieved |  |  |
| # STANDING ORDERS AND FINANCIAL REGULATIONS |  |  |  |  |  |  |  |  |  |  |  |
| Review and revise the Council’s Standing Orders & Financial regulations to take account of the procedures set out in the e-procurement policy. | Director of Resources |  |  | Director of Resources | Adopted By Council |  |  |  | June 2006 |  |  |
| Develop & maintain a Code of Practice/ Procurement User Guide | Procurement Officer |  |  | Procurement Officer | Documents in place |  |  |  | Oct 2006 |  |  |
| Ensure that all staff involved in procurement are aware of & understand the requirements of S.O’s & Financial Regulations. Supported by /in conjunction with training provided to ELEP Wkg Group | Training sessions |  |  | Snr Accountant ELEP Procurement Officer | Training programme |  |  |  | mid Jan 2007 |  |  |
| Ensure compliance with S.O’s & Financial Regulations | Internal Audit |  |  | Service Managers & Internal Audit | Ongoing |  |  |  | Ongoing |  |  |
| # POLICY & STRATEGY IMPLEMETATION |  |  |  |  |  |  |  |  |  |  |  |
| Ensure that the principles of risk management are applied to all new & existing procurement contracts and projects* | Procurement Officer Service Managers |  |  | Service Managers | Contract compliance |  |  |  | Ongoing |  |  |
| Ensure that health & safety issues are addressed in all new and existing contracts * | Procurement Officer Service Managers |  |  | Service Managers | Contract compliance |  |  |  | Ongoing |  |  |
| (N) Ensure that equality issues are addressed in all new and existing contracts * | Procurement Officer Service Managers |  |  | Service Managers | Contract compliance |  |  |  | Ongoing |  |  |
| (N) Ensure regeneration issues are considered in all new/ existing contracts. RVBC to encourage a diverse/ competitive supply market inc. small firms, social enterprises, ethnic minority businesses & voluntary/ community sector suppliers. * | Procurement Officer Service Managers |  |  | Service Managers | Contract compliance |  |  |  | Ongoing |  |  |
| (N) The Council to sign up to the national Concordat for SME’s | Chief Executive |  |  | Chief Executive | Concordat signed Check with Anne A |  |  |  | August 2006 |  |  |
| (N) Ensure that the objectives of the Community Plan are considered in all new and existing contracts * | Service Managers |  |  | Service Managers | Reports to Corporate Management Team |  |  |  | 6 monthly |  |  |
| (N) Develop and conclude a compact with the voluntary and community sector for the provision of services where appropriate * | Regeneration Officer |  |  | Regeneration Officer | Compact in place Check with Anne A |  |  |  | Achieved |  |  |
| (N) Ensure sustainability issues are considered in all new and existing contracts * eg. energy procurement Note: All actions marked * are addressed in Contract Procedure Rules – RVBC Oct 2006 | Service Managers |  |  | Service Managers | Contract compliance |  |  |  | 6 monthly |  |  |
| PROCUREMENT OF MAJOR SERVICES AND PARTNERSHIPS | RESOURCE REQUIREMENT |  | OFFICER/ S RESPONSIBLE |  | HOW MONITORED AND MEASURED |  |  |  | TARGET DATE |  |  |
| (N) Ensure that staff that may be affected by a major procurement project are consulted at each stage of the process. Employment considerations shall be built into the process including compliance with the Local Government Act 2003. | Project team |  | Project manager |  | Ongoing |  |  |  | Ongoing |  |  |
| (N) Give active consideration to meeting the corporate objectives of the Council in a range of service delivery, maintenance and construction projects by way of partnership working. This would be by either partnering arrangements with either the Public or Private sector, or collaboration with other councils to jointly procure or commission services. The number of active partnerships shall be recorded and reported, and opportunities for such arrangements identified. Ensure is inc. in Corporate Plan | Monitoring of National and local opportunities for Partnership and Collaboration. |  | Corporate Services Manager Procurement Officer Management Team |  | Annual review of RVBC Corporate Plan Due May/June 2007 |  |  |  | Ongoing |  |  |
| (N) All best value service reviews shall include a robust and challenging appraisal of the different service delivery models available. | Best Value Service Review Teams |  | Corporate Services Manager |  | Outcome of Reviews inc. subsequent inspections. |  |  |  | Ongoing |  |  |
| (N) Ensure RVBC representation at Regional Centre of Excellence in Procurement and Contract Management events. | Officer time ELEP fees |  | ELEP Procurement Officer |  | Attend NWCoE Procurement events & report back to CMT |  |  |  | Ongoing |  |  |
| (N) Systems to be developed to make sure that all OJEU procurement processes take under one year to complete. | Service Managers |  | Service Managers |  | OJEU Periods |  |  |  | Ongoing |  |  |
| (N) The process of review should identify progress against elements of the National Procurement Strategy included within this Strategy. | Staff time to carry out regular reviews |  | Corporate Services Manager |  | Ongoing |  |  |  | Ongoing |  |  |
| (N) For all procurements over £50k, the Council to produce an information memorandum to prospective bidders setting out the background to the project, the Council’s objectives, and the outline and timetable for the procurement process, making clear the roles and responsibilities. | Service Managers ELEP |  | Service Managers |  | Ongoing Included in Contract Procedure Rules |  |  |  | Ongoing |  |  |
| (N) Invitations to tender / negotiate for partnerships to include a requirement to submit optional, priced proposals for delivery of community benefits which are relevant to the contract and add value to the Ribble Valley Community Strategy. | Service Managers ELEP |  | Service Managers |  | Project records |  |  |  | Ongoing |  |  |
| (N) Prospective bidders to demonstrate their track record in achievement of value for money through effective use of their supply chain, including the use of small firms. This will continue to be examined as part of the management of any contract awarded. This can be addressed in standard Invitation to Tender (ITT) document. AB to provide. Tenderers be invited to complete options (variants) in addition to a proposal compliant with ITT specification. | Service Managers ELEP |  | Service Managers |  | Project records Standard ITT doc |  |  |  | Ongoing |  |  |
| #### DEVELOP CONTRACT MANAGMENT PROCEDURES & GUIDELINES | ###### RESOURCE REQUIREMENT |  |  | OFFICER/S RESPONSIBLE |  |  | HOW MONITORED AND MEASURED |  | TARGET DATE |  |  |
| Establish a Procurement and Contract Management Steering Group to comprise: CX, DoR, CSM, Snr Acct (LO), DoCS, E.Member(tbd) + ELEP Proct Mgr | Officer time |  |  | Chief Executive D of R |  |  | Group established Nov 2006 |  | September 2006 |  |  |
| Establish a Procurement and Contract Management Working Group to comprise: CSM, Snr Acct (LO), Principal Bldg Svyr, SSM, C&DMgr, Snr Sol, Regn Off, PA to DoR. DDS to nominate rep | Officer time |  |  | Corporate Services Manager |  |  | Group established |  | September 2006 |  |  |
| Continue to ensure that all contracts are operating within the context of good practice (ref.contract procedure rules) | Procurement Working Group |  |  | Procurement Working Group |  |  | Project records |  | Ongoing |  |  |
| Produce a plan detailing how the Council will approach the development of contract management arrangements. ELEP developing guidance early 2007 following general training | Procurement Working Group |  |  | Procurement Working Group |  |  | Plan produced |  | Feb 2007 |  |  |
| Identify a lead contact officer for each contract across the council with responsibility for maintaining a clear audit trail for the contract | Procurement Working Group |  |  | Procurement Working Group |  |  | Project records |  | Ongoing |  |  |
| Identify how Members will be engaged in contract management. Strategic role approving this Strategy + operational role letting contracts | Procurement & C.Mgt Steering Group |  |  | Procurement & C.Mgt Steering Group |  |  | Project records |  | Ongoing |  |  |
| Provide training in contract management for all officers & Members involved in contract management | Procurement & C.Mgt Steering Group |  |  | ELEP Procurement Mgr |  |  | No. Trained |  | Spring 2007 |  |  |
| Establish and maintain a contract register for all contracts above £50,000 across the Council | Snr. Acct (LO) |  |  | Internal Audit |  |  | Register established |  | Ongoing |  |  |
| Report to Management Team and Members on the status and performance of all capital projects >£50k on a 3 monthly basis via capital monitoring reports. | Service Managers |  |  | Service Managers |  |  | 3 monthly report |  | Ongoing |  |  |
| Report to Management Team and Members on the status and performance of all ELEP contracts on a 6 monthly basis | Procurement Officer |  |  | Procurement Officer |  |  | 6 monthly report |  | Ongoing |  |  |
| Review and re-assess the packaging of all contracts across the Council. AB to provide standard terms and conditions to LO for consideration by Working Group. | Procurement Officer |  |  | Procurement Working Group |  |  | Ongoing |  | April 2007 |  |  |
| FINANCIAL MANAGEMENT SYSTEM & PROCUREMENT |  |  |  |  |  |  |  |  |  |  |  |
| Provide relevant and timely financial management information for procurement | New FMS (Financial Management System) |  |  | Snr Accountant Procurement Officer |  |  | System introduced |  | Achieved |  |  |
| Continue to reduce the number and transaction cost of invoices processed. | New FMS (Financial Management System) |  |  | Snr Accountant Procurement Officer |  |  | Ongoing |  | Ongoing |  |  |
| #### PERFORMANCE MEASUREMENT |  |  |  |  |  |  |  |  |  |  |  |
| Develop and agree a suite of performance indicators & measures for procurement. Working Group to look at list of PIs in use elsewhere. | Review national suite of PIs available |  |  | Procurement Officer ELEP |  |  | New P.I.’s in place |  | Jan 2007 |  |  |
| Develop monitoring and reporting mechanisms for Procurement Performance Information | New FMS (Financial Management System) |  |  | Snr Accountant Procurement Officer |  |  | New P.I.’s in place |  | Jan 2007 |  |  |
| #### TENDERING ARRANGEMENTS |  |  |  |  |  |  |  |  |  |  |  |
| Review and revise the approved supplier lists. AB to assist | Procurement & Contract Mgt Wkg Gp |  |  | Procurement Officer |  |  | No. of lists revised and updated |  | Jan/Feb 2007 |  |  |
| Review & revise the tender letting and evaluation documentation AB to assist | Procurement & Contract Mgt Wkg Gp |  |  | Procurement Officer |  |  | Under development (AB) |  | Jan/Feb 2007 |  |  |
| (N) Produce a guide of ‘How to do Business with the Council’ AB to assist | Procurement & Contract Mgt Wkg Gp |  |  | Procurement Officer |  |  | Document in place |  | Jan/Feb 2007 |  |  |
| PROCUREMENT OF ROUTINE GOODS & SERVICES #### & DOING BUSINESS ELECTRONICALLY | RESOURCE REQUIREMENT | OFFICERS/S RESPONSIBLE |  |  |  | HOW MONITORED AND MEASURED |  | TARGET DATE |  |  |  |
| Identify the categories of the most commonly purchased goods and services by value and volume within the Council (Spend Analysis). Repeat analysis for 06/07 spend in July 2007 | ELEP | Procurement Officer |  |  |  | Work Complete |  | June 2005 |  |  |  |
| (N) Implement an e-Procurement solution as part of the e-Government programme. | New Civica Financial System | Financial Services Manager Procurement Officer |  |  |  | Implementation complete |  | June 2006 |  |  |  |
| Hold a “meet the buyer” event | East Lancashire Chamber of Commerce | ELEP Procurement Officer |  |  |  | Event(s) held |  | April 2007 |  |  |  |
| Develop framework agreements for all contracts | ELEP / ELCOC | Financial Services Manager Procurement Officer |  |  |  | Call off contracts in use |  | Ongoing |  |  |  |
| #### (N) Full use of an appropriate e-Marketplace | Senior Accountant | Senior Accountant |  |  |  | System fully developed |  | Achieved |  |  |  |
| #### ENERGY |  |  |  |  |  |  |  |  |  |  |  |
| Develop a plan to ensure that, as an initial target, 15% of all energy used by the Council is from a guaranteed renewable source to contribute to the UK climate change programme. This proportion to be increased year on year as availability increases. | Procurement & Contract Mgt Steering Group + ELEP | Principal Building Surveyor |  |  |  | By reports from energy suppliers |  |  | April 2007 Check with Rod |  |  |
| Develop a plan to ensure that all energy procured, including renewable source energy, used within the Council is purchased at the most economically advantageous rates | Principal Building Surveyor | Principal Building Surveyor |  |  |  | Ongoing |  |  | Achieved |  |  |
| #### RETHINKING CONSTRUCTION PROCUREMENT |  |  |  |  |  |  |  |  |  |  |  |
| Discuss at Corporate Management Team and appoint a Lead Officer | CMT | Director of Commercial Services |  |  |  | Report to CMT |  |  | Completed |  |  |
| Introduce further procurement partnering arrangements where appropriate | CMT | CMT |  |  |  | Report to CMT |  |  | Ongoing |  |  |
| Monitor success of council house improvement contract | Director of Commercial Services | Director of Commercial Services |  |  |  | Report to CMT & to every Housing Cttee. |  |  | Ongoing |  |  |