RIBBLE VALLEY BOROUGH COUNCIL

INFORMATION

REPORT TO POLICY AND FINANCE COMMITTEE

Agenda Item No

meeting date: 	27 MARCH 2007

title:	CAPITAL PROGRAMME 2007/08

submitted by: 	DIRECTOR OF RESOURCES

principal author: 	JANE PEARSON

1	PURPOSE

1.1	To inform members of the capital programme for this committee for the forthcoming financial year (2007/08).

2	BACKGROUND

  - Full Council approved the 5 year capital programme for 2007/12 on 6 March 2007.

- SCHEMES

  - There are 3 schemes for this committee which total £87,800.  Annex 1 shows more details listing each scheme.

  - During the closure of our capital accounts there will inevitably be some slippage on schemes in the current year.  A report will be brought to committee in June/July giving further details.

  - As in previous years responsible officers have been asked to complete capital evaluation sheets for each new scheme.  These are attached at Annex 2.  I intend to report these quarterly to members to give an indication of progress on schemes.

- RECOMMENDED THAT COMMITTEE

  - Note the report.

JANE PEARSON

FINANCIAL SERVICES MANAGER

PF12-07/JP/AC

14 MARCH 2007

ANNEX 1

CAPITAL PROGRAMME 2007/08

|  |  |  | # Budget Analysis |
| --- | --- | --- | --- |
| Cost |  | Budget Holder | Original |
| Centre | Schemes |  | Estimate |
|  |  |  | 2007/08 |
|  |  |  | £ |
|  | ### Policy & Finance Committee |  |  |
| PRRIS | Replace Risograph Printer | msm | 6,200 |
| OFCEI | Fire safety improvements to council office ceilings | rp | 21,600 |
| TRING | Grant to Trinity | ms | 60,000 |
|  | Total Policy & Finance Committee |  | 87,800 |

ANNEX 2

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | OFCEI |
| Name of Scheme | COUNCIL OFFICES – FIRE SAFETY IMPROVEMENTS TO CEILINGS |  |  |  |
| Officer Responsible | ROD PEARCE |  |  |  |
| Description of Scheme | Replacement of existing suspended ceilings |  |  |  |
| Benefits of Scheme | Improved fire and safety energy performance |  |  |  |
| Project Timetable | Start Date | July 2005 |  |  |
|  | Completion Date |  |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
|  |  | Strip our concealed grid ceiling and replace with exposed grid ceiling |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | None |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | None |  |  |  |

|  |  |  |  |  |  | Cost Centre | OFCEI |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Original Budget for year: |  |  |  |  | £21,600 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £85,757 |  |
|  | Approved by Committee: |  |  |  |  | Council |  |
|  | Date: |  |  |  |  | 1 March 2005 |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  | Actual Expenditure 2005/06 £ | Expected Expenditure 2006/07 £ | Expected Expenditure 2007/08 £ | Total Cost of Scheme £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  | 35,557 | 28,600 | 21,600 | 85,757 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  | 35,557 | 28,600 | 21,600 | 85,757 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| End June 2005 |  | Design works carried out. Delay due to programming on site. Works to start during holiday period to minimise disruption. Anticipate some of the budget may not be needed or may need to be moved to 2006/07, depending on progress. |  |  |  |  |  |
| End Sept 2005 |  | Work complete to several areas, including housing, level C, chief executive. Remaining ceiling due for replacing January 2006. |  |  |  |  |  |
| End Dec 2005 |  | As September 2005 |  |  |  |  |  |
| End March 2006 |  | Work to commence on staircases March 2006. Office area to Level C legal services planned for July 2006. |  |  |  |  |  |
| End Sept 2006 |  | Work delayed since July due to contractor commitments. Work planned October 2006 for Environmental Health Section followed by Legal Services. If funding allows then other items will be identified and work carried out. |  |  |  |  |  |
| End Dec 2006 |  | Work done to Environmental Health Section ceiling. Legal Section to commence February. Hope to carry out other work before end of March. Will be some slippage into 2007/08. |  |  |  |  |  |
| March 2007 |  | Work undertaken to remainder of Level C over weekends of 3, 4 and 10, 11 March 2007. Final phase of work to Level B will be undertaken during 07/08 in June with Budget for 2007/08 |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | PRRIS |
| Name of Scheme | REPLACE RISOGRAPH PRINTER |  |  |  |
| Officer Responsible | MICHELLE SMITH |  |  |  |
| Description of Scheme | To replace the Risograph Printer in central printing department |  |  |  |
| Benefits of Scheme | Enables cost effective production of council papers and documents. High volume machines more cost effective than photocopiers. Machine currently produces one million copies per year. |  |  |  |
| Project Timetable | Start Date | April 2007 |  |  |
|  | Completion Date | April December 2007 |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | N/A |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | N/A |  |  |  |

|  |  |  |  |  |  | Cost Centre | PRRIS |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £6,200 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £6,200 |  |
|  | Approved by Committee: |  |  |  |  | Full Council |  |
|  | Date: |  |  |  |  | 6 March 2007 |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  |  |  |  | Expected Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  | 6,200 |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  |  |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  |  | 6,200 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |
| March 2007 |  | Currently seeking quotes for replacement from supplier |  |  |  |  |  |

| RIBBLE VALLEY BOROUGH COUNCIL |  |  |  |  |
| --- | --- | --- | --- | --- |
| CAPITAL PROGRAMME 2007/08 |  |  |  |  |
| CAPITAL PROJECT EVALUATION STATEMENT |  |  | Cost Centre | TRING |
| Name of Scheme | GRANT TO TRINITY |  |  |  |
| Officer Responsible | MARSHAL SCOTT |  |  |  |
| Description of Scheme | To support the purchase of St Mary’s Centre |  |  |  |
| Benefits of Scheme | To help support the creation of the proposed Arts Centre |  |  |  |
| Project Timetable | Start Date | Summer 2007 |  |  |
|  | Completion Date | N/A |  |  |
|  | Any Other Key Dates | Description of Work |  |  |
| Indication of any problems which may ultimately affect either the project timetable or final costs | Dependant on Trinity progressing scheme, receiving planning permission and support from North West Development Agency/Clitheroe the Future |  |  |  |
| Can the scheme be achieved with existing staff capacity? If not, what do you propose | Yes |  |  |  |
| What are the revenue implications of the scheme? | Loss of interest on Capital Sum/Interest on amount borrowed |  |  |  |

|  |  |  |  |  |  | Cost Centre | TRING |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Financial | Approved Budget for Current Year: |  |  |  |  | £60,000 |  |
| Summary | Expected Total Cost of Scheme: |  |  |  |  | £60,000 |  |
|  | Approved by Committee: |  |  |  |  | Full Council |  |
|  | Date: |  |  |  |  | 6 March 2007 |  |
|  | Minute Ref: |  |  |  |  |  |  |
| Expenditure Analysis |  |  |  |  |  |  | Expected Expenditure 2007/08 £ |
|  | Land |  |  |  |  |  |  |
|  | Cost of Work |  |  |  |  |  |  |
|  | Retention (show separately) |  |  |  |  |  |  |
|  | Other Costs |  |  |  |  |  | 60,000 |
|  | External Fees |  |  |  |  |  |  |
|  | Internal Salaries |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  |  | 60,000 |
| Monitoring - Comments on Progress (Completed Each Period by Officer Responsible) |  |  |  |  |  |  |  |