PROGRAMME OF KEY TASKS FOR 3 STREAM WASTE COLLECTION SERVICE

| # DATE | DAY | ACTION |
| --- | --- | --- |
| 29 October | Monday | - Start of collections on Phase I and trial round and change of collection days for properties on Phase II. |
| 19 October | Friday | - Last day for delivery of wheeled bins and information leaflets to properties on Phase I. - Last day for delivery of leaflets/calendar to properties on trial round. - Last day for delivery of letters to properties on Phase II re change of collection day, etc. |
| 12 October | Monday | - Finalise press release for CA&T on 18/25 October, Longridge News on 19/26 October, Lancs Telegraph week commencing 22 October. |
| 1 October | Monday | - Delivery of wheeled bins to properties on Phase I to start today (including information leaflets) – allows 3 week delivery period. - Delivery of additional wheeled bins to some properties on trial round to start today. |
| 28 September | Friday | - Last day by which letters to properties on Phase I are to be received advising of new arrangements and delivery of bins. - Last day by which new information leaflets are to be supplied to RVBC from printers. |
| 17 September | Monday | - Start distribution of letters to properties in Phase I advising of new arrangements and delivery of wheeled bins (+ properties on trial scheme) – allows 2 week delivery period. - Start production of leaflets (12315) |
| 14 September | Friday | - Last day by which details of revisions to information leaflets shall be with the printers. - Sign off new leaflets. |
| 13 September | Thursday | - Second/final amendments and send to printer. |
| 12 September | Wednesday | - Return of second proofs from printer. |
| 11 September | Tuesday | - Meeting of Community Committee where members are to get report updating on progress. |
| 7 September | Friday | - Last day by which Titan require full address list for chipping and delivery of wheeled bins. - Complete first amendments and send to printer. |
| DATE | DAY | ## ACTION |
| 3 September | Monday | - Last date for start of revision of information leaflets. - Report to Community Committee to be completed by today. |
| 31 August | Friday | - Return of first proofs for leaflet from printer. |
| 24 August | Friday | - Last date for receipt of revised rounds schedules from ENTEC. - Copy deadline for updated leaflets to send to printer. |
| 20 August | Monday | - Start drafting of letters and production of delivery point plans. |
| 13 August | Monday | - Start sorting data for plans for collection prints. |
| 10 August | Friday | - Last day by which data is to be sent to ENTEC for production of final rounds design and schedules. |