- Lancashire Local Area Agreement

- Programme Plan

- 2007/08

for

#### Ribble Valley Borough Council

Version Control

| Release | Release Date | Release Notes |
| --- | --- | --- |
| v.1.0 | 10.08.07 | Complete except for PSA performance |
| v.1.1 | 06.09.07 | PSA performance data included to Q1 2007/08. |

| 1. Contact Details Name of Contact Person: Jeffrey Fenton |  |  |
| --- | --- | --- |
| Title and Role: Corporate Services Manager |  | # Organisation: # Ribble Valley BC |
| Address: Council Offices, Church Walk, Clitheroe, Lancs BB7 2RA |  |  |
| # Telephone:01200 414593 |  | # Mobile: |
| Fax: 01200 414488 |  | Email:jeff.fenton@ribblevalley.gov.uk |
| Website (if applicable): www.ribblevalley.gov.uk |  |  |
| 1a. Contact Details ( Finance Lead) : Trudy Holderness |  |  |
| Title and Role: Senior Accountant | # Organisation: # Ribble Valley BC |  |
| Address: As above |  |  |
| # Telephone:01200 414436 | # Mobile: |  |
| Fax: 01200 414488 | Email: trudy.holderness@ribblevalley.gov.uk |  |
| Start Date: 1st April 2007 | End Date: 31st March 2008 |  |

2 Programme Summary: Summarise the main purpose of your programme identifying how it addresses the Local Area Agreement (LAA). LAA Programme funding at RVBC is received via four specific grant streams – Anti Social Behaviour (ASB), Building Safer Communities Fund (BSCF), Waste Performance and Efficiency Grant (WPEG) and Rural and Social Community Programme (RSCP). The funding contributes towards activities that, in turn, contribute towards the outcomes outlined in the LAA. Although all the funding is delivered via the Safer and Stronger Communities (SSC) block, the RSCP stands alone in that the activities it funds contribute towards Healthier Communities and Older People (HCOP) block. All these grants are revenue funding but in addition the BSCF and WPEG grants also include separate capital funding elements. The funding is used to support three main areas of activity – A. Rural Housing initiatives (RSCP), B. waste management (WPEG), and C. building safer communities (ASB & BSCF). These are detailed on the following pages annotated with the letters given here (i.e. A, B & C). A. The Ribble Valley and Pendle Rural Housing Enabler Scheme is a united initiative between the Borough Councils of Ribble Valley and Pendle. The scheme was formed to improve the position of affordable housing within rural areas and comes under the national network of Rural Housing Enablers The project aims to work with local groups and other partners to increase the supply of affordable housing in rural communities where it is needed. Affordable housing is about providing places to live for local people who are struggling to get on the property ladder, or who cannot afford market rents and prices. It is about ensuring that people can stay and live in their local community if they wish and about keeping those communities vibrant and sustainable with a good mix of residents in terms of ages and skills. The role of Ribble Valley and Pendle’s Rural Housing Enabler is to:- - Undertake parish-wide housing needs surveys to investigate local needs across the whole of the Ribble Valley and rural Pendle. - Work in partnership with local communities, Parish Councils and other organisations such as housing associations, local authority housing and planning departments, landowners and developers to explore development options to meet identified needs within Parishes. - Promote the value of affordable housing as a means of securing sustainable rural communities. - Promote the importance of affordable housing to residents in rural communities and provide them with information about affordable housing, housing associations, low cost home ownership, and shared ownership and equity schemes. - Influence future policy. - Act as an honest broker between all parties. The work of the Rural Housing Enabler Scheme will also define an accurate picture of the housing needs parishes, both now and in the future. This information can then be used by planners and housing services to:- - Develop up to date strategies, which include the need for affordable houses in rural parishes. - Assist planning officers when negotiating agreements for social housing to be included in new housing developments. - Identify redundant and derelict buildings, which can be brought back into use for both residential and economic redevelopment. - Identify areas of good practice pertaining to sustainable development of new build, redundant buildings, construction methods and regeneration of rural communities. - Assist in developing more open community engagement with regard to planning applications. It meets the Healthy Communities and Older People Block by increasing the amount of affordable decent housing brought on stream. It also ‘improves the quality of life for people in the most disadvantaged neighbourhoods and ensures service providers are more responsive to neighbourhood needs and improved service delivery’ under the Safer and Stronger Communities Block. The majority of rural parishes targeted by this scheme are classified as disadvantaged through the access to affordable homes. ##### B. Waste Management and Recycling WPEG funding is being used to contribute towards the Council’s major new 3 stream waste collection scheme. The £1.2m scheme is being introduced to help the council meet its demanding targets to increase the proportion of domestic waste that is being recycled, whilst at the same time reducing the amount going to landfill. C. Safer communities – reducing crime and anti-social behaviour. Main focus of activity is addressing PSA 1– a 3 year target set in 2005 to reduce crime by 13.5% by 31.03.08, and reducing fear of crime and encouraging greater community engagement.

3.  Key Objectives:  Identify the key objectives/strands that will be delivered to meet the outcomes and indicators of the LAA Blocks.

Safer Stronger Communities (SSC)

Improves the quality of life for people in the most disadvantaged neighbourhoods and ensures service providers are more responsive to neighbourhood needs and improved service delivery.

Reducing PSA 1 crime by 13.5%

Reducing Fear of Crime

Increasing Community Engagement

Healthier Communities & Older People (HCOP)

Increasing the amount of affordable decent housing brought on stream

Children & Young People (CYP)                             )        Not detailed – these activities

)

Economic Development and Enterprise (ED&E)     )          are  not in receipt of LAA

)

Cross Cutting (CC)                                                 )           Pooled Allocation funding

4.	How is the VCFS sector involved in the development and delivery of your programme to deliver the LAA?

A. Local Housing Needs Surveys are undertaken in partnership with Parish Councils and include active Community Groups such as Parish Plan and Parish Plan Subgroups, Village Hall Committee Groups, Almshouse Association etc. As well as district and sub-regional groups such as Ribble Valley Senior Action Group and East Lancs Disability Awareness Group in order to quantify realistic affordable housing needs within a Parish.

B. No involvement

C. Minimal involvement

5.	Identify the posts created and/ or appointed in administering the programme funded wholly or partly by the LAA?

1. Quality of Life Officer (part) RVBC £16,500 ASB

2. Community Sports Facilitator (part) RVBC £2,750 ASB, £10,000 BSCF.

3. PPO Coordinator (part) National Probation Service, Lancs (East Division) £6,600 BSCF

4. Drug education workers (x2) LCC Youth & Community Team £17,500 BSCF.

5. Rural Housing Enabler (part) RVBC £19,920 RSCP

| 6. Identify the significant risk factors that may hinder the delivery of the LAA outcomes and outline contingency plans. |  |
| --- | --- |
| Risks | Contingency |
| A. RHE Leaving | Re-advertise job and appoint a.s.a.p. Look at outside consultants / Housing Association / or Rural Community Council (Community Futures) to meet work demands and commitments, during re-appointment stage |
| B. The LAA outcome could be affected by a failure by one of the contractors supplying goods /services to RVBC, but this is covered by separate risk management arrangements governing the contract. |  |
| C. Withdrawal of funding from LAA | Look at other sources of funding |

- How will the funding and performance for LAA be controlled and monitored?

General: Budget is monitored on a monthly basis, with variances in excess of £1,000 reported to management team on a monthly basis and to committees on a quarterly basis.

Performance is monitored on an ongoing basis by the relevant officers and their line (Service) managers with significant variances reported to senior management. Relevant indicators are provided to the Corporate Services Team for inputting to RVBC’s and LCC’s performance management systems (Covalent and Perform).

A. Line manager for RHE role is Rachel Stott and for Pendle BC Clive Thomasson. Reporting will also be undertaken to the Housing Matters Group of the Healthier Communities block.

B. Funding controlled through RVBC Finance Dept (dedicated accountant). Performance is reviewed on a monthly basis by the multi-agency Criminal Damage Sub Group and Violent Crime Sub Group who receive up to date statistics from a Police Analyst. Performance is also monitored by the CDRP Steering Group every 2 months. Internally (within RVBC) performance is also monitored via BVPIs 82a(i) and (ii), 82b (i) and (ii), 84a, 84b and 86 annually, and three yearly through various satisfaction indicators including BVPI 89 and 90.

C. Performance is monitored by a range of specific measures BVPI 225 half yearly and BVPI 126, 127a, 127b and 128 quarterly. The PSA measures are listed in the performance summary that is attached at Part 2 (Section 10) below.

8.	How will programme be evaluated and when?

A report detailing the Council’s overall progress on the LAA will be reported to Overview and Scrutiny (Resources) Committee in October 2007.

RHE Evaluated internally on a yearly basis.

Programme is evaluated on a quarterly basis by the Working Group.

9.	Please state what assets exceeding £10,000 wholly or partly funded by the LAA you may look to acquire or improve, provide outline costs?

| Asset | Costs |
| --- | --- |
| Refuse Collection vehicle (part funded) | £24,457 WPEG capital contribution towards new refuse collection fleet (part of total scheme cost of £1.2m) |

- Key Strategic Milestones (refer to question 6)

This should only include key strategic milestones for your programme giving an indication that if they are not achieved there will be a significant impact on the programme.

| Quarter 1 Apr-Jun 07 | Quarter 2 Jul-Sept 07 | Quarter 3 Oct-Dec 07 | Quarter 4 Jan-Mar 08 |
| --- | --- | --- | --- |
| A. Housing Needs Surveys | 6 Housing Needs Surveys with rural parishes. | 6 Housing Needs Surveys with rural parishes. |  |
| Housing Strategy & Conference |  | Ribble Valley and Pendle Affordable Housing strategy. | Ribble Valley and Pendle Affordable Housing Strategy & Conference. |
| B. Three Stream Waste Scheme |  | Delivery of wheeled bins & commencement of Phase 1 service. | Delivery of new vehicles. Delivery of wheeled bins & prepare to commence Phase 2. (end of April) |
| C. Targeting hotspots project. Work targeting youths at risk through sports & outdoor recreation. | Ongoing | Ongoing | Ongoing |
| Drugs education project in schools and on outreach | Project in abeyance in schools over summer holidays | Project continues on new timetable | Programme completed Evaluations |
| Salthill Sports Project Consultation period | Discussions with user groups, Clitheroe Cricket Cub and young people | Agreement signed with Cricket Club over youth usage. Scheme commences. | Evaluation of usage and crime levels |
| Crime Prevention Formation of Link 59 Business Link | Criminal damage to vehicles printed and distributed to households |  |  |
| RV on the Road – mobile facility shared with youth service, sexual health team & Connexions. | The service provides advice from a bus targeted to hotspots & in schools. |  |  |

Please complete Part 2 of the Programme Plan (the programme plan is unable to be considered in the absence of part 2).

| Local Area Agreement Outcomes |  |  | Part 2 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome Table: 2007/08 | Organisation: Ribble Valley BC |  |  |  |  |  |  |  |  |
| Project | Healthier Communities & Older People Outcomes | Sub Outcome | Measures/Performance Indicators (include mandatory indicators) | Baselines (Year) | Qtr 1 Apr-Jun | Qtr 2 Jul-Sep | Qtr 3 Oct-Dec | Qtr 4 Jan-Mar | Position 2007/08 |
| A. RHE Ribble Valley and Pendle | Better homes for Lancashire people | H20 - Affordable decent housing brought on stream | No. of Parish Housing Needs Surveys Completed (Local Measure) | 12 No. - GONW Funding Application |  | 6 | 6 |  | 12 |
|  |  | H20 - Affordable decent housing brought on stream | Development of Affordable Housing Strategies | 2 No. - GONW Funding Application |  |  |  | 2 | 2 |
|  | Safer Stronger Communities |  |  |  |  |  |  |  |  |
| B. 3 stream waste | To have cleaner, greener and safer public places | Communities are cleaner and greener | BVPI 82a (i) | 21.54% (2006/07) | - | - | - | - | 25% for 2007/08 |
| C. PSA 1 | To reduce crime |  | Reduce crime by 13.5% between 2005 and 2008. | See separate attachment (follows). |  |  |  |  |  |

###### Ribble Valley Community Safety Partnership Performance Monitoring Framework

11.	Declaration:

I confirm that this programme plan including Part 2 and all information supplied in connection with it is correct and accurate to the best of my knowledge and belief.  I confirm that I am duly authorised to sign the Programme Plan on behalf of the organisation.

Signature:

Print Name in full:               JEFFREY BRIAN FENTON

Position in Organisation: CORPORATE SERVICES MANAGER

Organisation Name: RIBBLE VALLEY BOROUGH COUNCIL

Date:	6th September 2007

Completed forms to be submitted to

Tahera Fazaeli

Funding Programme Manager

Lancashire County Council

Policy Unit 3rd Floor

Christ Church Precinct

PO Box 78

Preston

PR1 8XJ

Tel: 01772 533429

Fax: 01772 533353

Email: tahera.fazaeli@css.lancscc.gov.uk