Ribble Valley Borough Council

DOCUMENT 1

INVITATION TO TENDER FOR BRUNGERLEY PARK IMPROVEMENTS.

INSTRUCTIONS TO PERSONS TENDERING, CONDITIONS OF CONTRACT, SPECIFICATION, BILL OF QUANTITIES AND FORM OF TENDER

Engineering Section

Council Offices

Church Walk

CLITHEROE

Lancashire

BB7 2RA

Tel: 01200 425111

CONTENTS

PAGE NO

Important Notice	3

Summary Instructions and Details of Contract	4

Timetable	5

Background	6

Conditions of Tender	7

Instructions to Persons Tendering	30

Construction Industry Tax Deduction Scheme	31

Form of Tender	31

Appendix to Form of Tender – Part 1	33

Appendix to Form of Tender – Part 2	36

Certificate of Non-Collusion	37

Undertaking Statement	39

Pre Construction Health and Safety Information	40

Bankers Letter	47

Form of Agreement	48

Conditions of Contract	50

Special Conditions of Contract	52

List of Subcontractors	57

Special Requirements in Relation to Central Electricity Generating Board and Area Electricity Boards	….58

Special Requirements in Relation to Cadent Gas Ltd	59

Special Requirements in Relation to Openreach Ltd	61

Special Requirements in Relation to United Utilities, Yorkshire Water and the Environment Agency (EA)	62

Specification	63

List of Substitute, Additional or Cancelled Clauses	64

Bill of Quantities	71

Summary Sheet	75

IMPORTANT NOTICE

This Invitation to Tender (“ITT”) is issued to those wishing to tender (“Tenderers”) to Ribble Valley Borough Council (the “Council” and the “Client”) for the Brungerley Park Improvements project.

The contents of this ITT and of any other documentation sent to you in respect of this tender process, are provided on the basis that they remain the property of the Council and must be treated as confidential.  If you are unable or unwilling to comply with this requirement you are required to destroy this ITT and all associated documents immediately and not to retain any electronic or paper copies.

### No Tenderer will undertake any publicity activities with any part of the media in relation to the Contract or this ITT process without the prior written agreement of the Council, including agreement on the format and content of any publicity.

This ITT is made available in good faith.  No warranty is given as to the accuracy or completeness of the information contained in it and any liability or any inaccuracy or incompleteness is therefore expressly disclaimed by the Council and its advisers.

The Council reserves the right to cancel the tender process at any point. The Council is not liable for any costs resulting from any cancellation of this tender process nor for any other costs incurred by those tendering for this Contract.

You are deemed to understand fully the processes that the Council is required to follow under relevant European and UK legislation, particularly in relation to The Public Contracts Regulations 2015.

SUMMARY INSTRUCTIONS AND DETAILS OF CONTRACT

| ITEM | CONTRACT DETAILS |
| --- | --- |
| Contract Description: | ### Brungerley Park (E374,385 N443,259) is a country park on the Northerly edge of the town of Clitheroe. It is partially set in a former quarry and comprises a number of linear pathways at high and low levels running from Waddington Road (B6478) in a North-Easterly direction to West Bradford Road and vice-versa. The paths at the higher levels are generally set in a wooded area with a steep incline down towards the former quarry bottom and the River Ribble in places. The paths at the lower level are generally adjacent to the River Ribble, these paths are closed due to erosion and unsafe banking. This contract is concerned with improving the surfacing to the higher level paths and providing protective guard rail to prevent near-vertical falls into the former quarry bottom. |
| Insurance Requirements: | - Public Liability of £5 million - Employers Liability of £5 million |
| Procuring Officer: | Any queries must be submitted by email to procurement@ribblevalley.gov.uk by 5:00pm on Monday 25th November 2025 |
| Submission instructions: | ## 2 Paper Copies and a full version on CD or pen drive |
| Tenders to be sent to: | ## Head of Legal and Democratic Services, ## Council Offices, Church Walk, ## Clitheroe, ## Lancashire, ## BB7 2RA POSTAL ONLY Tenders submitted by facsimilie or electronic transmission will not be considered. |
| Date/time for Tender return: | No later than 2:00pm on Friday 6 December 2024 |
| Packaging: | Tenders must be submitted in a plain sealed envelope or package which shall bear the word “TENDER FOR BRUNGERLEY PARK IMPROVEMENTS” and shall not bear any name or mark indicating the sender. |

Timetable

This timetable is indicative only. The Council reserves the right to change it at its discretion.

| Stage | Date(s)/time |
| --- | --- |
| Deadline for Submission of Tenders | 2:00pm on Friday 6th December 2024 |
| Evaluation of Tenders | 9th December 2024– 13th December 2024 |
| Notification of result of evaluation | 13th December 2024 |
| Mandatory Standstill Period | 13th December 2024 – 27th December 2024 |
| Expected date of award of Contract(s) | 6th January 2025 |
| Contract commencement | To Be Agreed |
| Contract Completion | No later than 14th March 2025 |

CHECKLIST FOR TENDERERS

Failure to provide all of the items in the checklist may cause your Tender to be non-compliant and not be considered.

| No | Item | Included in Tender? |
| --- | --- | --- |
|  | Responses to Method Statements – Section 4 |  |
|  | All information requested, pages 9 - 26 |  |
|  | Form of Tender, pages 31 - 35 |  |
|  | Certificate of Non-Collusion and Non-Canvasing , pages 36 - 37 |  |
|  | Undertaking Statement, Page 38 |  |
|  | Bankers Letter, Page 47 |  |
|  | Form of Agreement, pages 48 - 49 |  |
|  | Bill of Quantities, Pages 71 - 76 |  |

- BACKGROUND

1.1	The Ribble Valley Sculpture Trail was launched in 1993. The first of its kind to be established in Lancashire, which now includes over 20 permanent works of art. The trail travels through Brungerley Park and Cross Hill Quarry, a local nature reserve managed by the Lancashire Wildlife trust, only a mile from Clitheroe town centre.

Selected artists have created unique artworks, working with local community groups, responding to the local environment and its rich heritage. Building a substantial body of work for visitors to enjoy.

The aim of the trail is to make art more accessible, by creating a free cultural activity it encourages people to enjoy the park, explore the outdoors and keep active whilst seeing the natural beauty of the area and its wildlife.

You pass through a variety of woodland and flower rich grassland. The old Cross Hill Quarry that last worked in the early 1900's is now a wildlife haven. You'll see dramatic views over the Forest of Bowland, an Area Of Outstanding Natural Beauty. The River Ribble contributes significantly to the pleasure of walking the trail, bringing its own wildlife including kingfishers, herons, salmon, sandpipers, otters, bats and many more species of animals and birds. You may even see deer.

  - If you have any questions or require any clarifications, please email the address shown below:

procurement@ribblevalley.gov.uk

  - Other than the person or persons identified above, no Council employee or member of the Council has the authority to give any information or make any representation (express or implied) in relation to this ITT or any other matter relating to the Contract.

  - Please note that the Council’s responses to any queries or clarification requests may, at the Council’s discretion, be published on the council’s website at:  www.ribblevalley.gov.uk/cpt

  - The Council reserves the right to issue supplementary documentation at any time during the tendering process to clarify any issue or amend any aspect of the ITT.  All such further documentation that may be issued shall be deemed to form part of the ITT and shall supplement and/or supersede any part of the ITT to the extent indicated.  Supplementary documentation will be published on the council’s website at:  www.ribblevalley.gov.uk/cpt

  - Tenderers must obtain for themselves at their own expense all information necessary for the preparation of their Tenders.

  - Under the Contract the Council will require compliance with its policies. Tenderers are advised to satisfy themselves that they understand all of the requirements of the Contract before submitting their Tender.

  - The Tender must be received in accordance with the relevant instructions no later than the time and date indicated.

# 2.	CONDITIONS OF TENDER

## 2.1	Tenders must be completed in the English language or a full English translation provided at no cost to the Council.

## 2.2	Only one Tender is permitted from each Tenderer. In the event that more than one is submitted by a Tenderer the one with the latest time of submission will be evaluated and the other(s) disregarded.

## 2.3	The Tender (including price) should remain valid for a minimum period of 90 days.

## 2.4	The Tender should not be qualified in any way.

## 2.5	Any signatures must be made by a person who is authorised to commit the Tenderer to the Contract.

## 2.6	Your full registered business/name and main office address must also be provided on all documents.

## 2.7	Abnormally Low Tenders

Where the pricing of a Tender is abnormally low the Council reserves the right to reject the Tender in accordance with the requirements for further investigation under The Public Contracts Regulations 2015.

# 3.	CONTRACT DOCUMENTS

## 3.1	Any resulting Contract will consist of the Contract Particulars and the Standard Terms (Conditions of Contract) and will be subject to English law.

## 3.2	The Council cannot enter into any negotiations on the Tender or Contract.

## 3.3	Any contract award will be conditional on the Contract being approved in accordance with the Council’s internal procedures and the Council being generally able to proceed and will allow the statutory standstill period of a minimum of 10 calendar days to elapse before sending confirmation of contract award to the successful Tenderer.

# 4.	TENDER EVALUATION AND AWARD CRITERIA

## 4.1	The Council does not undertake to accept the lowest or any Tender and reserves the right to accept the whole or any part of any Tender submitted.

## 4.2	Each Tender will be checked initially for compliance with all requirements of the ITT.

## 4.3	Tenders will be evaluated against the award criteria set out below.

## 4.4	During the evaluation period, the Council reserves the right to seek clarification in writing from the Tenderers, to assist it in its consideration of their Tenders.

## 4.5	The Council may decide to interview Tenderers, to assist its tendering process, and Tenderers will be notified in due course.

## 4.6	Tenders will be evaluated to determine the most economically advantageous tender taking into consideration the award criteria.

## 4.7	Tenders will be evaluated to determine the qualities of the tenderers.  Only bids that pass this selection criteria will be evaluated for economic advantage.  The criteria are:

- Grounds for Exclusion:  This section will be evaluated pass/fail basis.

- Insurance: This section will be evaluated pass/fail basis.

## We will seek evidence relating to the question. Justification to fail is not to provide the adequate insurance levels.

- Financial Information: This section will be evaluated pass/fail basis.

## Tenders will be evaluated for overall acceptability and sound financial condition to perform the estimated size of the contract. We will seek evidence relating to the questions, if required.

- Health and Safety: This section will be evaluated pass/fail basis.

- Environmental Issues:  This section will be evaluated pass/fail basis.

- Technical Capacity:  This section will be evaluated pass/fail basis.

- Equality and Diversity:  This section will be assessed and responses evaluated on a pass/fail basis.  Organisations must demonstrate they comply with equality in employment legislation. We will seek evidence relating to questions, if required.

- Modern Slavery Act 2015:  This section will be assessed and responses evaluated on a pass/fail basis.

## 4.8	Tenders will be evaluated to determine the most economically advantageous Tender with a weighting of 100% pricing.

## 4.9	Submissions will be evaluated by comparing costs across tender submissions. Submissions will be ranked in order of price.

## PRICING

    - Tenderers must base their tender upon the specifications within the tender documents, including the Bill of Quantities.

    - All Prices shall be stated in pounds sterling and exclusive of VAT.

    - Due to the admeasurable nature of the Contract it is essential that the unit rate for a measured item is submitted by the Tenderer. If any rates are omitted the tender will be void.

### 4.10.4	The Bill of Quantity rates must include all costs associated with each item.

- INFORMATION REQUIRED

5.1	Organisation Profile

Please provide the following details:

Business name (or Consortium Name):

Registered or trading name if different:

Type of organisation (e.g. private limited company, partnership, sole trader):

Registered address:

Correspondence address if different from the above:

Address from which the Contract will be provided if different from the above:

Name of ultimate holding/parent company or subsidiary companies including addresses and an explanation of group structure and internal relationships:

Company Registration Number of ultimate holding/parent company or subsidiary companies:

If you have included details of an ultimate holding/parent company above would this company be willing to guarantee your contract performance and enter into any requisite legal documentation?

Indication of the principal areas of business activity of your organisation:

| Contact name: |  |
| --- | --- |
| Contact's position: |  |
| Contact's telephone number: |  |
| Contact's fax number: |  |
| Contact’s email address: |  |
| Companies registration number(s): |  |
| Place of registration: |  |
| Year established: |  |
| VAT number: |  |

5.2	GROUNDS FOR EXCLUSION

This section will be evaluated on a pass/fail basis.

Please confirm that, to the best of your knowledge, the organisation named above is not in breach of the provisions of Regulation 57 of the Public Contracts Regulations 2015 as summarised below.

5.2.1.	Mandatory Grounds

The organisation (or its directors or any other person who has powers of representation, decision or control of such organisation) has not been convicted of any of the following offences:

| Conspiracy within the meaning of section 1 of the Criminal Law Act 1977 where that conspiracy relates to participation in a criminal organisation as defined in Article 2(1) of Council Joint Action 98/733/JHA;or | YES/NO (Delete as appropriate) |
| --- | --- |
| Corruption within the meaning of section 1 of the Public Bodies Corrupt Practices Act 1889 or section 1 of the Prevention of Corruption Act 1906; or | YES/NO (Delete as appropriate) |
| The offence of bribery; or | YES/NO (Delete as appropriate) |
| Fraud, where the offence relates to fraud affecting the financial interests of the European Communities as defined by Article 1 of the Convention relating to the protection of the financial interests of the European Union, within the meaning of:- - the offence of cheating the Revenue; or - the offence of conspiracy to defraud; or - fraud or theft within the meaning of the Theft Act 1968 and the Theft Act 1978; or - fraudulent trading within the meaning of section 458 of the Companies Act 1985; or - defrauding the Customs within the meaning of the Customs and Excise Management Act 1979 and the Value Added Tax Act 1994; or - an offence in connection with taxation in the European Community within the meaning of section 71 of the Criminal Justice Act 1993; or - destroying defacing or concealing of documents or procuring the extension of a valuable security within the meaning of section 20 of the Theft Act 1968; or | YES/NO (Delete as appropriate) |
| Money laundering within the meaning of the Money Laundering Regulations 2003; or | YES/NO (Delete as appropriate) |
| Any other offence within the meaning of Article 45(1) of the Public Sector Directive. | YES/NO (Delete as appropriate) |

If you are unable to confirm any of the above, please give details below, including any action taken to resolve the situation.

Please confirm the following statements or give details if you answer no to any of the questions.

5.2.2 	Discretionary Grounds

The organisation (or its directors or any other person who has powers of representation, decision or control of such organisation) confirms that:

| Being an individual he is not bankrupt or has not had a receiving order or administration order or bankruptcy restrictions order made against him or has not made any composition or arrangement with or for the benefit of his creditors or has not made any conveyance or assignment for the benefit of his creditors or does not appear able to pay or to have no reasonable prospect of being able to pay, a debt within the meaning of section 268 of the Insolvency Act 1986, or article 242 of the Insolvency (Northern Ireland) Order 1989, or in Scotland has not granted a trust deed for creditors or become otherwise apparently insolvent, or is not the subject of a petition presented for sequestration of his estate, or is not the subject of any similar procedure under the law of any other state; or | YES/NO (Delete as appropriate) |
| --- | --- |
| Being a partnership constituted under Scots law it has not granted a trust deed or become otherwise apparently insolvent, or is not the subject of a petition presented for sequestration of its estate; or | YES/NO (Delete as appropriate) |
| Being a company or any other entity within the meaning of section 255 of the Enterprise Act 2002 has not passed a resolution or is not the subject of an order by the court for the company’s winding up otherwise than for the purpose of bona fide reconstruction or amalgamation, or has not had a receiver, manager or administrator on behalf of a creditor appointed in respect of the company’s business or any part thereof or is not the subject of the above procedures or is not the subject of similar procedures under the law of any other state; or | YES/NO (Delete as appropriate) |
| They have not been convicted of a criminal offence relating to the conduct of the business or profession; or | YES/NO (Delete as appropriate) |
| They have not committed an act of grave misconduct in the course of the business or profession; or | YES/NO (Delete as appropriate) |
| It has fulfilled obligations relating to the payment of social security contributions under the law of any part of the United Kingdom or of the relevant State in which the organisation is established; or | YES/NO (Delete as appropriate) |
| It has fulfilled obligations relating to the payment of taxes under the law of any part of the United Kingdom or of the relevant State in which the economic operator is established; or | YES/NO (Delete as appropriate) |
| They are not guilty of serious misrepresentation in providing any information required of them under this regulation; or | YES/NO (Delete as appropriate) |
| In relation to procedures for the award of a public services contract, it is licensed in the relevant State in which he is established or is a member of an organisation in that relevant State when the law of that relevant State prohibits the provision of the services to be provided under the contract by a person who is not so licensed or who is not such a member; or | YES/NO (Delete as appropriate) |
| Where applicable, it is registered with the appropriate trade or professional register(s) in the EU Member State where it is established (as set out in Annex IXB of Directive 2004/18/EC) under the conditions laid down by that Member State. | YES/NO (Delete as appropriate) |

If you are unable to confirm any of the above, please give details below, including any action taken to resolve the situation.

5.2.3 	Insurance

This section will be evaluated on a pass/fail basis.

Please provide confirmation that you have or, if successful, will buy the following minimum levels of insurance:

|  | Confirmed |
| --- | --- |
| Public liability £10 million | YES/NO |
| Employers liability £10 million | YES/NO |
| Professional Indemnity £2 million | YES/NO |

The successful tenderer will be required to provide the Council with proof of insurance cover prior to commencement of the contract.

5.2.4 	Financial Information

This section will be evaluated on a pass/fail basis.

We may seek evidence relating to the questions below, if required and we reserve the right to use the services of an independent third party to assess your financial standing/appraisal

What was your turnover in the last two years (if this applies)?

| £ ……..……… for year ended __ / __ / ____ | £ ……..……… for year ended __ / __ / ____ |
| --- | --- |

Has your organisation met the terms of its banking facilities and loan agreements (if any) during the past year?

YES/NO (delete as appropriate)

If the answer to the above question is no, what were the reasons, and what has been done to put things right?

Has your organisation met all its obligations to pay its creditors and employees during the past year?

YES/NO (delete as appropriate)

If the answer to the above question is no, please explain why not:

Have you completed the draft Bankers Letter attached as Schedule 7?

YES/NO (delete as appropriate)

What is the name and branch of your bankers who could provide a reference?

| Name |  |
| --- | --- |
| Branch |  |
| Contact Details |  |

The following must be provided:

A copy of your most recent accounts, audited if applicable (for the last two years if this applies).  If not applicable please provide an Accountant’s Reference instead

| Please tick the box to confirm the above documents are enclosed: |  |
| --- | --- |

The following may be requested:

Income and Expenditure Statement, Balance Sheet and Cash Flow Forecast for the current year and a bank letter outlining the current cash and credit position

| Please confirm you could provide documents if requested: | Yes | No |
| --- | --- | --- |

NOTES TO ORGANISATION: - Where the organisation is a subsidiary of a group all questions must be answered for both the subsidiary and the ultimate parent. - Where this Tender is being submitted as a consortium, the above information is required for each member organisation

5.2.5 Health and Safety

This section will be evaluated on a pass/fail basis.

Responsibility and Structure

Please state the name and position of the person with overall responsibility for health and safety in your organisation together with details of experience and any relevant qualifications.

| Name |  |
| --- | --- |
| Position in Organisation |  |
| Experience |  |
| Qualifications |  |

Please state the name and position of the person (if different to above) appointed to provide health and safety advice as required by Regulation 7 of the Management of Health & Safety Work Regulations 1999, together with details of experience and any relevant qualifications.

| Name |  |
| --- | --- |
| Position in Organisation |  |
| Experience |  |
| Qualifications |  |

How many persons does your organisation normally employ?

Does your organisation (not individuals within it) have current membership of any trade associations, safety organisations, registration with or accreditation by any accrediting bodies, for example CHAS or equivalent?

YES/NO (delete as appropriate)

If the answer is yes, provide details, using full names of associations, bodies and any applicable registration number.  Please do not use abbreviations.

NOTES TO ORGANISATION: - Organisations are informed that the Council operates a policy that an organisation will pass the Council’s Health and Safety requirements on the basis that they participate in the relevant contractor Health & Safety Assessment Scheme (CHAS) “Scheme” - Organisations will therefore not have to complete the remainder of the Health and Safety section of this tender, if they participate in the Scheme. Organisations who do not participate in the Scheme are required to complete the remainder of the Health and Safety section.

Policies and Procedures

Does your organisation have a written Health and Safety Policy (covering General Policy, Organisation and Arrangements) as required by Section 2(3) of the Health and Safety at Work etc Act 1974 and issue any codes of safe working practices to workforce?

YES/NO (delete as appropriate)

If the answer is yes please enclose a copy of the policy.

If your organisation does not have a written Health and Safety Policy please give the reason why.

Please state how health and safety policies and procedures are communicated to your workforce and administered within your organisation?

Does your organisation have a procedure for the reporting and recording of accidents and dangerous occurrences in accordance with RIDDOR?

YES/NO (delete as appropriate)

Have you enclosed a copy of your procedure for accident reporting, recording and investigation?

YES/NO (delete as appropriate)

Please complete the following table in respect of accidents and dangerous occurrences as set out below.

| Year | Fatal | Major Injury or “Over 3-Day” | Non-Reportable | Dangerous Occurrences | Reportable ill-health | Near Misses |
| --- | --- | --- | --- | --- | --- | --- |
| This year |  |  |  |  |  |  |
| Last year |  |  |  |  |  |  |
| Year before last |  |  |  |  |  |  |

During the last five years, has the organisation been subject to formal enforcement (e.g. Prosecution, Prohibition Notice or Improvement Notice) for contravention of the Health and Safety at Work etc Act 1974, or equivalent legislation arising from your conduct of activities similar to those covered by this contract?

YES/NO (delete as appropriate)

If the answer is yes, please provide full details and explain corrective action taken to prevent re-occurrence.

Does your organisation have Risk Assessment Procedures in place for all work activities as required by the Management of Health and Safety at Work Regulations 1999 and associated legislation?

YES/NO (delete as appropriate)

If the answer is yes, please supply 2 examples of risk assessments and safety method statements for work activity undertaken within the last 12 months relevant to the works included in this contract

| Copy of above enclosed if appropriate | Yes | No |
| --- | --- | --- |

Does your organisation have a health and safety training programme for your workforce to ensure that they are competent for their duties?

YES/NO (delete as appropriate)

If the answer is yes, please enclose brief details of training courses or programmes undertaken by managers and workforce.

Does your organisation have arrangements in place for consultation with workforce on health and safety matters?

YES/NO (delete as appropriate)

Where appropriate, does your organisation undertake health monitoring of workforce?

YES/NO (delete as appropriate)

If the answer is yes, please provide details.

If your organisation uses sub-contractors, do you have a system in place for assessing their competence and the ongoing monitoring and review of their Health and Safety performance?

YES/NO (delete as appropriate)

If the answer is yes, please provide details.

Do you have a system in place for monitoring your Health and Safety arrangements including auditing them at periodic intervals and for reviewing them on an ongoing basis?

YES/NO (delete as appropriate)

If the answer is yes, please provide details including examples.

| Name of Person completing this form |  |
| --- | --- |
| Position in Organisation |  |
| Contact Tel No |  |
| Email Address |  |
| Date |  |
| Signature |  |

5.2.6	ENVIRONMENTAL ISSUES

This section will be evaluated on a pass/fail basis.

| Environmental |  |
| --- | --- |
| The Council is committed to the protection of the environment and the promotion of sustainable environmental development. Tenderers should note the various obligations contained within the Contract which will ensure that the successful Tenderer will provide the Contract in a non-detrimental manner to the environment. |  |
| Would you be willing to work with the Council regarding any environmental issues the Council considers relevant, comply with contractual obligations and carry out any reasonable requests to ensure the protection of the environment and promotion of sustainable development throughout the Contract Period. | Yes / No |

5.2.7	TECHNICAL CAPACITY

This section will be evaluated on a pass/fail basis.

| Technical Capacity |  |
| --- | --- |
| ### The Organisation must demonstrate that they have the technical capacity to carry out this project and we will seek evidence relating to the questions below, if required. |  |
| The Principal Contractor has to be certified to National Highways Sector Scheme 30 (NHSS 30) | Yes / No |
| All electrical work will be carried out by a NICEIC registered contractor | Yes / No |

5.2.8 	EQUALITY AND DIVERSITY

This section will be evaluated on a pass/fail basis.

### The Organisation must demonstrate they comply with equality in employment legislation and we will seek evidence relating to the questions below, if required.

### The Council is committed to: Providing its services in a way that promotes equality of opportunity at every possibility.  It is expected that the successful Tenderer will be equally committed to equality and diversity in its employment practices and service provision, and will ensure compliance with all anti-discrimination legislation.

#### Expectation of the Tenderer: Tenderers should note that the successful Tenderer will be asked to contract with the Council to ensure that they adhere to these obligations.  The Council will, if appropriate, monitor the successful Tenderer’s compliance throughout the Contract Period.

#### Compliance with Equality Legislation: The Council requires service providers to demonstrate that they comply with equality in employment legislation.  The levels of compliance become more demanding depending on the number of employees employed by the organisation.  Organisations employing less than 5 employees face minimum requirements, whilst organisations employing 50 or more employees need to meet more comprehensive criteria.  During the Contract Period the Council may work with contractors, who at present do not fully comply, to help them put in place policies and practices to do so.

#### LEVEL 1 (LESS THAN 5 EMPLOYEES)

#### Organisations with fewer than 5 directly employed persons will be expected to meet the appropriate level of compliance for the delivery of the Contract.  Should recruitment increase the size of the organisation to 5 or more employees the organisation will be expected to meet the appropriate level of compliance.

#### LEVEL 2 (5 TO 49 EMPLOYEES)

#### All organisations with between 5 and 49 employees must achieve criteria 1 – 4 listed below.

- All organisations must have an equality policy in respect of race, gender, disability, age, sexual orientation and religion/belief that covers at least:

- Recruitment, selection, training, promotion, discipline, grievance and d	dismissal.

- Discrimination, harassment, and victimisation, making it clear that these are disciplinary offences within the firm.

- Identification of the senior position with responsibility for the policy and its effective implementation.

- How you communicate the policy to your employees.

- Effective implementation of the policy in the organisation’s recruitment practices, to include open recruitment methods such as the use of job centres, careers service or press advertisements.

- The policy should either be reviewed to reflect changes in legislation or within a three-year period whichever occurs first.

- To monitor the gender, disability and ethnicity of job applicants.  We would also encourage organisations to monitor in respect of age, sexual orientation and religion/belief.

#### LEVEL 3 (50 OR MORE EMPLOYEES)

#### All organisations with 50 or more employees must achieve criteria 1-4 in level 2 and the additional criteria 5-10 listed below:

- Provide written instructions to managers and supervisors on equality in recruitment, selection, training, promotion, discipline, grievance and dismissal of employees.

- Provide equality training for managers and any employees responsible for recruitment and selection.

- In addition to criterion 4 (Level 2) carry out monitoring on the number of employees from different gender, disability and ethnic groups by grade when:

- in post

- applying for posts

- taking up training and development opportunities

- promoted

- transferred

- disciplined and dismissed

- a grievance is raised

- leaving employment

#### The Council would also encourage organisations to monitor in respect of age, sexual orientation and religion/belief.

- If the above monitoring reveals inequalities, organisations will be expected to take steps to address imbalances.

- In respect of 7 and 8 above, annual monitoring and reporting is required regarding equality issues within the workforce.

- Organisation’s recruitment advertisements and publicity literature should state that equal opportunities practices are in place.

Does your organisation comply with its legal obligations relating to the following?

| Race | YES/NO (delete as appropriate) |
| --- | --- |
| Sexual Orientation | YES/NO (delete as appropriate) |
| Disability | YES/NO (delete as appropriate) |
| Age | YES/NO (delete as appropriate) |
| Religion or Belief | YES/NO (delete as appropriate) |
| Gender | YES/NO (delete as appropriate) |
| Human Rights | YES/NO (delete as appropriate) |
| NOTE TO ORGANISATION: You must keep up to date with relevant changes in legislation. |  |

In the last three years has any finding of unlawful discrimination been made against your organisation by any court or industrial or employment tribunal?

YES/NO (delete as appropriate)

In the last three years has your organisation been the subject of a formal investigation on grounds of alleged unlawful discrimination by, for example, the Commission for Racial Equality (CRE), Disability Rights Commission (DRC), Equal Opportunities Commission (EOC) or Equality and Human Rights Commission (EHRC)?

YES/NO (delete as appropriate)

If the outcome of either of the last two questions (above) was yes, what actions were you required to take as a result of that finding or investigation?

If you were required to take action, what action did you take?

If you were required to take action and no action was taken, please explain why not?

If you were required to take action, did the action taken satisfy the relevant organisation?

YES/NO (delete as appropriate)

5.2.9	MODERN SLAVERY ACT 2015

| Are you a relevant commercial organisation as defined by section 54 ("Transparency in supply chains etc.") of the Modern Slavery Act 2015 ("the Act")? | YES/NO |
| --- | --- |
| If you have answered yes to the question above, are you compliant with the annual reporting requirements contained within Section 54 of the Act 2015? | YES - Please provide the relevant web address to view the statement NO - Please provide an explanation |

## 6.	CORPORATE REQUIREMENTS

## 6.1	The Council has a statutory requirement to ensure compliance with a number of corporate considerations when providing its services.  The Council is delivering its services when a contractor is delivering services on behalf of the Council.  It is therefore incumbent upon the Council to ensure that these statutory requirements are carried out by any contractor that is working for the Council.  Consequently, the Council is looking for a commitment within Tenders to assisting the Council in these duties.  The Council does not consider that these requirements will be onerous and so pricing should not be affected in complying with any of these obligations but if a Tenderer believes there is a pricing impact, the impact of complying with these obligations should be clearly identified in their Pricing Schedule.

# 7.0	CLARIFICATION MEETINGS, SITE VISITS AND INTERVIEWS

7.1	The Council reserves the right to hold clarification meetings, site visits and interviews as it considers appropriate both before and after Tender submission.  Responses to any questions you submit may, at the Council’s discretion be circulated to all Tenderers.

## 7.2	Tenderers are only permitted access to the site by pre-arranged appointments with the Council.  Representatives of the Council must accompany Tenderers when they visit and inspect the site.

## 7.3	Tenderers will additionally be able to meet with the Council to discuss their approach to the requirements.  Any issues raised at the meeting which are not commercially confidential will be shared with the other Tenderers.

# 8.0	FREEDOM OF INFORMATION ACT AND ENVIRONMENTAL INFORMATION STATEMENT

  - The Council is subject to The Freedom of Information Act 2000 (“Act”) and The Environmental Information Regulations 2004 (“EIR”).

  - As part of the Council’s obligations under the Act or EIR, it may be required to disclose information concerning the procurement process or the Contract to anyone who makes a reasonable request.

  - If Tenderers consider that any of the information provided in their Tender is commercially sensitive (meaning it could reasonably cause prejudice to the organisation if disclosed to a third party) then it should be clearly marked as "Not for disclosure to third parties” together with valid reasons in support of the information being exempt from disclosure under the Act and the EIR.

  - The Council will endeavour to consult with Tenderers and have regard to comments and any objections before it releases any information to a third party under the Act or the EIR.  However the Council shall be entitled to determine in its absolute discretion whether any information is exempt from the Act and/or the EIR, or is to be disclosed in response to a request of information.  The Council must make its decision on disclosure in accordance with the provisions of the Act or the EIR and can only withhold information if it is covered by an exemption from disclosure under the Act or the EIR.

  - The Council will not be held liable for any loss or prejudice caused by the disclosure of information that:

- has not been clearly marked as "Not for disclosure to third parties" with supporting reasons (referring to the relevant category of exemption under the Act or EIR where possible); or

- does not fall into a category of information that is exempt from disclosure under the Act or EIR (for example, a trade secret or would be likely to prejudice the commercial interests of any person); or

- in cases where there is no absolute statutory duty to withhold information, then notwithstanding the previous clauses, in circumstances where it is in the public interest to disclose any such information.

### 9.0	HEALTH AND SAFETY

### 9.1	The Council is fully committed to meeting its responsibilities under the Health and Safety at Work etc. Act 1974, the Management of Health and Safety at Work Regulations 1999 and associated protective legislation. The Council requires any contractor delivering works, goods or services on behalf of the Council to support it in meeting its health and safety responsibilities. To this end the Contractor should familiarise themselves with the Council’s “Health and Safety Policy – General Statement of Intent” included with these Invitation to Tender documents.

# INSTRUCTIONS TO PERSONS TENDERING

1.	These instructions are issued for the guidance of tenderers and will not form part of the contract. Failure to comply with these instructions may result in the rejection of a tender.

2.	Tenderers are advised to examine the drawings, Conditions of Contract, Specification and Bill of Quantities and also to inspect the site of the works. If larger sized drawings are required by the tenderer, then a request should be made to the Engineer who will be able to make these available for collection only. The whole of these documents should be read and their true intent and meaning ascertained before the Bill of Quantities is priced. Any apparent ambiguities, errors or omissions in the tender documents should be notified to the engineer without delay.

3.	No unauthorised alteration or addition is to be made to the Form of Tender, drawings, Conditions of Contract, Specification or Bill of Quantities and qualified tenders may be rejected.

4.	Should any alterations or additions to the documents as issued to the tenderers be deemed necessary prior to the date for submission of the tenders, these will be issued to all tenderers in the form of supplementary or amendment sheets and tenderers will be required to acknowledge receipt of any such supplementary or amendment sheet.

5.	Tenderers should submit offers for the whole of the works only.

6.	Tenderers will treat the tender document and all details contained therein as private and confidential.

7.	One copy of the Bill of Quantities, fully priced and accompanied by copies of the Conditions of Contract, Specification and any other required particulars including Pre-Construction Phase Plan with required Method Statements, shall be submitted with the completed Form of Tender and Appendix to Ribble Valley Borough Council no later than 2:00pm on Friday 6th December 2024

8.	Where examination of a tender reveals errors or discrepancies which would affect the tender total in an otherwise successful tender, the tenderer will be given details of such errors and discrepancies and afforded an opportunity to confirm or withdraw his offer. If the tenderer withdraws his offer, the next tenderer in competitive order will be examined and dealt with in the same way.

9.	All quantities in this Bill are provisional and claims will not be considered for any variations in these amounts.

## BOROUGH OF RIBBLE VALLEY

## FINANCE (NO 2) ACT 1975

# CONSTRUCTION INDUSTRY TAX DEDUCTION SCHEME

In connection with the provisions of the above-mentioned Act, the following information is required:

I/We are in possession of a tax exemption certificate

Classified:	* I
	* P
	* C

*	I/We are not at present in possession of a relevant tax exemption certificate.

*	I/We understand that the Borough of Ribble Valley has previously been appraised of the current position regarding my/our tax certification.

*	Delete as applicable.

I/We undertake to furnish the Borough of Ribble Valley with the necessary evidence of certification at any time on request.

Signed:

On behalf of:

SHORT DESCRIPTION OF WORKS

### Brungerley Park is a country park on the Northerly edge of the town of Clitheroe. It is partially set in a former quarry and comprises a number of linear pathways at high and low levels running from Waddington Road (B6478) in a North-Easterly direction to West Bradford Road and vice-versa. The paths at the higher levels are generally set in a wooded area with a steep incline down towards the former quarry bottom and the River Ribble in places. The paths at the lower level are generally adjacent to the River Ribble, these paths are closed due to erosion and unsafe banking. This contract is concerned with improving the surfacing to the higher level paths and providing protective guard rail to prevent near-vertical falls into the former quarry bottom.

# Form of Tender

## (NOTE: The Appendix forms part of the Form of Tender)

To: Ribble Valley Borough Council

Having examined the drawings, Conditions of Contract, Specification and Bill of Quantities for the construction of the above-mentioned works (and the matters set out in the Appendix hereto), we offer to construct and complete the whole of the said works and maintain the permanent works in conformity with the said drawings, Conditions of Contract, Specification and Bill of Quantities for such sum as may be ascertained in accordance with the said Conditions of Contract.

To comparing tenders, our tender total is:

Amount in words: Click here to enter text.

We undertake to complete and deliver the whole of the permanent works comprised in the contract within the time stated in the Appendix hereto.

If our tender is accepted we will, if required, provide security for the due performance of the contract as stipulated in the Conditions of Contract and the Appendix hereto.

Unless and until a formal agreement is prepared and executed this tender together with your written acceptance thereof shall constitute a binding contract between us.

We understand that you are not bound to accept the lowest or any tender you may receive.

Yours faithfully,

Signature:

Company:

Address:

Date:

# FORM OF TENDER (APPENDIX)

## (NOTE: Relevant clause numbers are shown in brackets)

## Appendix – Part 1 (to be completed prior to the invitation to tender)

1.	Name of the Employer (Clause 1(1)(a)): The Borough Council of Ribble Valley

Address: Council Offices, Church Walk, Clitheroe, Lancashire, BB7 2RA

2.	Name of the Engineer (Clause 1(1)(c)): Winston Robinson

Address: Council Offices, Church Walk, Clitheroe, Lancashire, BB7 2RA

3.	Defects Correction Period (Clause 1(1)(s)): 52 weeks

4.	Parts or Sections of the Works which shall not be sub-contracted without the Engineer’s prior written approval (Clause 4(2))

5.	Number and type of copies of Drawings to be provided (Clause 6(1)(b)): None, included in Bill (see 6(1)(a))

6.	Form of Agreement (Clause 9): Required

If required, Signed/Sealed

7.	Performance Bond (Clause 10(1)): Not Required

Amount of Bond (if required) to be: n/a

8.	Minimum amount of third party insurance (persons and property) (Clause 23(3): £10,000,000 (each and every occurrence)

9.	Works Commencement Date (if known) (Clause 41(1)(a)): TBA

10.	Time for Completion (Clause 43)a

for the whole of the works:	10 weeks.

OR for sections of the works (Clause 1(1)(u)b:

Section A		_n/a__ weeks

Section B		  _ n/a __ weeks

Section C		__ n/a _ weeks

Section D		__ n/a _ weeks

the remainder of the works:	__ n/a _weeks

11.	Liquidated damages for delay (Clause 47)

per day/week	limit of liability

| EITHER for the whole of the works: | £0 |  | £0 |
| --- | --- | --- | --- |
| OR for Section A (as above): | £ n/a |  | £ n/a |
| Section B (as above): | £ n/a |  | £ n/a |
| Section C (as above): | £ n/a |  | £ n/a |
| Section D (as above): | £ n/a |  | £ n/a |
| the remainder of the works (as above): | £ n/a |  | £ n/a |

12.	Vesting of materials not on site (Clauses 54(1) and 60(1)(c)) (if required by the employer)d:

1.		4.

2.		5.

3.		6.

13.	Method of Measurement adopted in preparation of Bill of Quantities Civil Engineering Standard Method of Measurement (CESMM 3)

14.	Percentage of the value of goods and materials to be included in interim certificates (Clause 60(2)(b)): 80%

15.	Minimum amount of interim certificates (Clause 60(3)): £50,000

16.	Rate of retention (recommended not to exceed 5%) (Clause 60(5)): 5%

17.	Limit of retention (% of Tender Total) (Clause 60(5)) (recommended not to exceed 3%): 3%

18.	Bank whose Base Lending Rate is to be used (Clause 60(7)): Barclays Bank PLC

19.	Requirement for prior approval by the employer before the Engineer can act. DETAILS TO BE GIVEN AND CLAUSE NUMBER STATED (Clause 2(1)(b))f

20.	Name of the Principal Designer (if required in accordance with the Construction (Design and Management) Regulations 2015))

Winston Robinson

Council Offices, Church Walk, Clitheroe, Lancashire, BB7 2RA

21.	Name of the Principal Contractor (in accordance with the Construction (Design and Management) Regulations 2015))

Address

22.	The arbitration procedure to be used if (Clause 66C(2)(a))

(a)	The Institution of Civil Engineers’ Arbitration Procedure 1997g or

(b)	The Construction Industry Model Arbitration Rulesg

If no deletion is made, the Institution of Civil Engineers’ Arbitration Procedure 1997 shall be used.

a	If not stated is to be completed by Contractor in Part 2 of the Appendix.

b	To be completed if required, with brief description. Where Sectional completion applies the item for “the Remainder of the Works” must be used to cover the balance of the Works if the Sections described do not in total comprise the whole of the Works.

c	Delete where not required.

d	(If used) Materials to which the Clauses apply must be listed in Part I (Employer’s option) or Part 2 (Contractor’s option).

e	Insert here any amendment or modification adopted if different from that stated in Clause 57.

f	If there is any requirement that the Engineer has to obtain prior approval from the Employer before he can act full particulars of such requirements must be set out above.

g	Delete one as appropriate.

# Appendix – Part 2

## (To be completed by Contractor)

1.	Insurance policy excesses (Clause 25(2)):

Insurance of the Works (Clause 21(1)): £

Third party (property damage) (Clause 23(1)): £

2.	Time for Completion (Clause 43) (if not completed in Part 1 of the Appendix)

EITHER for the whole of the Works:	10 weeks

OR for Sections of the Works (Clause 1(1)(u) (as detailed in Part 1 of the Appendix)

Section A	N/A weeks

Section B	N/A weeks

Section C	N/A weeks

Section D	N/A weeks

the Remainder of the Works	N/A weeks

3.	Vesting of materials not on site (Clauses 54(1) and 60(10(c) (at the option of the contractor – seed in Part 1):

1.		4.

2.		5.

3.		6.

4.	Percentage(s) for adjustment of PC sums (Clauses 59(2)(c) and 59(5)(c) (with details if required):

Ribble Valley Borough Council

Brungerley Park Improvements

CERTIFICATE OF NON-COLLUSION AND NON-CANVASSING

To:	Ribble Valley Borough Council

Council Offices

Church Walk

Clitheroe

Lancashire

BB7 2RA

Date:

For the Attention of: Head of Legal and Democratic Services

Statement of non-canvassing

I/we hereby certify that I/we have not canvassed any member, Director, employee, representative or adviser of the Council in connection with the proposed award of the Contract by the Council, and that no person employed by me/us or acting on my/our behalf, or advising me/us, has done any such act.

I/we further hereby undertake that I/we will not canvass any member, Director, employee, representative or adviser of the Council in connection with the award of the Contract and that no person employed by me/us or acting on my/our behalf, or advising me/us, will do any such act.

Statement of non-collusion

The essence of selective tendering for the Contract is that the Council shall receive bona fide competitive Tenders from all Tenderers.

In recognition of this principle, I/we certify that this is a bona fide offer, intended to be competitive and that I/we have not fixed or adjusted the amount of the offer in accordance with any agreement or arrangement with any other person (except any sub-contractor identified in this offer).

I/we also certify that I/we have not done, and undertake that I/we will not do, at any time any of the following acts:

- communicate to a person other than the Council, the amount or approximate amount of my/our proposed offer except where the disclosure in confidence of the approximate value of the Tender was essential to obtain insurance premium quotations required for the preparation of the Tender; or

- enter into any agreement or agreements with any other person that they shall refrain from tendering or as to the amount of any offer submitted by them; or

- offer or agree to pay or give or actually pay or give any sum of money, inducement or valuable consideration, directly or indirectly, to any person for doing or having done or having caused to be done in relation to any other offer or proposed offer, any act or omission.

I/we agree that the Council may, in its consideration of the offer and in any subsequent actions, rely upon the statements made in this Certificate.

Signed:	……………..........................

Name:   …………………………………………..

Position:	……………..........................

For and on behalf of [Tenderer]

..................................................

Ribble Valley Borough Council

Brungerley Park Improvements

UNDERTAKING STATEMENT

Before submitting the tender document, please ensure that:

# You have answered all the questions;

# You have enclosed all documents requested;

# You have read and signed the undertaking below.

I certify that the information supplied regarding the Applicant is accurate to the best of my knowledge and that I accept the conditions and undertakings requested in the questionnaire.  I understand and accept that false information could result in rejection of the tender.

I also understand that it is a criminal offence, punishable by imprisonment, to give or offer any gift or consideration whatsoever as an inducement or reward to any servant of a public body.  I also understand that any such action will result in rejection of our tender and empower the Council to cancel any contract currently in force.

I understand and agree that if our tender is successful that the Applicant will purchase professional indemnity insurance as required if such insurance is not already held.

I understand and agree to the conditions set out in the Freedom of Information and Environmental Information Statement.

NB This undertaking is to be signed by a Partner, Director or authorised representative i.e. in their name on behalf of the Applicant.

Signed for and on behalf of the Applicant:

Signed:

Position/Status in the Applicant:

Applicant’s name:

Applicant’s address:

Date:

Ribble Valley Borough Council

Brungerley Park Improvements

PRE-CONSTRUCTION HEALTH AND SAFETY INFORMATION

CDM  2015

Project Title: - Brungerley Park Improvements

| SECTION 1. | ## DESCRIPTION OF PROJECT |  |  |
| --- | --- | --- | --- |
| - Project Description and Nature of works (include timescale) | The works include taking provision and installation of ‘key-clamp’ guard rail and the reinstatement of pathways in bitumen macadam. |  |  |
| Locations | Brungerley Park (E374,385 N443,259) is a country park on the Northerly edge of the town of Clitheroe. It is partially set in a former quarry and comprises a number of linear pathways at high and low levels running from Waddington Road (B6478), 63.0m AOD, in a North-Easterly direction to West Bradford Road, 90.0m AOD, and vice-versa. |  |  |
| Programme details including commencement and duration. | It is expected that works on-site will begin early January 2025 for ten weeks until the middle of March 2025. |  |  |
| Client | Ribble Valley Borough Council Council Offices Church Walk Clitheroe BB7 2RA Tel: 01200 425111 |  |  |
| Principal Designer | Ribble Valley Borough Council Council Offices Church Walk Clitheroe BB7 2RA Tel: 01200 425111 |  |  |
| Existing records | Utility records have been checked online and included under separate cover. |  |  |
| Surveys undertaken | Topographical Survey and Drainage survey has been undertaken by RVBC staff. |  |  |
| HSE F10(rev) Notification sent | The works are non-notifiable under the CDM Regulations 2015. |  |  |
| HSE Area Office | HSE, Redgrave Court, Merton Road Bootle, Merseyside, L20 7HS Tel: 0345 300 9923 |  |  |
| Contact | (name) (tel. no) Winston Robinson 01200 414495 |  |  |
| This Pre-construction information has been supplied for the determination of resources necessary to meet the health and safety requirements for the pre- construction phase of the above project, and shall not be used as the Construction Phase Health and Safety Plan |  |  |  |
| Signed: |  | Client: | Date: |
| ## SECTION 2 |  | ### CLIENT’S CONSIDERATIONS AND MANAGEMENT REQUIREMENTS |  |
| Structure and organisation |  | All persons working on site must be competent to carry out the duties requested of them. Any person placed in charge of the site will be conversant with all of the Principal Contractor’s duties under the CDM2015. HSE expect all site managers on CDM projects to have undergone the CITB 5-day Site Managers Safety Training Scheme or equivalent to be able to demonstrate competence. The Principal Contractor must be satisfied that all sub-contractors are competent prior to offering appointments. Sub-contractors must undergo a form of health and safety competence assessment relevant to the duties they are asked to perform. Contractors will be required to confirm that health and safety standards on site will be controlled and that welfare facilities will be provided, in accordance with schedule 2 of the CDM2015 Regulations, prior to commencement on site. Formerly known as the Construction Health Safety and Welfare Regulations 1996. The Principal Contractor will be required to provide relevant information to the Client to be included within Health & Safety file for the building. The site layout, size, parking and access/egress points, restricts vehicle access. There are parking/turning restrictions at the sites. The contractor must review the site plan and assess the movement of site transport. The construction phase plan must include the proposal for traffic management and deliveries to consider the heavy foot and vehicle traffic immediately outside the site. There is a public, off-street car park to the East of the site and a limited number of on-street parking spaces available close to site. |  |
| Safety Goals |  | The following health and safety goals are required on this project: Monitoring of accidents and near misses with a goal of zero major accidents and zero near misses. Minimise risk, disruption or inconvenience to park users, amenities, flora and fauna, wildlife. |  |
| Permits and authorisation |  | The Principal Contractor must agree procedures for the control of visitors to site. Such procedures will include site inductions and the signing in and out of visitors to the site and arrangements for accompanying them at all times. |  |
| Emergency procedures |  | First aid –The Principal Contractor must identify those with first aid responsibilities. The nearest accident and emergency hospital is Blackburn A&E. Fire – The principal contractor must arrange fire prevention and fire-fighting equipment. This should include regular liaison regarding any temporary obstructions to means of escape, fire doors, alarms etc. And coordination with the Clients activities. The principal contractor is to report any incidents to Ribble Valley Borough Council representative in addition to the statutory authorities under The Reporting of Injuries, Diseases and Dangerous Occurrences Regulations 1995 (RIDDOR) as they require the 'responsible person' to notify any death, reportable injury, disease or dangerous occurrence, to the relevant enforcing authority. |  |
| Site rules |  | The following arrangements are required on this project: No radios are permitted or any behaviour inappropriate to areas accessed by members of the public. Regular report on progress to be provided to client to including details of incidents and near misses. The Principal Contractor to have a continuous presence on site. No headphones to be used on site. All equipment brought to site must be fit for purpose and where necessary. Inspected and tested in accordance with relevant legislation. Electrical supply for tools and equipment must not be in excess of 110 Volts and should have an RCD protection. Ensure all who are likely to work on site (inc. subcontractors) are aware of the rules before they go on site. Ensure the Client is aware of any changes that may be required before the changes take place. No smoking onsite or abusive / foul language on any area of the site at any time. Operatives must be ‘Competent’ to carry out work for which have been engaged. Know the emergency procedure rules. Keep work areas tidy, consider others working in that area and keep them informed where necessary. Appropriate PPE/relevant procedures to be worn / followed at all times. |  |
| Liaison arrangements between parties |  | Regular meetings to be held between the Client and the Principal Contractor to discuss progress, financials, health and safety and any other issues that could affect the contract. The Client to agree a series of meetings with the Principal Contractor before work proceeds on-site. |  |
| Security arrangements |  | The works are external in nature and at ground floor level. The site compound is to be enclosed with appropriate fencing/barriers to prevent unauthorised access. Materials, tools and substances should not be stored on the public thorough fare when not in use, they should be contained securely within the site compound. The Principal Contractor must ensure that a banksman is provided to assist reversing vehicles. |  |
| SECTION 3 |  | ENVIRONMENTAL RESTRICTIONS AND EXISTING ON-SITE RISKS |  |
| Boundaries and access |  | The Site Compound is to be situated close to the working site at an approved location. |  |
| Adjacent land uses |  | The majority of the surrounding land is urban, predominantly housing, with limited on-street and off-street car parking. |  |
| Existing storage of hazardous materials |  | N/A |  |
| Location of existing services |  | To be provided under separate cover. |  |
| Welfare Facilities |  | Sufficient space for toilet and welfare facilities should be made available in the designated site compound area. The contractor will be responsible for ensuring that the facilities meet the requirements of the CDM Regulations 2015. The Construction Phase Plan should include how the Principal Contractor will meet the requirements for site welfare, i.e. wash facilities, drying facilities, drinking water, toilets and rest facilities. Suitable facilities must be provided from the commencement of the project, reflecting the numbers of operatives on site and the nature of the work being undertaken. The Construction Phase Plan must additionally describe how these facilities will be maintained. |  |
| Ground conditions |  | Drawings with statutory undertaker detail will be provided to the Principal Contractor by the Client however, the contractor is responsible for identifying all underground services and for protecting them during the works. |  |
| Existing structures |  | The south of the site is bound on the north side by the River Ribble and on the south side by Moorland School. The Northern area of the site was the former Cross Hills Quarry and it is bound by a chemical factory to the south and rural land to the north. |  |
| Hazardous materials |  | The following hazardous substances have been highlighted in the surveys provided. The Principal Contractor is required to assess the risks from the substances and ensure that suitable controls are implemented: None Identified |  |
| Health risks arising from Principal Contractor’s activities |  | The park is to remain ‘open’ with uninterrupted access Therefore the contractor must ensure controls are put in place to prevent significant risks. |  |
| SECTION 4 |  | SIGNIFICANT DESIGN AND CONSTRUCTION HAZARDS |  |
| Design assumptions and control measures |  | (Principles of design) Designers should ensure that risks are at best, eliminated, and at worst, that they are controlled. The Principal Contractor will need to recognise and identify the hazards associated with the nature and location of the work and should put in practice suitable controls to minimise risks to the workforce and the general public. |  |
| Significant and principal hazards |  | - Utilities - General Public - Weather - Fragile materials. - Abrasive materials/chemical burn materials - Vehicle Movements - Electrical. - Collapse or overturning. - Slips, trips or falls. - Working from heights - Falls from height. - Inadequate guardrail - Lack of adequate tethering. - Lack of toe boards. - Struck by moving, flying or falling object. - Ladder defects. - Slow rescue of person suspended on harness. - Injury/Damage caused by power tools. - Injury/Damage caused by manual tools. - Lifting/manual handling - Dust - Noise - Guards and fail safe’s to equipment - PPE, including eye and ear protection |  |
| Materials requiring particular precautions |  | None expected |  |
| SECTION 5 |  | EMERGENCY CONTACT NUMBERS |  |
| Gas (Cadent) |  | Tel: 0800 111 999 |  |
| Electricity North West |  | Tel: 0800 195 4141 |  |
| British Telecom |  | Tel: 100 |  |
| Environment Agency |  | Tel: 0800 807 060 |  |

Ribble Valley Borough Council

Brungerley Park Improvements

BANKERS LETTER

BANKERS LETTER

Date:

Bank

Dear Sirs

# Re: Bankers Reference

I confirm that, by authority of this letter, I give permission for:

Council

To be supplied with a current bank reference in respect of:

Account Name:

Account Number:	 	 			 (12345678)

Sort Code:			 			 (99-99-99)

Branch:

Any costs associated with this reference are to be met by us.

Yours faithfully

# FORM OF AGREEMENT

THIS AGREEMENT made the	day of	20

BETWEEN

of

in the County of	(hereinafter called “the Employer”)

and

of

in the County of	(hereinafter called “the Contractor”)

WHEREAS the Employer is desirous that certain Works should be constructed, namely the Permanent and Temporary Works in connection with  Brungerley Park Improvements and accepted a Tender by the Contractor for the construction and completion of such Works.

NOW THIS AGREEMENT WITNESSETH as follows:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Conditions of Contract hereinafter referred to.

2.	The following documents shall be deemed to form and be read and construed as part of this Agreement, namely:

(a)	the said Tender and the written acceptance thereof;
(b)	the Drawings;
(c)	the Conditions of Contract;
(d)	the Specification;
(e)	the priced Bill of Quantities.

3.	In consideration of the payments to be made by the Employer to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Employer to construct and complete the Works in conformity in all respects with the provisions of the Contract.

4.	The Employer hereby covenants to pay to the Contractor in consideration of the construction and completion of the Works the Contract Price at the times and in the manner prescribed by the Contract.

IN WITNESS whereof the parties hereto have caused this Agreement to be executed the day and year first above written.

SIGNED on behalf of the said	Limited/PLC (the Employer)

Signature		Signature

Position		Position

In the presence of		In the presence of

SIGNED on behalf of the said	Limited/PLC (the Contractor)

Signature		Signature

Position		Position

In the presence of		In the presence of

or

SIGNED [and SEALED*] AND DELIVERED AS A DEED by the said

Limited/PLC (the Employer)

in the presence of

or

SIGNED [and SEALED*] AND DELIVERED AS A DEED by the said

Limited/PLC (the Contractor)

in the presence of

* Delete as appropriate

# CONDITIONS OF CONTRACT

The Conditions of Contract shall be the “Infrastructure Conditions of Contract Measurement Version August 2011” based on the ICE Conditions of Contract as approved by the Association of Consulting Engineers and the Civil Engineering Contractors Association.

Modifications to Clauses

Clause 60(9)(b):	Line 2 delete “no later than five days after” and insert “by”

Line 3 after “sub-clause (2)” insert “the Contractor’s monthly statement given under sub-clause 60(1) shall be the payment notice or, in the event that no monthly statement was given by the Contractor,”

Clause 60(10):	Side Heading. Delete “withhold payment”. Insert “pay less”

Line 2 after “is to” insert “pay less than or”

Line 2 delete “after the final date for payment”
Line 2 delete “of” and replace with “from”

Line 5 after “specifying the “ delete the remainder of the sentence and insert “sum that the Employer considers to be due on the date the notice is served and the basis on which that sum is calculated.”

Clause 71	Heading and side heading – delete”2007” insert “2015”.

Replace Clause 71(1) and (2) with the following:

71(1)	In this Clause:

(a)	“the Regulations” means the Construction ( Design and Management) Regulations 2015 or any statutory re-enactment or amendment thereof for the time being in force

(b)	“Construction Phase Plan” means the document recording the health and safety arrangements site rules and any specific measures for construction work as described in regulation 2(1) of the Regulations and prepared in accordance with regulation 12 of the Regulations

(c)	“Principal Designer” and “Principal Contractor” mean the persons so described in regulation 2(1) of the Regulations

(2)	Where and to the extent that the Regulations apply to the Works and

(a)	the Engineer is appointed as Principal Designer and/or

(b)	the Contractor is appointed Principal Contractor

Then in taking any action as such they shall state in writing that the action is being taken under the Regulations.

71(3)(a) and (b) replace the words “CDM Co-ordinator” with the words “Principal Designer”.

Appendix – Part 1

Paragraphs 16 (Target Cost) 19 (Term) and 20 (Measurement and Ground Investigation) – Delete “CDM Co-ordinator” and insert “Principal Designer”

# SPECIAL CONDITIONS OF CONTRACT

73.	The employer shall be entitled to cancel the contract and to recover from the contractor the amount of any loss resulting from such cancellation if the contractor shall have offered or given or agreed to give to any person any gift or consideration of any kind as an inducement or reward for doing or forbearing to do or for having done or forborne to do any action in relation to the obtaining or execution of the contract or any other contract with the employer or for showing or forbearing to show favour or disfavour to any person in relation to the contract or any other contract with the employer or if the like act shall have been done by any person employed by the contractor or acting on its behalf (whether with or without the knowledge of the contractor) or if in relation to any contract with the employer the contractor or any person employed by it or acting on its behalf have committed any offence under the Prevention of Corruption Acts 1889–1916, or shall have given any fee or reward, the receipt of which is an offence under subsection (2) of Section 117 of the Local Government Act 1972.

74.	The contractor shall keep proper wages books and time sheets showing the wages paid to and time worked by the workpeople in his employ in and about the execution of the contract, and such wages books and time sheets shall be produced whenever required for the inspection of any officer authorised by the employer.

75.	Where an appropriate British Standard Specification or British Standard Code of Practice issued by the British Standards Institution is current at the date of the tender, all goods and materials used or supplied in the execution of the contract and all workmanship shall be in accordance with that standard.

76.	Whenever under the contract any sum of money shall be recoverable from or payable by the contractor, such sum may be deducted from or reduced by the amount of any sum or sums then due or which at any time thereafter may become due to the contractor under the contract or any other contract with the employer.

77.	This contract shall be carried out on a firm price basis and no adjustment shall be made to any amounts payable by the employer to the contractor in accordance with Clause 60 regardless of any variations in the costs of labour, plant or materials during the contract period.

78.	CONFIDENTIALITY

78.1	Subject to clause 78.2, the parties shall keep confidential all matters relating to this agreement and shall use all reasonable endeavours to prevent their Representatives from making any disclosure to any person of any matters relating hereto.

78.2	Clause 78.1 shall not apply to any disclosure of information:

(a)	required by any applicable law, provided that clause 78.1 shall apply to any disclosures required under the FOIA or the Environment Information Regulations;

(b)	that is reasonably required by persons engaged by a party in the performance of such party's obligations under this agreement;

(c)	where a party can demonstrate that such information is already generally available and in the public domain otherwise than as a result of a breach of clause 78.1;

(d)	by the Employer of any document to which it is a party and which the parties to this agreement have agreed contains no commercially sensitive information;

(e)	to enable a determination to be made under clause 66 of the Infrastructure Conditions of Contract Measurement Version 2011 as amended.

(f)	which is already lawfully in the possession of the receiving party, prior to its disclosure by the disclosing party;

(g)	by the Employer to any other department, office or agency of the Government; and

(h)	by the Employer relating to this agreement and in respect of which the Contractor has given its prior written consent to disclosure.

78.3	On or before the completion of the works the Contractor shall ensure that all documents and/or computer records in its possession, custody or control which relate to personal information of the Authorities' employees, rate-payers or service users, are delivered up to the Employer or securely destroyed.

79.	The contractor shall comply with all appropriate statutes, regulations, codes and agreements (including amendments thereto) relating to health, safety and welfare including, where applicable, The Borough of Ribble Valley, health and safety at work safety policy and codes of practice.

80.	If, during the execution of the works, the contractor or his subcontractors discover materials or structures containing asbestos, they shall immediately report the matter to the engineer. The engineer shall issue instructions in regard to the treatment, removal and disposal of the asbestos. Such instruction may require the contractor to permit the removal of the asbestos by a third party. Any such third party, for insurance purposes, shall be a person for whom the employer is responsible and shall not be a subcontractor to the contractor.

If, in the opinion of the engineer, compliance with the provisions of this clause has involved the contractor in direct loss and/or expense for which he would not be reimbursed by a payment made under any other provision of this contract, then the engineer shall ascertain the amount of such loss and/or expense, and this amount shall be added to the contract sum.

81.	FREEDOM OF INFORMATION

81.1	The contractor acknowledges that the employer is subject to the requirements of the Freedom of Information Act 2000 (FOIA) and the Environmental Information Regulations 2004and shall assist and co-operate with the Employer (at the Contractor's expense) to enable the employer to comply with these information disclosure requirements.

81.2	The contractor shall and shall procure that its Sub-Contractors shall:

(a)	transfer the Request for Information to the employer as soon as practicable after receipt and in any event within two Working Days of receiving a Request for Information;

(b)	provide the employer with a copy of all Information in its possession or power in the form that the employer requires within five Working Days (or such other period as the Employer may specify) of the employer requesting that Information; and

(c)	provide all necessary assistance as reasonably requested by the employer to enable the employer to respond to a Request for Information within the time for compliance set out in section 10 of the FOIA or regulation 5 of the Environmental Information Regulations.

81.3	The employer shall be responsible for determining at its absolute discretion whether commercially sensitive information and/or any other Information:

(a)	is exempt from disclosure in accordance with the provisions of the FOIA or the Environmental Information Regulations; and/or

(b)	 is to be disclosed in response to a Request for Information under the FOIA or the Environmental Information Regulations.

81.4	In no event shall the contractor respond directly to a Request for Information unless expressly authorised to do so by the employer.

81.5	The contractor acknowledges that the employer may, acting in accordance with the Secretary of State for Constitutional Affairs' Code of Practice on the discharge of public authorities' functions under Part 1 of FOIA (issued under section 45 of the FOIA, November 2004), be obliged under the FOIA or the Environmental Information Regulations to disclose Information:

(a)	without consulting with the contractor; or

(b)	following consultation with the contractor and having taken its views into account,

provided always that where clause 81.5(b) applies the employer shall, in accordance with any recommendations of the Code, take reasonable steps, where appropriate, to give the Contractor advanced notice, or failing that, to draw the disclosure to the Contractor's attention after any such disclosure.

81.6	The Contractor shall ensure that all Information produced in the course of the agreement or relating to the agreement is retained for disclosure and shall permit the Employer to inspect such records as requested from time to time.

81.7	The Contractor acknowledges that any lists or Schedules provided by it outlining Confidential Information are of indicative value only and that the Employer may nevertheless be obliged to disclose Confidential Information in accordance with clause 81.5.

82.	DATA PROTECTION

82.1	The Contractor shall (and shall procure that any of its Contractor's Personnel involved in the provision of the agreement shall) comply with any notification requirements under the DPA and both Parties shall duly observe all their obligations under the Data Protection Act 2015 (DPA), which arise in connection with the agreement.

82.2	Notwithstanding the general obligation in clause 82.1, where the Contractor is processing Personal Data as a Data Processor for the Employer, the Contractor shall ensure that it has in place appropriate technical and contractual measures to ensure the security of the Personal Data (and to guard against unauthorised or unlawful processing of the Personal Data and against accidental loss or destruction of, or damage to, the Personal Data), as required under the Sixth Data Protection Principle in Section 40 of the DPA; and

(a)	provide the Employer with such information as the Employer may reasonably require to satisfy itself that the Contractor is complying with its obligations under the DPA;

(b)	promptly notify the Employer of any breach of the security measures required to be put in place pursuant to clause 82.2; and

(c)	ensure it does not knowingly or negligently do or omit to do anything which places the Employer in breach of the Employer's obligations under the DPA.

82.3	The provisions of this clause shall apply during the continuance of the agreement and indefinitely after its expiry or termination.

83.	WAIVER

No forbearance or delay by either party in enforcing its respective rights will prejudice or restrict the rights of that party, and no waiver of any such rights or of any breach of any contractual terms will be deemed to be a waiver of any other right or of any later breach. In particular, but without limitation to the generality of the foregoing, any prior acceptance or approval communicated by the Employer to the Contractor in respect of the Services or any omission on the part of the Employer to communicate such prior acceptance or approval shall not relieve the Contractor of its obligations to deliver the Services in accordance with the provisions of this agreement.

84.	CUMULATION OF REMEDIES

Subject to the specific limitations set out in this agreement, no remedy conferred by any provision of this agreement is intended to be exclusive of any other remedy except as expressly provided for in this agreement and each and every remedy shall be cumulative and shall be in addition to every other remedy given thereunder or existing at law or in equity by statute or otherwise.

85.	SEVERABILITY

If any of the provisions of this agreement is judged to be illegal or unenforceable, the continuation in full force and effect of the remainder of them will not be prejudiced.

86.	PARTNERSHIP OR AGENCY

Nothing in this agreement shall be construed as constituting a partnership between the parties or as constituting either party as the agent of the other for any purpose whatsoever except as specified by the terms of this agreement.

87.	THIRD PARTY RIGHTS

No term of this agreement is intended to confer a benefit on, or to be enforceable by, any person who is not a party to this agreement

88.	PUBLICITY

The Contractor shall not:

(i)	make any press announcements or publicise this agreement or its contents in any way; or

(ii)	use the Employer's name or brand in any promotion or marketing or announcement of orders,

without the prior written consent of the Employer, which shall not be unreasonably withheld or delayed].

89.	ENTIRE AGREEMENT

This agreement, the schedules and the documents annexed to it or otherwise referred to in it and including but not limited to the Infrastructure Conditions of Contract Measurement version  2011 as amended and The Specification for Highways Works 1998 contain the whole agreement between the parties relating to the subject matter hereof and supersede all prior agreements, arrangements and understandings between the parties relating to that subject matter.

90.	COUNTERPARTS

This agreement may be executed in any number of counterparts, each of which when executed and delivered shall constitute an original of this agreement, but all the counterparts shall together constitute the same agreement. No counterpart shall be effective until each party has executed at least one counterpart.

91.	GOVERNING LAW AND JURISDICTION

91.1	This agreement and any dispute or claim arising out of or in connection with it or its subject matter shall be governed by and construed in accordance with the law of England and Wales.

91.2	The parties irrevocably agree that the courts of England and Wales shall have exclusive jurisdiction to settle any dispute or claim that arises out of or in connection with this agreement or its subject matter.

# LIST OF SUBCONTRACTORS AND THEIR ROLES IN THE PROPOSED SCHEME

# SPECIAL REQUIREMENTS IN RELATION TO THE CENTRAL ELECTRICITY GENERATING BOARD AND AREA ELECTRICITY BOARDS

1.	In these special requirements the following expressions shall have the meanings assigned to them.

1.1	“Board” means the Central Electricity Generating Board and/or the Area Electricity Board(s) or any successors to these Boards.

1.2	“Board’s engineers” means the District Manager of the Generating Board and/or the Area Board concerned or his nominated representative.

1.3	“Plant or equipment” means any plant equipment or gear machinery apparatus or appliance or any part thereof as defined in the Construction (General Provisions) Regulations 1961 and the Construction (Lifting Operations) Regulations 1961.

2.	The work should be carried out to conform with the requirements of the Health and Safety Executive Guidance Note No GS6 “Avoidance of Danger from Overhead Electric Cables” and the National Joint Utilities group document “Recommendations on the Avoidance of Danger from Underground Electricity Cables”.

3.	3.1	Except under such restrictions as the Board’s engineer may impose for the safety of persons and the protection of property a distance of 15 metres shall be maintained at all times between any part of any plant or equipment or anything connected to such plant and equipment (eg the jib of a crane hoist rope load, etc) and any part of the Board’s electric lines where these lines are carried on wood poles. Excavation spoil must not be dumped or accumulated so as to cause infringement of these distances. The permission of the Board’s engineers must be obtained in writing before plant or equipment is operated or work of any kind is carried out within the above distances.

3.2	The contractor shall give at least 14 days’ notice to the Board’s engineers of the dates upon which it is intended to operate plant or equipment or carry out any work for which permission has been given by the Board’s engineers under paragraph 3(i). Such operations or work shall only be carried out in the presence of the Board’s engineers unless notice shall have been obtained in writing from the Board’s engineers that they do not require to be present.

3.3	In the event of the Board requiring work to be executed on the overhead electric lines or supports during the period of the contract, the contractor shall afford all facilities to the Board or its contractors and the contractor shall amend his programme of working to suit any and all requirements of the Board during such period of working.

3.4	The contractor shall consult the Board’s engineers as early as possible and such consultation shall not be less than fourteen days before it is proposed to commence work to ascertain whether any underground electricity cables or apparatus will be affected by the proposed work in which event the contractor shall make all necessary arrangements with the Board’s engineer to safeguard the cables or apparatus.

3.5	Work should not be carried out in the immediate vicinity of the overhead lines during periods of poor visibility. If this is not reasonably practicable, additional precautions must be taken to ensure maintenance of the appropriate safety clearance.

4.	The above requirements will not relieve the contractor of any responsibility for taking every precaution to avoid risk to persons or damage to property including compliance with Regulations 44 (2) of the Construction (General Provisions) Regulations 1961.

# SPECIAL REQUIREMENTS IN RELATION TO Cadent Gas Ltd

## GENERAL CONDITIONS AND PRECAUTIONS TO BE TAKEN WHEN CARRYING OUT WORK ADJACENT TO CADENT GAS LTD DISTRIBUTION APPARATUS

These general conditions and precautions apply to the distribution system of Cadent Gas Ltd and are additional to the requirements to be observed when carrying out work adjacent to the high pressure transmission and feedstock pipeline system (where relevant a copy of the latter conditions is attached hereto).

1.	On request, Cadent Gas Ltd will give approximate locations of mains according to their records. These records do not normally show the positions of service pipes from the mains to properties nor are they necessarily accurate or complete. No person or company shall be relieved from liability for damage caused by reason of the actual positions and/or depths being different from those shown on the plan. Any special requirements relative to our plant will be indicated. National Grid Gas PLC staff will visit any site at reasonable notice to assist in the location of gas plant and advise any precautions that may be required to obviate any damage.

2.	In order to achieve safe working conditions adjacent to any apparatus the following should be observed:

2.1	All gas apparatus should be located by hand digging prior to the use of mechanical excavation.

2.2	During construction work where heavy plant may have to cross the line of a gas main, and the main is not under a carriageway of adequate standard of construction, crossing points should be suitably reinforced with sleepers, steel plates or a specially constructed RC raft as necessary. These crossing points should be clearly indicated and crossing the line of the gas main at other places should be prevented. Cadent Gas Ltd staff will advise on the type of reinforcement necessary.

2.3	No explosives to be used within 32 metres of any Cadent Gas Ltd pipe without prior consultation with Cadent Gas Ltd.

2.4	Where it is proposed to carry out piling within 15 metres of any pipe, Cadent Gas Ltd should be consulted so that affected pipes may be surveyed.

3.	3.1	Where excavation of trenches adjacent to any pipe affects its support, the pipe must be supported to the satisfaction of the Cadent Gas Ltd engineer.

3.2	Where a trench is excavated crossing or parallel to the line of the pipe, the backfill should be adequately compacted to prevent any settlement which could subsequently cause damage to the main. In special cases, it may be necessary to provide permanent support to a pipe which has been exposed over the length of the excavation before backfilling and reinstatement is carried out. There should be no concrete backfill in contact with the pipe.

4.	No apparatus should be laid over and along the line of a gas pipe irrespective of clearance. A minimum clearance of 300 millimetres should be allowed between any plant being installed and an existing gas pipe to facilitate repair, whether the adjacent plant be parallel to or crossing the gas pipe. No manhole or chambers shall be built over or round a gas pipe.

5.	Where a Cadent Gas Ltd pipe is coated with special wrapping and this is damaged, even to a minor extent, Cadent Gas Ltd must be notified so that repairs can be made. If the damage is of a minor nature and can be repaired by our emergency team, no charge will be made for the repair, provided that the damaged part is not backfilled and access readily given. In the case of any material damage to the pipe itself causing leakage, or weakening of the mechanical strength of the pipe, the necessary remedial work will be charged.

6.	If leakage is caused by a contractor or subcontractor and an escape of gas is evident, the following action should be taken at once:

6.1	Remove all personnel from the immediate vicinity of the escape.

6.2	Inform Cadent Gas Ltd at the telephone number given.

6.3	Prevent any approach by the public, prohibit smoking, extinguish all naked flames or other source of ignition for at least 15 metres from the leakage.

6.4	Assist Cadent Gas Ltd personnel, police or fire services as may be requested.

# SPECIAL REQUIREMENTS IN RELATION TO OPENREACH LTD

1.	Before commencing any work or moving heavy plant or equipment over any portion of the site, the contractor shall confirm details of Openreach Ltd’ underground plant within the site with the appropriate telephone number.

2.	Where such details show that the contractor’s works or the movements of plant or equipment may endanger Openreach Ltd’ plant, the contractor must give the telephone manager at least one week’s notice of the date on which it is intended to commence such work of movement of plant and equipment in order that the presence of buried plant can be indicated by markers to be supplied by British Telecommunication and placed by the contractor under the supervision of a Openreach Ltd’ representative. The contractor shall ensure that Openreach Ltd’ plant is protected from damage.

3.	In the event of a Openreach Ltd’ marker being disturbed for any reason, it shall not be replaced other than in the exact position and to its former depth unless the repositioning is carried out at the direction and under the supervision of a Openreach Ltd’ representative.

4.	The above requirements do not relieve the contractor of any of his obligations under the contract.

5.	Raising of frames and covers:

5.1	Carriageway – unless expressly stated otherwise in the contract, Openreach Ltd has reserved the right to adjust its own apparatus within the carriageway. It will be the contractor’s responsibility to allow for this in his rates and programme accordingly as no claim for delays or additional cost will be entertained against this item.

5.2	Footway – additional specification Clause 517A refers.

# SPECIAL REQUIREMENTS IN RELATION TO UNITED UTILITIES, YORKSHIRE WATER AND THE ENVIRONMENT AGENCY (EA)

1.	The contractor is required to comply with the provision of the Rivers Prevention of Pollution Acts 1951 and 1961 or the Control of Pollution Act 1974 and any bylaws made thereunder, the Land Drainage Act 1976 and any bylaws made thereunder, and be responsible for obtaining any licences to abstract water for use on the works in accordance with the requirements of the Water Resources Act 1963 and any subsequent enactment.

2.	The contractor shall, before carrying out any temporary diversions or temporary works in the main channels of any river, stream, or water course, submit details of such work to the engineer for his approval and the approval of the engineer to the EA before the works are commenced.

3.	The contractor shall give seven days’ notice of any works authorised by the above approval to the area engineer of the EA.

4.	The contractor shall take all precautions during the carrying out of the works so as not to obstruct, impede or interfere with the flow of water in, into or out of the river, stream or watercourse and shall maintain the flow of any river, stream or watercourse at all times.

5.	The contractor shall take all necessary precautions to secure the efficient protection of all rivers, streams, waterways, lakes and the like against silting, erosion and pollution which may be likely to contaminate water supplies or to cause injury to fish or plant life.

6.	On completion of the works, any damage to the banks or the river channel shall be made good to the satisfaction of the engineer and the engineer of the EA and the banks and the river shall be left in a clean and tidy condition.

7.	The contractor will be responsible for making his own arrangements for obtaining mains water for the works and he shall comply with all local conditions regarding the use of water.

All details of the point of extraction receiving apparatus, abstraction methods, draw-off rates and times shall be agreed with and confirmed in writing to the engineer and the EA.

The contractor shall provide constant attendance when water is being drawn off any hydrant.

8.	Stand pipes will be loaned by district offices, subject to the payment of a deposit which will be refunded on the safe return of the apparatus on completion of the works.

Hydrants shall be inspected on completion of the works and it will be a condition of these arrangements to withdraw water that the cost of repairing damage to apparatus will be reimbursed by the contractor.

Any charges for water shall be borne by the contractor.

9.	The above requirements do not relieve the contractor of any of his obligations under the contract.

# SPECIFICATION

1.	The Specification referred to in the tender documents shall be the “Specification for Highway Works” 1998 including all following amendments.

2.	The Specification shall be modified and extended in accordance with the following:

2.1	A substitute clause, as indicated by the suffix “S”, is an amendment of a clause in the Specification for Highway Works and supersedes the whole of the clause.

2.2	An additional clause as indicated by the suffix “A”, supplements the clauses of the Specification for Highway Works and has a number subsequent to the last one of the appropriate series of those clauses, relevant to the subject matter covered.

2.3	A cancelled clause, as indicated by the suffix “C”, is a clause entirely deleted from the Specification for Highway Works.

2.4	Insofar as any substitute or additional clause may conflict or be inconsistent with any provision of the 1998 edition of the Specification for Highway Works and any supplement, the substitute or additional clause shall always prevail.

2.5	Any reference in the contract to a clause number shall refer to any substituted version of the clause within the contract.

2.6	The British Standards and other references set out in the Specification are included for information only. The editions listed may have been revised and reference to British Standards and other publications in specification clauses shall be deemed to refer to the editions with amendments, current at the date of invitation to tender.

2.7	Any clauses in this Specification which relate to work or materials not required by the works shall be deemed not to apply.

3.	3.1	An index of substitute, additional or cancelled clauses is contained at page 16.

# LIST OF SUBSTITUTE, ADDITIONAL OR CANCELLED CLAUSES

CLAUSE NO	TITLE	PAGE NO

SERIES 100 – GENERAL

116S	Privately and publicly-owned services	22

122A	Existing carriageways to be kept clean and clear	22

123A	Interference with land interests	22

124A	Interference with access to properties	23

125A	Procedure for complaints and claims for damages	23

126A	Protection against damage	23

127A	Tidiness of site	23

SERIES 500 – DRAINAGE AND SERVICE DUCTS

515A	Resetting or replacing manhole frames on public sewers	23

516A	Resetting or replacing gully grates and frames	25

517A	Relevelling of Telecom frames and covers in carriageway using resin edging bedding and resin mortar	25

116S (Substitute Clause)

Privately and publicly-owned services

1.	The contractor is responsible for making arrangements with the statutory undertakers and public authorities concerned for the phasing into his programme of works of all work which need to be done by them or their contractors concurrently with the works.

2.	The contractor shall take any and all measures reasonably required by any public or statutory authority for the support and full protection of its mains, pipes, cables and other apparatus during the progress of the works, and shall construct and provide to the satisfaction of the authority concerned, all works necessary for the prevention of damage or interruption of services. If, in the execution of works, by reason of any subsidence caused by, or any act of neglect or default of, the contractor, any damage to any apparatus or any interruption of, or delay to the provision of, any service is caused, the contractor shall bear and pay the cost reasonably incurred by the authority concerned in making good such damage, and shall make full compensation to the authority for any loss sustained by reason of such interruption or delay.

3.	The contractor shall, at all times during the progress of the works, afford facilities to properly accredited agents of any public or statutory authority for access to all or any of their apparatus situated in or under the site, as may be necessary for inspecting, reporting, maintaining, removing, renewing or altering such apparatus in connection with the construction of the Works or for any other purpose whatsoever.

4.	The positions of statutory undertakers’ mains and services and public authorities drains and sewers on the drawings have been based on information extracted from the records of the various bodies and must be regarded as approximate only. The engineer does not guarantee either the accuracy of the information or that the location of such apparatus is as shown on the drawings, and no warranty must be implied as the position, depth, size or gradient thereof. The contractor must make his own enquiries of the statutory undertakers and public authorities and satisfy himself as to the exact position of such apparatus and the depth, size and gradient thereof.

5.	If any privately owned service for water, electricity, drainage, etc passing through the site is affected by the works, then the contractor shall locate it and provide a satisfactory alternative service before cutting the existing service.

122A (Additional Clause)

Existing carriageways to be kept clean and clear

All carriageways within and surrounding the working site which are being used by the contractor’s, his subcontractors’ or his suppliers’ vehicles for the works shall be kept clean and clear of all dirt, mud and rubbish by the contractor. The contractor shall provide, maintain and use as necessary, suitable equipment, including mechanical road sweepers, throughout the course of the works. The Engineer shall have the right to stop the works if it is considered that dirt, mud or anything deposited by the contractor or those working for him or his suppliers creates a hazard to traffic. In this respect, the attention of the contractor is drawn to the need to avoid fouling road surfaces by spillage of oil or fuel at any time during the course of his works and, in particular, when refuelling equipment.

123A (Additional Clause)

Interference with land interests

The contractor shall confine his constructional operations within the site, or such other areas of land as may be negotiated and shall instruct his employees and subcontractors not to trespass.

124A (Additional Clause)

Interference with access to properties

Before interfering with existing accesses to any property, the contractor shall provide satisfactory alternative arrangements. The contractor shall notify the engineer and the relevant occupiers in writing 14 days in advance of any such interference.

125A (Additional Clause)

Procedure for complaints and claims for damages

1.	Details of all claims or notices of intended claims which the contractor may receive in respect of matters against which he is required by the contract to indemnify the employer shall be notified without delay to the engineer, who shall, likewise, pass the contractor any such claims or notices which may be submitted directly to the engineer or employer.

2.	A similar exchange of information shall also be made in respect of all complaints which may be received.

3.	The contractor shall notify the engineer in writing immediately following any damage or injury arising out of the execution of the works.

126A (Additional Clause)

Protection against damage

1.	The contractor shall take all necessary precautions to avoid causing any damage to roads, lands, properties, trees and other features, and during the currency of the contract, shall deal promptly with any complaints by owners or occupiers.

2.	Where any portion of the works is close to, across, or under any existing apparatus of public utilities or other authorities, bodies or parties, the contractor shall temporarily support and work round, under or adjacent to all apparatus in a manner designed to avoid damage, leakage or danger and to ensure uninterrupted operation.

3.	Should any leakage or damage be discovered, the contractor shall at once notify the engineer and the statutory authority or owner concerned and the contractor shall afford every facility for the repair or replacement of the apparatus affected.

127A (Additional Clause)

Tidiness of site

The contractor shall be responsible for the proper upkeep and maintenance of the site and works and all materials and equipment shall be positioned, stored and stacked in an orderly and safe manner.

515A (Additional Clause)

Resetting or replacing manhole frames on public sewers

To be read in conjunction with Drawing No 1.

1.	General

1.1	Prior to the removal of the frame:

(a)	Where the sewer is fast flowing

The sewer must be protected from debris by placing timber across the benching and then by covering this with plastic. If this is not practical, it must be reported to the Main Drainage section prior to commencement of work.

On completion of the work, the protection must be carefully removed, allowing no debris to pass to sewer.

(b)	Where the sewer is slow running or dry

Work may proceed without the above protection but the channel and adjacent pipework must be cleaned out immediately after the work has been completed.

1.2	The frame, along with any unstable brickwork (maximum three courses), must be removed. If the brickwork below this level is in a poor condition, report to the engineer for further instructions.

1.3	Replace the necessary brickwork 225mm thick with the top course laid as headers.

1.4	Place the necessary packing (maximum thickness 40mm) and bed the frame onto Class M1 mortar and then back up the frame with granolithic concrete leaving the top of the haunch 50mm below the finished road surface.

The whole of the frame shall rest on packing mortar or concrete. Voids and spaces must not be left unfilled.

1.5	Lay the bitmac as temporary reinstatement.

2.	Additional Requirements for Work in Highways

2.1	The work must be signed in accordance with Clause 117 of this Specification.

2.2	Where the manhole is in the carriageway, a quick setting mortar and bedding compound will be used so that the road can be reopened as soon as possible.

3.	Materials

Brickwork: Class B engineering bricks.

Manhole cover and frame: Ductile iron MA60, 600mm square clear opening.

Mortar: Monoset or GP Fastset.

Granolithic concrete: To requirements of CP 204: Part 2.

Packing: Pieces of sound stone or slate (min size 300mm x 150mm).

Quick setting compounds: Manufactured by Ronacrete, Ilford, Essex, or similar approved.

Bitmac: 10mm nominal size dense bitmac wearing course BS 4987.

4.	Fixing Tolerances

The cover must be set between 0 to +6mm.

516A (Additional Clause)

Resetting or replacing gully grates and frames

Materials – as for Clause 515A.

To be read in conjunction with Drawing No SD5.

517A (Additional Clause)

Relevelling of Telecom frames and covers in carriageway using resin edging bedding and resin mortar

1.	General

This Specification describes the method that shall be employed by local authorities whenever that authority raises or lowers the level of, or otherwise has cause to replace, British Telecom carriageway frames and covers to conform to the road surface level. The work shall be carried out using quick setting materials in order to allow completion of the operation and reopening to traffic within a working day. These materials (see paragraphs 2, 3 and 4) will be supplied by British Telecom.

2.	Materials

2.1	Resin bedding

Description

A three component polyester resin compound comprising a translucent liquid, a white powder hardener and a filler. The complete pack is readily divisible into two half packs for ease of mixing which should be carried out using a clean dry polyethylene bucket and a clean dry stick.

Half pack mixing

Pour the resin from one oblong can into the bucket and gradually add the white powder hardener from one of the small plastic bags whilst stirring continuously with the stick until free from lumps. Add and mix the filler from one of the larger plastic bags in a similar manner until a uniform consistency is achieved.

2.2	Resin Mortar

Description

A three component polyester resin compound comprising a translucent liquid, a white powder hardener and a sand filler. The complete pack is readily divisible into two half packs for ease of mixing which should be carried out using a polyethylene bucket, a stick, a mixing board and a trowel or shovel, all of which shall be clean and dry.

Half pack mixing

Empty the sand from one of the larger plastic bags onto the mixing board. Pour the resin from one oblong can into the bucket and gradually add the white powder hardener from one of the small plastic bags whilst stirring continuously with the stick until free from lumps. Add the liquid to the sand and thoroughly mix with the trowel or shovel.

NOTE: Once the hardener has been added, both materials have a working life of approximately twenty minutes and the initial set will occur after approximately thirty minutes.

2.3	Quantity of materials required

Single rectangular cover installation – TWO packs of resin bedding.

Two rectangular or four triangular cover installation – THREE packs of resin bedding.

The quantity of resin mortar will vary according to the amount of raising required.

3.	Safety precautions

When mixing and/or using resin bedding or resin mortar, the following precautions should be observed:

3.1	Barrier cream should be applied to the hands and forearms if exposed, before handling the materials.

3.2	Disposable gloves should be worn.

3.3	Mixing should be carried out in a well-ventilated place but shielded against any wind.

3.4	Eyeshields should be worn during the mixing stage to protect the eyes against the white powder hardener which contains a small proportion of peroxide.

3.5	An ori-nasal type respirator fitted with a dust and organic vapour filter should be worn.

3.6	After use, all soiled containers, waste and gloves should be disposed of in a refuse bin.

NOTE: All tools should be cleaned immediately after use. Any resin remaining in the bucket should be allowed to solidify when it can be removed easily and safely by flexing the bucket.

4.	Method of relevelling

NOTE: When British Telecom covers are lifted, removed or replaced, it is important that the correct keys are employed to avoid damage and accidents. The appropriate keys will be loaned by the British Telecom upon request.

4.1	Raise one end (rectangular) or corner (triangular) of the cover and hold open by supporting it on a suitable block of wood. Test for gas in the chamber. Should the test indicate the presence of gas, replace the cover and immediately use the Freefone 111 services. If the chamber is free from gas, lift out the cover(s) and removable grid(s) when fitted, then proceed as follows:

4.2	Excavate an area approximately 150mm wide around the frame and to the depth of the frame taking care not to damage the frame or walls of the chamber.

4.3	Remove the frame. If of the rectangular type and in the opinion of the British Telecom representative to be damaged or any other way unsuitable for reuse, the frame and cover shall be replaced with an appropriate triangular type supplied by the British Telecom.

4.4	Cut back the jointing chamber walls or shaft to a sound and reasonably level surface approximately 165mm below the carriageway surface. Where it is necessary to exceed this dimension, build up the walls or shaft to this level using bricks or quarry tiles bonded with resin mortar as shown on the attached plan.

4.5	Remove any old material from the underside of the frame and cut off any levelling screws flush with the underside of the frame.

4.6	Remove all foreign matter from the top of the chamber walls or shaft and, if wet, wipe off all surface water with a clean cotton rag.

4.7	Locate the frame square with the chamber walls or shaft and, by supporting it under the corners with pieces of broken tile or other suitable material, raise the frame until it is level with the carriageway surface.

4.8	Clean the cover and frame seatings, carefully replace the cover(s) and check for rocking. If necessary, adjust to eliminate any rock by providing similar supports under the long sides of the frame, particularly under any frame joints.

4.9	Remove the covers taking care not to disturb the frame.

4.10	On the inside of the chamber, face off the gap under the frame and any voids between the bricks or quarry tiles with resin mortar. DO NOT FORCE THE MORTAR UNDER THE FRAME – the purpose of the facing is to provide an inside shutter to contain the resin bedding.

4.11	Allow the mortar to develop initial set, which is indicated when it feels firm against finger pressure, then mix the resin bedding and pour it around the frame until the bedding just lips over the lower flange.

4.12	Check that the covers do not rock and/or foul the jointing chamber walls or removable grids. If either occurs take whatever corrective action is necessary and ensure that the cover and the frame seatings are free of dirt or spilt resin.

5.	Reinstatement

The sides of the excavation and frame shall be primed with bitumen emulsion and the space around the frame reinstated in accordance with the Engineer’s department.

Bill of Quantities

CLASS A: GENERAL ITEMS

| Number | Item Description | Unit | Quantity | Rate | Total |
| --- | --- | --- | --- | --- | --- |
|  | Contractual Requirements |  |  |  |  |
| A120 | Insurance of the Works | Sum | 1 |  |  |
| A130 | Insurance of Plant and materials | Sum | 1 |  |  |
| A140 | Insurance against damage to persons and property | Sum | 1 |  |  |
|  | Specified Requirements |  |  |  |  |
| A279.2 | Establishment of and removal of fencing. pedestrian barriers, safety signage, site barriers etc. ( Any signage within the highway to be in accordance with Chapter 8 of the traffic signs manual.) | Sum | 1 |  |  |
| A279.3 | Maintenance of the above safety measures for the duration of the works | Wks | 10 |  |  |
|  | Provisional Sums |  |  |  |  |
|  | Method Related Charges |  |  |  |  |
|  | Other associated costs to be inserted by the Tenderer in accordance with section 7 of C.E.S.M.M. 3 (Provisional) | Sum | 1 |  |  |
|  | Prime Cost Items |  |  |  |  |
|  | None |  |  |  |  |
| CLASS A Carried forward to Grand Summary |  |  |  |  |  |

CLASS E: EARTHWORKS

| Number | Item Description | Unit | Quantity | Rate | Total |
| --- | --- | --- | --- | --- | --- |
|  | Footway |  |  |  |  |
| E421.1 | Excavate and dispose of up to 60mm bitumen macadam patch footpath surfacing | m² | 975 |  |  |
| E421.2 | Excavate and dispose of sub base to existing footpath area, up to 60mm thick | m² | 975 |  |  |
| E421.3 | Take down and dispose of existing timber post and rail fence | m | 100 |  |  |
| CLASS E Carried forward to Grand Summary |  |  |  |  |  |

CLASS R: ROADS & PAVINGS

| Number | Item Description | Unit | Quantity | Rate | Total |
| --- | --- | --- | --- | --- | --- |
|  | Light Duty Pavements |  |  |  |  |
| R713 | Provide and lay MOT type 1 sub-base regulating layer to build up low areas, as required, place and compact in layers, depth up to 60mm. (Provisional Item for regulating). As shown on drawings 01a, 01b, 02 and 03. | tonnes | 50 |  |  |
| R783.2 | Provide and lay 40mm, 10mm dense base course to BS 4987 Part 1, Clause 6.5 with 150 pen bitumen binder. As shown on drawings 01a, 01b, 02 and 03. | m² | 975 |  |  |
| R783.3 | Provide and lay 20mm, 6mm dense base course to BS 4987 Part 1, Clause 7.5 with 150 pen bitumen binder. As shown on drawings 01a, 01b, 02 and 03. | m² | 975 |  |  |
| CLASS R – Roads and Pavings Carried forward to Grand Summary |  |  |  |  |  |

CLASS R: ROADS & PAVINGS

| Number | Item Description | Unit | Quantity | Rate | Total |
| --- | --- | --- | --- | --- | --- |
|  | Ancillaries |  |  |  |  |
| R841.1 | Provide and install 150 m x 38 mm tanalised timber edgings, including 50 x 50 x 600 mm long tanalised timber stakes at 900mm c/c, as per the detail on drawings 01a, 01b, 02 and 03. | m | 1300 |  |  |
| R841.2 | Provide and install ‘Kee Clamp’ post and twin rail, galvanised steel guard rail, or similar approved by the Engineer. Item to include all joints and concrete foundations as per the detail on drawings 01a, 01b, 02 and 03. | m | 500 |  |  |
| R841.3 | Provide and install galvanised mesh infill panels 50 x 50 x 10g, H470 x W1382, including brackets. | m | 250 |  |  |
| CLASS R - Ancillaries Carried forward to Grand Summary |  |  |  |  |  |

GRAND SUMMARY

| CLASS A: GENERAL ITEMS | Total |  |  |
| --- | --- | --- | --- |
| CLASS E: EARTHWORKS | Total |  |  |
| CLASS R: ROADS & PAVINGS – Light Duty Pavings | Total |  |  |
| CLASS R: ROADS & PAVINGS - Ancillaries | Total |  |  |
| SUB TOTAL |  |  |  |
| Contingency Sum at 10% | Sum |  |  |
| GRAND TOTAL CARRIED TO FORM OF TENDER |  |  |  |